## How to use
Gather Construction Progress Report Template
Free template by Gather - gatherinsights.com ¦ One spreadsheet, fewer reporting gymnastics.
How to use this workbook
| 1 | Set up the job | Open the Progress Report tab and fill in the yellow project setup cells: project name, contract value, reporting week and report date.
| 2 | Update weekly progress | Use the Weekly Data tab to enter planned %, actual %, actual cost, labour hours, plant hours, safety incidents and key notes for each reporting week.
| 3 | Review the report | The Progress Report tab pulls the selected reporting week into KPIs, charts and a client-ready summary. Formula cells are locked so the workbook is harder to break.
| 4 | Log risks and issues | Use the Issue & Risk Log for blockers, RFIs, delays, commercial issues and open actions. Overdue open actions are highlighted automatically.
| 5 | Use the example | The Worked Example tab shows a 12-week project with realistic planned vs actual movement, cost pressure and site notes.
What the report tells you
• Planned vs actual progress: whether the job is ahead or behind the agreed baseline.
• Cost pressure: whether actual cost is running ahead of earned value.
• Forecast: EAC and ETC give an early view of likely final cost if current efficiency holds.
• Evidence: notes, milestones, delays and issue logs keep the narrative tied back to site records.
CTA
Want this report built automatically from site diaries, allocations, photos and cost data? Book a demo.
Free template by Gather — https://www.gatherinsights.com

## Progress Report
Construction Progress Report
Dashboard + weekly narrative. Yellow cells are inputs; black cells are formulas.
| Project setup |  |  |  | Planned complete |  | Actual complete |  | Progress variance | Actual cost
| Project name | Project Alpha |  |  | 0% |  | 0% |  | 0% | 0
| Client | Client / employer
| Contract value (BAC) | 2400000
| Reporting week # | 8 |  |  | CPI |  | SPI |  | EAC | ETC
| Report date | 2026-06-30
| Prepared by | Your name
Executive summary
Overall status
Progress narrative
Cost narrative
Safety / quality
Key blockers
Client decisions needed
Next period lookahead
Auto summary snippets
Progress position
Cost position
Forecast position
Evidence / photos / records to attach
| Ref | Date | Type | Description | Location / area | Linked diary / allocation ref | Owner | Status
Note on C7: Contract value / Budget at Completion (BAC). Update this to match the project.
Note on C8: Choose the reporting week to pull through from Weekly Data.

## Weekly Data
Weekly Data
Enter one row per reporting week. Dashboard and charts update from this table.
| Contract value / BAC |  |  | 2400000
| Tip | Only update yellow cells. Formula columns calculate value, variances, CPI and SPI.
Week # | Week start | Week end | Planned % complete | Actual % complete | Planned Value (PV £) | Earned Value (EV £) | Actual Cost (AC £) | Progress variance | Cost variance (CV £) | CPI | SPI | Labour hours | Plant hours | Safety incidents | Weather lost hrs | Milestones / completed work | Notes / blockers
1 | [10 empty] | #VALUE!
2 | [10 empty] | #VALUE!
3 | [10 empty] | #VALUE!
4 | [10 empty] | #VALUE!
5 | [10 empty] | #VALUE!
6 | [10 empty] | #VALUE!
7 | [10 empty] | #VALUE!
8 | [10 empty] | #VALUE!
9 | [10 empty] | #VALUE!
10 | [10 empty] | #VALUE!
11 | [10 empty] | #VALUE!
12 | [10 empty] | #VALUE!
13 | [10 empty] | #VALUE!
14 | [10 empty] | #VALUE!
15 | [10 empty] | #VALUE!
16 | [10 empty] | #VALUE!
17 | [10 empty] | #VALUE!
18 | [10 empty] | #VALUE!
19 | [10 empty] | #VALUE!
20 | [10 empty] | #VALUE!
21 | [10 empty] | #VALUE!
22 | [10 empty] | #VALUE!
23 | [10 empty] | #VALUE!
24 | [10 empty] | #VALUE!
25 | [10 empty] | #VALUE!
26 | [10 empty] | #VALUE!
27 | [10 empty] | #VALUE!
28 | [10 empty] | #VALUE!
29 | [10 empty] | #VALUE!
30 | [10 empty] | #VALUE!
31 | [10 empty] | #VALUE!
32 | [10 empty] | #VALUE!
33 | [10 empty] | #VALUE!
34 | [10 empty] | #VALUE!
35 | [10 empty] | #VALUE!
36 | [10 empty] | #VALUE!
37 | [10 empty] | #VALUE!
38 | [10 empty] | #VALUE!
39 | [10 empty] | #VALUE!
40 | [10 empty] | #VALUE!
41 | [10 empty] | #VALUE!
42 | [10 empty] | #VALUE!
43 | [10 empty] | #VALUE!
44 | [10 empty] | #VALUE!
45 | [10 empty] | #VALUE!
46 | [10 empty] | #VALUE!
47 | [10 empty] | #VALUE!
48 | [10 empty] | #VALUE!
49 | [10 empty] | #VALUE!
50 | [10 empty] | #VALUE!
51 | [10 empty] | #VALUE!
52 | [10 empty] | #VALUE!

## Issue & Risk Log
Issue & Risk Log
Track blockers, commercial issues, RFIs, delays and actions that affect progress.
Opened | Category | Impact area | Issue / risk description | Owner | Due date | Status | Impact severity | Cost / time impact | Action required | Linked evidence ref | Closed date | Age / overdue flag
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
No due date
Formulas:
Age / overdue flag = IF([Status]="Closed","Closed",IF([Due date]="","No due date",IF([Due date]<TODAY(),"Overdue","Open")))

## Worked Example
Worked Example — 12 Week Construction Progress Report
A deliberately imperfect job: behind programme, cost pressure, visible warnings.
| Contract value / BAC |  |  | 2400000
Week # | Week start | Week end | Planned % complete | Actual % complete | Planned Value (PV £) | Earned Value (EV £) | Actual Cost (AC £) | Progress variance | Cost variance (CV £) | CPI | SPI | Labour hours | Plant hours | Safety incidents | Weather lost hrs | Milestones / completed work | Notes / blockers
1 | 2026-04-06 | 2026-04-12 | 2% | 1.8% | 48000 | 43200 | 52000 | -0.2% | -8800 | 0.83077 | 0.9 | 180 | 45 | 0 | 3 | Mobilisation, welfare setup | Slow start due to access permit
2 | 2026-04-13 | 2026-04-19 | 6% | 5.5% | 144000 | 132000 | 150000 | -0.5% | -18000 | 0.88 | 0.91667 | 430 | 90 | 0 | 5 | Site clearance complete | Minor plant downtime
3 | 2026-04-20 | 2026-04-26 | 13% | 12.5% | 312000 | 300000 | 330000 | -0.5% | -30000 | 0.90909 | 0.96154 | 760 | 160 | 0 | 8 | Groundworks underway | Wet weather slowed excavation
4 | 2026-04-27 | 2026-05-03 | 24% | 23% | 576000 | 552000 | 600000 | -1% | -48000 | 0.92 | 0.95833 | 1040 | 250 | 0 | 0 | Substructure progress | Concrete pour completed
5 | 2026-05-04 | 2026-05-10 | 38% | 36.5% | 912000 | 876000 | 948000 | -1.5% | -72000 | 0.92405 | 0.96053 | 1320 | 340 | 1 | 0 | Peak labour begins | One minor safety observation
6 | 2026-05-11 | 2026-05-17 | 54% | 51.5% | 1296000 | 1236000 | 1340000 | -2.5% | -104000 | 0.92239 | 0.9537 | 1530 | 390 | 0 | 6 | Frame installation | Late steel delivery
7 | 2026-05-18 | 2026-05-24 | 68% | 65% | 1632000 | 1560000 | 1690000 | -3% | -130000 | 0.92308 | 0.95588 | 1600 | 420 | 0 | 0 | Peak works | Additional crew mobilised
8 | 2026-05-25 | 2026-05-31 | 80% | 76.5% | 1920000 | 1836000 | 1985000 | -3.5% | -149000 | 0.92494 | 0.95625 | 1480 | 370 | 0 | 4 | Envelope works | Design query affecting zone B
9 | 2026-06-01 | 2026-06-07 | 89% | 85.5% | 2136000 | 2052000 | 2200000 | -3.5% | -148000 | 0.93273 | 0.96067 | 1270 | 310 | 0 | 0 | Fit-out starts | MEP coordination ongoing
10 | 2026-06-08 | 2026-06-14 | 95% | 92.5% | 2280000 | 2220000 | 2350000 | -2.5% | -130000 | 0.94468 | 0.97368 | 980 | 260 | 0 | 0 | Fit-out progress | Snagging list opened
11 | 2026-06-15 | 2026-06-21 | 98% | 96% | 2352000 | 2304000 | 2420000 | -2% | -116000 | 0.95207 | 0.97959 | 720 | 180 | 0 | 0 | Commissioning | Testing paperwork awaited
12 | 2026-06-22 | 2026-06-28 | 100% | 98.5% | 2400000 | 2364000 | 2470000 | -1.5% | -106000 | 0.95709 | 0.985 | 460 | 120 | 0 | 0 | Practical completion target | Final defects remain
Example dashboard
| Planned complete |  |  | Actual complete |  |  | Progress variance |  |  | Actual cost
| 100% |  |  | 98.5% |  |  | -1.5% |  |  | 2470000
| CPI |  |  | SPI |  |  | EAC |  |  | ETC
| 0.95709 |  |  | 0.985 |  |  | 2507614.2132 |  |  | 37614.2132