## How to use
Gather ¦ Construction Cost-to-Complete Forecast Template
A practical package-level forecast workbook for QS and commercial teams
What this template does
Use this workbook to forecast final cost by package, compare forecast against budget, track risk allowance, and highlight packages that need commercial attention. It is designed for construction projects where package-level visibility matters more than a pretty dashboard with no teeth.
How to use
| 1 | Enter project details | Use the yellow cells on the Cost Forecast tab for project, data date, contract value, contingency and reporting period.
| 2 | Fill each package row | Enter original budget, approved changes, committed cost, actual cost to date, accruals, cost to complete and risk/opportunity allowance.
| 3 | Review the dashboard | The dashboard calculates final forecast, variance, risk status, top overruns, committed exposure and cost-to-complete totals.
| 4 | Use the risk log | Capture risks and opportunities that explain the forecast movement. Link them back to the package row where possible.
| 5 | Export for reporting | Use the dashboard as the management-report view, then archive each monthly version for audit trail and trend analysis.
Gather CTA
Free template by Gather — gatherinsights.com
Want this forecast built from real site diaries, allocation records and cost data? → Book a demo

## Forecast Dashboard
Forecast Dashboard
Linked summary from Cost Forecast. Use for monthly reporting and management review.
Project summary
Project |  |  | Report period |  |  | Data date |  | Contract value
Revised budget |  |  | Final forecast cost |  |  | Forecast variance |  | Forecast margin
Forecast breakdown | [6 empty] | Risk status count
Actual cost to date | [6 empty] | Green
Remaining forecast | [6 empty] | Amber
Risk / opp allowance | [6 empty] | Red
Forecast variance
Top overrun watchlist
Package ref | Package / trade | Owner | Final forecast cost (£) | Variance (£) | Risk status | Action required
Free template by Gather — gatherinsights.com
Want this forecast built from real site diaries, allocation records and cost data? → Book a demo

## Cost Forecast
Cost Forecast
Yellow cells are inputs. Formula cells are protected. No macros.
Project controls | [6 empty] | Forecast summary
Project name | Example Project / Replace me | [5 empty] | Original budget
Client | Client name | [5 empty] | Approved changes
Report period ending | 2026-07-31 | [5 empty] | Revised budget
Data date | 2026-07-31 | [5 empty] | Actual + accruals
Contract value (£) | 2400000 | [5 empty] | Remaining forecast
Target margin % | 8% | [5 empty] | Risk / opp allowance
Final forecast cost
Forecast variance
Forecast margin
Package ref | Package / trade | Owner | Status | Original budget (£) | Approved changes (£) | Revised budget (£) | Committed cost (£) | Actual cost to date (£) | Accruals (£) | Cost to complete (£) | Risk / opp allowance (£) | Final forecast cost (£) | Variance to revised budget (£) | Variance % | Forecast margin % | Committed % of final | CTC % of final | Risk status | Action required | Notes / evidence link | Package | Revised budget | Final forecast
P01 | Preliminaries |  | Not started
P02 | Groundworks |  | Not started
P03 | Frame |  | Not started
P04 | Envelope |  | Not started
P05 | MEP |  | Not started
P06 | Internal finishes |  | Not started
P07 | External works |  | Not started
P08 | Testing & commissioning |  | Not started
Chart updates from the first 10 package rows. Add or replace package rows above as needed.

## Risk & Opportunities
Risk & Opportunities
Track the risks and opportunities that explain movement in cost-to-complete forecasts.
Risk / opp ref | Package ref | Type | Description | Probability | Impact (£) | Expected value (£) | Owner | Mitigation / action | Due date | Status | Linked evidence | Notes | Closed date

## Worked Example
Worked Example
Pre-filled example showing a forecast that is under pressure but still recoverable.
Project controls | [6 empty] | Forecast summary
Project name | Riverside Mixed-use Block | [5 empty] | Original budget
Client | Example Client Ltd | [5 empty] | Approved changes
Report period ending | 2026-07-31 | [5 empty] | Revised budget
Data date | 2026-07-31 | [5 empty] | Actual + accruals
Contract value (£) | 2400000 | [5 empty] | Remaining forecast
Target margin % | 8% | [5 empty] | Risk / opp allowance
Final forecast cost
Forecast variance
Forecast margin
Package ref | Package / trade | Owner | Status | Original budget (£) | Approved changes (£) | Revised budget (£) | Committed cost (£) | Actual cost to date (£) | Accruals (£) | Cost to complete (£) | Risk / opp allowance (£) | Final forecast cost (£) | Variance to revised budget (£) | Variance % | Forecast margin % | Committed % of final | CTC % of final | Risk status | Action required | Notes / evidence link | Package | Revised budget | Final forecast
P01 | Preliminaries | Commercial Manager | Watch | 220000 | 15000 |  | 180000 | 92000 | 18000 | 55000 | 12000 | [7 empty] | Agree reduced prelim extension
P02 | Groundworks | QS | Complete | 310000 | 28000 |  | 300000 | 296000 | 4000 | 6000 | 0 | [7 empty] | Close final account | Instruction 014, diary refs W02-W08
P03 | Frame | Project QS | Complete | 420000 | 0 |  | 418000 | 410000 | 5000 | 3000 | 0 | [7 empty] | Close remaining defects cost
P04 | Envelope | Package QS | At risk | 360000 | 45000 |  | 310000 | 295000 | 18000 | 80000 | 35000 | [7 empty] | Resolve design change valuation | CE-017, photos, subcontractor notice
P05 | MEP | MEP QS | At risk | 520000 | 60000 |  | 490000 | 420000 | 35000 | 145000 | 50000 | [7 empty] | Reforecast labour productivity | TQ log, revised programme
P06 | Internal finishes | QS | Watch | 280000 | 20000 |  | 210000 | 165000 | 12000 | 105000 | 15000 | [7 empty] | Confirm acceleration cost exposure
P07 | External works | QS | On track | 190000 | 5000 |  | 98000 | 82000 | 6000 | 86000 | 5000 | [7 empty] | Monitor weather allowance
P08 | Testing & commissioning | PM | Not started | 100000 | 0 |  | 30000 | 15000 | 0 | 65000 | 8000 | [7 empty] | Update commissioning plan
P09 | Design / consultants | Commercial Manager | Watch | 85000 | 12000 |  | 70000 | 58000 | 9000 | 26000 | 5000 | [7 empty] | Confirm remaining design support
P10 | Contingency / client risk | Project Director | On track | 115000 | 0 |  | 0 | 0 | 0 | 65000 | -20000 | [7 empty] | Hold pending CE outcomes

## Definitions
Definitions
Plain-English guide for the forecast fields and dashboard metrics.
Term | Formula / source | Plain-English meaning | Why it matters
Original budget | Input | The original allowance for the package before approved changes. | Shows whether pressure comes from bad budget, change, or delivery.
Approved changes | Input | Approved additions or omissions to the package budget. | Keeps forecast variance measured against the latest agreed position.
Revised budget | Original budget + approved changes | The current budget baseline. | This is the number final forecast is measured against.
Committed cost | Input | Value already committed through orders, subcontracts or POs. | Shows how much of the final cost is already locked in.
Actual cost to date | Input | Costs posted to date from cost records. | Grounds the forecast in what has actually hit the job.
Accruals | Input | Known cost incurred but not yet posted. | Stops the forecast looking artificially healthy before invoices arrive.
Cost to complete | Input | Expected remaining cost to finish the package. | The core forecast judgement.
Risk / opportunity allowance | Input | Positive for risk cost, negative for opportunities/savings. | Makes risk explicit instead of hiding it in the remaining forecast.
Final forecast cost | Actual + accruals + CTC + risk/opportunity | Expected final cost for the package. | The main commercial control number.
Variance to revised budget | Revised budget - final forecast cost | Positive is forecast saving; negative is overrun. | Quickly flags the packages hurting margin.
Forecast margin % | Variance / revised budget | Expected margin against current budget. | Useful for spotting packages below target margin.
Committed % of final | Committed cost / final forecast cost | How much of the forecast is already committed. | Low committed percentage with high CTC means more uncertainty.
CTC % of final | Cost to complete / final forecast cost | How much of the forecast is still to be spent. | Large remaining percentage means the forecast can still move materially.
Risk status | Red / Amber / Green formula | Red if overrun; Amber if low margin; Green otherwise. | Helps management focus on the right packages first.
CTA | Want this forecast built from real site diaries, allocation records and cost data? → Book a demo