## How to use
Daily Diary to Weekly Report Template
Gather construction template - practical spreadsheet for live project controls
What this template does
Turns daily site diary records into a weekly construction progress report: labour, plant, activities, delays, safety, quality, weather, key issues and client-ready summary metrics.
How to use it
| 1 | Fill the yellow input cells only. Formula cells are protected so the workbook is harder to break.
| 2 | Use the worked example first to see the intended level of detail.
| 3 | Update the log weekly or daily, then review the dashboard and red/amber flags.
| 4 | Use links/references back to site diary entries, photos, drawings, instructions, emails and cost records.
| 5 | Export or copy the report/dashboard into your client or internal progress pack.
Workbook tabs
| Weekly Dashboard | Auto-summary for a selected week.
| Daily Diary | Daily site record inputs.
| Weekly Report | Client/internal report layout generated from the diary data.
| Worked Example | Pre-filled example showing realistic site records.
Gather note
Use the spreadsheet if you are doing this manually. Use Gather when you are ready to stop copying records between diaries, trackers, reports and forecasts.
Free template by Gather - gatherinsights.com ¦ Want this built automatically from site records? Book a demo: https://www.gatherinsights.com/en/book-a-demo

## Weekly Dashboard
Weekly Dashboard
Select a week and review diary-driven progress indicators
| Inputs |  | Weekly KPIs
| Week commencing | 2026-07-06 | Diary days recorded
| Project | Example Project | Total labour hours
| Reporting period | Week 28 | Total plant hours
| Prepared by | Site Team | Delay hours
Open actions
Safety incidents
Weekly narrative
Progress achieved
Key blockers / delays
Safety / quality notes
Next week focus

## Daily Diary
Daily Diary
Input one row per day, location or key activity. Yellow cells are inputs; grey cells calculate.
Entry ID | Week commencing | Date | Day | Weather | Location / area | Activity completed | Trade | Labour headcount | Labour hours | Plant used | Plant count | Plant hours | Materials delivered | Progress evidence / photo ref | Delay hours | Safety incident? | Issue / risk / blocker | Action status | Notes

## Weekly Report
Weekly Progress Report
Client-ready weekly report structure linked to the Weekly Dashboard inputs
Report header
Project
Week commencing
Prepared by
Executive summary
Progress achieved
Key blockers / delays
Safety / quality notes
Next week focus
Weekly metrics
Diary days recorded
Total labour hours
Total plant hours
Delay hours
Open actions
Safety incidents
Free template by Gather - gatherinsights.com ¦ Want this built automatically from site records? Book a demo: https://www.gatherinsights.com/en/book-a-demo

## Worked Example
Worked Example
Example daily diary entries and weekly output for a live project
Entry ID | Week commencing | Date | Day | Weather | Location / area | Activity completed | Trade | Labour headcount | Labour hours | Plant used | Plant count | Plant hours | Materials delivered | Progress evidence / photo ref | Delay hours | Safety incident? | Issue / risk / blocker | Action status | Notes
D-001 | 2026-07-06 | 2026-07-06 |  | Dry | Block A | Poured ground floor slab | Concrete | 12 |  | Concrete pump | 1 |  | Rebar, C35 concrete | PH-001 | 0 | No | Awaiting revised drainage drawing | Open | Good pour, minor access congestion
D-002 | 2026-07-06 | 2026-07-07 |  | Rain | Block B | Drainage trenching and inspection chambers | Groundworks | 8 |  | Excavator | 1 |  | Drainage pipes | PH-002 | 2 | No | Rain slowed trench works | In progress | Pump used to manage standing water
D-003 | 2026-07-06 | 2026-07-08 |  | Mixed | Block A | Steel frame delivery and setting out | Steel | 10 |  | Telehandler | 2 |  | Steel sections | PH-003 | 0 | No | Missing bolts for bay A3 | Open | Supplier contacted
D-004 | 2026-07-06 | 2026-07-09 |  | Dry | Block C | M&E first fix containment | M&E | 9 |  | MEWP | 1 |  | Cable tray | PH-004 | 0 | No | Access clash with drylining | In progress | Coordination meeting arranged
D-005 | 2026-07-06 | 2026-07-10 |  | Wind | Block A | Steel frame erection paused for high winds | Steel | 6 |  | Crane | 1 |  | N/A | PH-005 | 5 | No | Crane wind limit exceeded | Closed | Rescheduled to Monday
Free template by Gather - gatherinsights.com ¦ Want this built automatically from site records? Book a demo: https://www.gatherinsights.com/en/book-a-demo