## How to use
Earned Value Management Calculator for Construction
Free template by Gather — gatherinsights.com
What this is | A formula-only EVM workbook for tracking planned value, earned value, actual cost, cost variance, schedule variance and forecast-at-completion.
Who it is for | QS, commercial, project controls and site teams who need a practical construction EVM calculator rather than a generic textbook sheet.
How to use it | Fill the yellow cells on the EVM Calculator tab: BAC, reporting period, planned percent complete, actual cost and actual percent complete. Blue cells calculate automatically.
Inputs | Yellow cells are editable. Formula cells are protected with no password so users can unprotect if they need to adapt the workbook.
Worked example | The example uses a 12-month, £2.4m project that is slightly over budget and behind programme so warnings, CPI/SPI and forecast outputs visibly respond.
No macros | The workbook uses formulas and native charts only, so it opens in Excel and Google Sheets.
CTA | Want EVM signals without manually rebuilding spreadsheets from site diaries, costs and progress updates? Book a demo. | Book a demo
Plain-English formulas
PV | Planned Value = BAC × planned % complete
EV | Earned Value = BAC × actual % complete
AC | Actual Cost = cumulative cost incurred to date
CV | Cost Variance = EV − AC. Negative means over budget.
SV | Schedule Variance = EV − PV. Negative means behind programme.
CPI | Cost Performance Index = EV ÷ AC. Below 1.00 means over budget.
SPI | Schedule Performance Index = EV ÷ PV. Below 1.00 means behind programme.
EAC | Estimate at Completion = BAC ÷ CPI. What the job will cost if current cost efficiency holds.
ETC | Estimate to Complete = EAC − AC.
VAC | Variance at Completion = BAC − EAC.
TCPI | To-Complete Performance Index = (BAC − EV) ÷ (BAC − AC).

## EVM Calculator
Earned Value Management Calculator
Construction EVM calculator by Gather — planned value, earned value, actual cost and forecast-at-completion.
Project inputs |  |  | Current period summary | [6 empty] | Forecast checks
Project name |  |  | Current PV (£) |  |  | PV = planned value to data date |  |  |  | ETC (£) |  |  | Estimate to complete = remaining forecast cost.
Budget at Completion (BAC) | 0 |  | Current AC (£) |  |  | AC = cumulative actual cost |  |  |  | VAC (£) |  |  | Variance at completion. Negative means forecast overrun.
Number of periods | 12 |  | Current EV (£) |  |  | EV = value of completed work |  |  |  | TCPI |  |  | Efficiency needed from now to hit BAC.
Period type | Month |  | Current CPI |  |  | CPI < 1 means over budget |  |  |  | Headline |  |  | Simple red/green read on cost and schedule.
Data date period # | 1 |  | Current SPI |  |  | SPI < 1 means behind plan |  |  |  | Commercial note | Use EAC as an early warning, not a substitute for package-level forecasting. |  | Reconcile with procurement, variations and risk.
Reporting date |  |  | Forecast EAC (£) |  |  | EAC = likely final cost |  |  |  | CTA | Book a demo: gatherinsights.com/en/book-a-demo |  | Gather automates these signals from site data and costs.
Period # | Period label / date | Planned % complete | Planned Value - PV (£) | Actual Cost - AC (£) | Actual % complete | Earned Value - EV (£) | Cost Variance - CV (£) | Schedule Variance - SV (£) | CPI | SPI | EAC (£) | ETC (£) | VAC (£) | TCPI | Status / interpretation | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
Free template by Gather — gatherinsights.com |  |  |  | Want these EVM signals automatically from site diaries, costs and progress data? Book a demo
Note on D12: PV = BAC x planned % complete
Note on G12: EV = BAC x actual % complete
Note on H12: CV = EV - AC. Negative = over budget.
Note on I12: SV = EV - PV. Negative = behind programme.
Note on L12: EAC = BAC / CPI. Forecast final cost if current efficiency holds.

## Worked Example
Worked Example — Earned Value Management Calculator
Construction EVM calculator by Gather — planned value, earned value, actual cost and forecast-at-completion.
Project inputs |  |  | Current period summary | [6 empty] | Forecast checks
Project name | Riverside Residential Phase 2 |  | Current PV (£) |  |  | PV = planned value to data date |  |  |  | ETC (£) |  |  | Estimate to complete = remaining forecast cost.
Budget at Completion (BAC) | 2400000 |  | Current AC (£) |  |  | AC = cumulative actual cost |  |  |  | VAC (£) |  |  | Variance at completion. Negative means forecast overrun.
Number of periods | 12 |  | Current EV (£) |  |  | EV = value of completed work |  |  |  | TCPI |  |  | Efficiency needed from now to hit BAC.
Period type | Month |  | Current CPI |  |  | CPI < 1 means over budget |  |  |  | Headline |  |  | Simple red/green read on cost and schedule.
Data date period # | 9 |  | Current SPI |  |  | SPI < 1 means behind plan |  |  |  | Commercial note | Use EAC as an early warning, not a substitute for package-level forecasting. |  | Reconcile with procurement, variations and risk.
Reporting date | 2026-06-30 |  | Forecast EAC (£) |  |  | EAC = likely final cost |  |  |  | CTA | Book a demo: gatherinsights.com/en/book-a-demo |  | Gather automates these signals from site data and costs.
Period # | Period label / date | Planned % complete | Planned Value - PV (£) | Actual Cost - AC (£) | Actual % complete | Earned Value - EV (£) | Cost Variance - CV (£) | Schedule Variance - SV (£) | CPI | SPI | EAC (£) | ETC (£) | VAC (£) | TCPI | Status / interpretation | Notes
1 | Month 1 | 2% |  | 52000 | 1.7% | [10 empty] | Mobilisation
2 | Month 2 | 6% |  | 150000 | 5.4%
3 | Month 3 | 13% |  | 330000 | 12.5% | [10 empty] | Groundworks
4 | Month 4 | 24% |  | 600000 | 23.3%
5 | Month 5 | 38% |  | 948000 | 37.1% | [10 empty] | Peak begins
6 | Month 6 | 54% |  | 1340000 | 52.9%
7 | Month 7 | 68% |  | 1690000 | 66.7% | [10 empty] | Peak
8 | Month 8 | 80% |  | 1985000 | 78.8%
9 | Month 9 | 89% |  | 2200000 | 87.9% | [10 empty] | Fit-out
10 | Month 10 | 95% |  | 2350000 | 94.2%
11 | Month 11 | 98% |  | 2420000 | 97.3%
12 | Month 12 | 100% |  | 2470000 | 99.6% | [10 empty] | Practical completion
13
14
15
16
17
18
19
20
21
22
23
24
Free template by Gather — gatherinsights.com |  |  |  | Want these EVM signals automatically from site diaries, costs and progress data? Book a demo
Note on D12: PV = BAC x planned % complete
Note on G12: EV = BAC x actual % complete
Note on H12: CV = EV - AC. Negative = over budget.
Note on I12: SV = EV - PV. Negative = behind programme.
Note on L12: EAC = BAC / CPI. Forecast final cost if current efficiency holds.

## Definitions
Definitions & interpretation guide
Use this tab to explain the EVM metrics to non-specialists.
Metric | Formula | Plain-English interpretation | Watch-out
BAC | Project budget at completion | The total approved budget for the job. | Use the current agreed baseline.
PV | BAC × planned % | What the programme says you should have earned by now. | Only useful if the baseline is credible.
EV | BAC × actual % | The value of work actually completed. | Progress % must be assessed consistently.
AC | Actual cost to date | What has actually been spent. | Include committed/accrued cost where your reporting rules require it.
CV | EV − AC | Negative means the job has spent more than the value earned. | Cost issue.
SV | EV − PV | Negative means the job has earned less than planned by this point. | Schedule/progress issue.
CPI | EV ÷ AC | Cost efficiency. Below 1.00 means over budget. | Can be distorted early in the job.
SPI | EV ÷ PV | Schedule efficiency. Below 1.00 means behind plan. | Can trend back to 1.00 near completion.
EAC | BAC ÷ CPI | Forecast final cost if current efficiency continues. | Use judgement, not blind automation.
ETC | EAC − AC | Forecast remaining cost to finish. | Should be reconciled to package forecasts.
VAC | BAC − EAC | Forecast final under/overrun. Negative means overrun. | Often the board-level number.
TCPI | (BAC − EV) ÷ (BAC − AC) | Efficiency needed on remaining work to hit BAC. | Above 1.00 means recovery is needed.