## How to use
Labour & Plant Allocation Tracker |  | Free template by Gather
Track where labour and plant time went, calculate cost by work package, and spot unallocated records before they turn into commercial fog. |  | Book a demo
1. Set up rate cards | Enter labour and plant rates in the Rate Card tab.
2. Fill the Allocation Tracker | Record date, package, activity, hours, rates, quantities, diary reference and status.
3. Review the dashboard | Use the dashboard to see total labour cost, plant cost, unallocated time, and high-cost packages.
4. Use with site diaries | Link each allocation line back to a diary reference, instruction, drawing, or photo pack.
5. Gather CTA | If the manual tracking hurts, Gather links diaries, allocation and cost data automatically. Spreadsheet painkiller not included.
Free template by Gather — gatherinsights.com ¦ Want this filled automatically from site diaries, allocation sheets and cost data? Book a demo.

## Dashboard
Allocation Dashboard | [5 empty] | Free template by Gather
Summary of labour, plant and total allocation cost. | [5 empty] | Book a demo
Key metrics
Total labour cost
Total plant cost
Total allocation cost
Unallocated / to review lines
Blocked allocation lines
Total labour hours
Total plant hours/days
Cost by type
Type | Cost
Labour
Plant
Materials / other
Cost by work package
Package | Labour cost | Plant cost | Other cost | Total cost | Cost %
Groundworks
Frame
Envelope
MEP
Fit-out
External works
Prelims
Other
Free template by Gather — gatherinsights.com ¦ Want this filled automatically from site diaries, allocation sheets and cost data? Book a demo.

## Allocation Tracker
Allocation Tracker | [8 empty] | Free template by Gather
Use one row per labour/plant/material allocation. Yellow cells are inputs; formula cells are protected. | [8 empty] | Book a demo
Daily labour, plant and material allocations
Date | Week ending | Area / location | Work package | Activity | Supervisor | Labour role | Gang / worker | Labour hours | Labour rate £/hr | Labour cost £ | Plant item | Plant hours / days | Plant rate £ | Plant cost £ | Materials / consumables £ | Other cost £ | Total cost £ | Planned qty | Actual qty | Unit | Productivity | Status | Diary / evidence ref

## Rate Card
Rate Card | [7 empty] | Free template by Gather
Optional lookup/reference sheet for labour and plant rates. Copy rates into the tracker; formulas stay simple and portable. | [7 empty] | Book a demo
Labour rates |  |  |  | Plant rates
Role | Typical rate £/hr | Notes | Source / owner | Plant item | Typical rate £/day or hr | Unit | Notes
Site manager | 65 | Example only | User input | Excavator 13t | 650 | day | Example only
Engineer | 55 | Example only | User input | Telehandler | 420 | day | Example only
Supervisor | 48 | Example only | User input | Dumper | 280 | day | Example only
Skilled operative | 32 | Example only | User input | Scissor lift | 95 | day | Example only
General operative | 24 | Example only | User input | Generator | 45 | day | Example only

## Worked Example
Worked Example | [8 empty] | Free template by Gather
Example allocations for a live construction project. | [8 empty] | Book a demo
Example allocation records
Date | Week ending | Area / location | Work package | Activity | Supervisor | Labour role | Gang / worker | Labour hours | Labour rate £/hr | Labour cost £ | Plant item | Plant hours / days | Plant rate £ | Plant cost £ | Materials / consumables £ | Other cost £ | Total cost £ | Planned qty | Actual qty | Unit | Productivity | Status | Diary / evidence ref
2026-07-06 | 2026-07-10 | Zone A | Groundworks | Drainage run excavation | A. Brown | Skilled operative | GW gang 1 | 64 | 32 |  | Excavator 13t | 5 | 650 |  | 850 | 0 |  | 80 | 72 | m |  | In progress | Diary-001 / photos
2026-07-07 | 2026-07-10 | Zone A | Groundworks | Cart away spoil | A. Brown | General operative | GW gang 1 | 40 | 24 |  | Dumper | 5 | 280 |  | 0 | 300 |  | 120 | 110 | m3 |  | Complete | Diary-002
2026-07-08 | 2026-07-10 | Core | Frame | Concrete pour prep | S. Khan | Skilled operative | Frame gang | 48 | 32 |  | Telehandler | 2 | 420 |  | 1200 | 0 |  | 450 | 420 | m2 |  | Complete | Diary-003
2026-07-09 | 2026-07-10 | Level 2 | MEP | First fix containment | L. Patel | Engineer | MEP team | 36 | 55 |  | Scissor lift | 3 | 95 |  | 2200 | 0 |  | 100 | 82 | m |  | Blocked | RFI-014
2026-07-10 | 2026-07-10 | Level 1 | Fit-out | Partition install | M. Jones | Skilled operative | Fit-out gang | 72 | 32 |  |  | 0 | 0 |  | 1800 | 150 |  | 220 | 200 | lm |  | In progress | Diary-005
2026-07-13 | 2026-07-17 | External | External works | Kerb installation | A. Brown | General operative | Civils gang | 56 | 24 |  | Dumper | 4 | 280 |  | 600 | 0 |  | 140 | 130 | m |  | Planned | Programme W29
Free template by Gather — gatherinsights.com ¦ Want this filled automatically from site diaries, allocation sheets and cost data? Book a demo.