## How to use
RFI / Technical Query Register Template
Gather construction template - practical spreadsheet for live project controls
What this template does
Tracks RFIs and technical queries from issue through response, with discipline, package, due-date, ageing and delay-risk flags.
How to use it
| 1 | Fill the yellow input cells only. Formula cells are protected so the workbook is harder to break.
| 2 | Use the worked example first to see the intended level of detail.
| 3 | Update the log weekly or daily, then review the dashboard and red/amber flags.
| 4 | Use links/references back to site diary entries, photos, drawings, instructions, emails and cost records.
| 5 | Export or copy the report/dashboard into your client or internal progress pack.
Workbook tabs
| Dashboard | RFI volume, overdue and response performance.
| RFI Register | Main technical query log.
| Worked Example | Pre-filled example.
| Guidance | Practical guidance for cleaner query records.
Gather note
Use the spreadsheet if you are doing this manually. Use Gather when you are ready to stop copying records between diaries, trackers, reports and forecasts.
Free template by Gather - gatherinsights.com ¦ Want this built automatically from site records? Book a demo: https://www.gatherinsights.com/en/book-a-demo

## Dashboard
RFI / TQ Dashboard
Track open technical queries, overdue responses and delay risk
Summary
Total RFIs
Open RFIs
Overdue
High delay risk
Average response days
Status counts
Draft
Open
Answered - review
Closed
Rejected / duplicate
Discipline counts
Architectural
Structural
M&E
Civil
Commercial
Other

## RFI Register
RFI / Technical Query Register
Track questions, responses, overdue items and delay risk. Yellow cells are inputs; grey cells calculate.
RFI / TQ ref | Date raised | Raised by | Package / area | Discipline | Question / query | Required answer date | Response date | Responder | Response summary | Days open | Response days | Status | Blocks work? | Delay risk | Action flag | Drawing / evidence ref | Notes
Formulas:
Days open = IF([Date raised]="","",IF([Response date]="",TODAY()-[Date raised],[Response date]-[Date raised]))
Action flag = IF([Status]="Closed","Closed",IF(AND([Required answer date]<>"",TODAY()>[Required answer date]),"Overdue",IF([Delay risk]="High","High risk","Open")))

## Worked Example
Worked Example
Example RFI / TQ register for a construction project
RFI / TQ ref | Date raised | Raised by | Package / area | Discipline | Question / query | Required answer date | Response date | Responder | Response summary | Days open | Response days | Status | Blocks work? | Delay risk | Action flag | Drawing / evidence ref | Notes
RFI-001 | 2026-06-02 | Site Manager | Block A | Structural | Confirm reinforcement lap detail at gridline A/3. | 2026-06-09 | 2026-06-07 | Engineer | Use detail S-214 rev C. |  |  | Closed | No | Low |  | S-214 rev C | Closed before pour
RFI-002 | 2026-06-10 | M&E Lead | Plant room | M&E | Clash between containment route and sprinkler main. Confirm preferred route. | 2026-06-17 |  | Design Manager |  |  |  | Open | Yes | High |  | Coordination model | Blocks first fix
RFI-003 | 2026-06-15 | QS | External works | Civil | Confirm kerb type to east access road. | 2026-06-22 | 2026-06-24 | Architect | Use conservation kerb type K2. |  |  | Answered - review | No | Medium |  | A-506 | Late answer created resequencing
RFI-004 | 2026-06-21 | Subcontractor | Reception | Architectural | Confirm reception wall finish behind desk. | 2026-06-28 |  | Architect |  |  |  | Open | Yes | Medium |  | A-310 | Needed before procurement
Free template by Gather - gatherinsights.com ¦ Want this built automatically from site records? Book a demo: https://www.gatherinsights.com/en/book-a-demo
Formulas:
Days open = IF([Date raised]="","",IF([Response date]="",TODAY()-[Date raised],[Response date]-[Date raised]))
Action flag = IF([Status]="Closed","Closed",IF(AND([Required answer date]<>"",TODAY()>[Required answer date]),"Overdue",IF([Delay risk]="High","High risk","Open")))

## Guidance
Guidance
How to make RFIs useful instead of inbox archaeology
Good RFI discipline
| Ask one clear question | Avoid bundling five issues into one RFI. It makes ownership and closure messy.
| Add the constraint | Record whether the query blocks work, procurement, inspection, design release or commercial agreement.
| Use due dates | A due date turns the register into a management tool rather than a list of grumbles.
| Link evidence | Reference drawings, model snapshots, diary entries, photos or meeting minutes.
| Close deliberately | Do not mark closed until the answer has been reviewed and the site team knows what to build.
Free template by Gather - gatherinsights.com ¦ Want this built automatically from site records? Book a demo: https://www.gatherinsights.com/en/book-a-demo