## How to use
2/4/6 Week Lookahead Planner Template
Free template by Gather — gatherinsights.com
What this workbook does
Use this template to turn the next six weeks of site activity into a live planning board.
Track activities, trades, locations, labour, plant, materials, constraints and owners in one place.
The dashboard highlights blocked work, overdue constraints, next-two-week activity and completion risk.
Yellow cells are inputs. Grey/white cells are formulas or guidance. No macros are used.
Recommended workflow
| 1 | Set project details and the report week start date on the Lookahead Dashboard.
| 2 | Enter activities in the Lookahead Planner tab. Use one row per activity or workface.
| 3 | Record constraints, owners and due dates. Anything overdue or unresolved will be flagged.
| 4 | Use the Resource Plan tab to summarise labour, plant and material needs by week.
| 5 | Review the dashboard before the coordination meeting and update status after the meeting.
Gather CTA
Want the lookahead built from real site diaries, allocations, photos and constraints instead of yet another Friday spreadsheet chase? Book a demo.

## Lists (hidden)
Lookup Lists
Free template by Gather — gatherinsights.com
Status | Priority | Risk | Constraint Type | Trade | Week Bucket
Not Started | High | Red | Design | Groundworks | Week 1-2
Ready | Medium | Amber | Material | Concrete | Week 3-4
In Progress | Low | Green | Labour | Steel | Week 5-6
Blocked |  |  | Plant | Envelope | Outside window
Complete |  |  | Access | MEP
Deferred |  |  | Permit | Drylining
|  |  | Client decision | Finishes
|  |  | Weather | Fit-out
|  |  | Safety | External works
|  |  | Other | General

## Lookahead Dashboard
Lookahead Dashboard
Free template by Gather — gatherinsights.com
Project controls
Project name | Example: Riverside Block A | Dashboard KPIs
Report week start | 2026-07-27 | Total activities | Next 2 weeks | Blocked activities |  | Overdue constraints | High priority open
Planning window weeks | 6
Prepared by | Site / planning team
Revision | Rev 01
Activity status summary |  |  |  | Work by lookahead window
Status | Count |  |  | Window | Activities
Not Started |  |  |  | Week 1-2
Ready |  |  |  | Week 3-4
In Progress |  |  |  | Week 5-6
Blocked |  |  |  | Outside window
Complete
Deferred
Free template by Gather — gatherinsights.com ¦ Want lookaheads built from live site diaries, allocations and constraints? Book a demo: https://www.gatherinsights.com/en/book-a-demo
Note on B6: Change this date each reporting week. All 2/4/6 week buckets and overdue flags are calculated against it.
Note on B7: Default is six weeks. The formulas classify work into Week 1-2, Week 3-4 and Week 5-6.

## Lookahead Planner
2/4/6 Week Lookahead Planner
Free template by Gather — gatherinsights.com
Instructions
Enter one activity per row. Yellow cells are inputs. The sheet calculates duration, week bucket, days to start and constraint flags automatically.
Inputs are yellow. Formula columns are protected.
Activity ID | WBS / Area | Activity | Location | Trade / Subcontractor | Planned Start | Planned Finish | Duration days | Labour needed | Plant needed | Materials needed | Constraint type | Constraint description | Constraint owner | Constraint due | Status | % Complete | Constraint flag | Priority | Week bucket | Notes

## Resource Plan
Resource Plan
Free template by Gather — gatherinsights.com
Weekly resource summary
Week bucket | Activities | Labour entries | Plant entries | Material entries | Blocked | High priority
Week 1-2
Week 3-4
Week 5-6
Coordination notes
Use this section for craneage clashes, labour pinch-points, permit requirements, long-lead materials or access risks.

## Constraints Log
Constraints Log
Free template by Gather — gatherinsights.com
Open constraints and actions
Constraint ID | Constraint / action | Type | Linked activity | Owner | Raised date | Due date | Status | Days overdue | Evidence / link | Notes

## Worked Example
Worked Example — Six Week Lookahead
Free template by Gather — gatherinsights.com
Example activities
Activity ID | WBS / Area | Activity | Location | Trade / Subcontractor | Planned Start | Planned Finish | Duration days | Labour needed | Plant needed | Materials needed | Constraint type | Constraint description | Constraint owner | Constraint due | Status | % Complete | Constraint flag | Priority | Week bucket | Notes
A-001 | Block A | Complete pile cap excavation | Grid A1-A4 | Groundworks | 2026-07-27 | 2026-07-29 |  | 6 operatives | 13t excavator | Rebar cages | Design | Latest rebar detail needed | Design mgr | 2026-07-26 | Blocked | 0% |  | High |  | Holding pour booking until detail confirmed
A-002 | Block A | Pour pile caps | Grid A1-A4 | Concrete | 2026-07-30 | 2026-07-31 |  | 8 operatives | Concrete pump | C40 concrete | Permit | Pour permit approval | Site mgr | 2026-07-28 | Ready | 0% |  | High |  | Book pump once permit issued
A-003 | Core | Erect core jumpform lift 3 | Core 1 | Concrete | 2026-08-03 | 2026-08-07 |  | 10 operatives | Tower crane | Formwork panels | Plant | Crane availability | Logistics | 2026-07-31 | In Progress | 25% |  | High |  | Crane shared with steel delivery
A-004 | Envelope | Install level 2 curtain wall brackets | North elevation | Envelope | 2026-08-06 | 2026-08-11 |  | 5 operatives | MEWP | Brackets fixings | Material | Bracket delivery confirmation | Package mgr | 2026-08-02 | Ready | 0% |  | Medium |  | Delivery due Tuesday
A-005 | MEP | First fix containment | Level 1 east | MEP | 2026-08-10 | 2026-08-16 |  | 7 operatives | Podium steps | Containment | Access | Area handover from drylining | Site mgr | 2026-08-08 | Not Started | 0% |  | Medium |  | Access depends on board completion
A-006 | Drylining | Board riser walls | Level 1 risers | Drylining | 2026-08-13 | 2026-08-18 |  | 6 operatives |  | Boards and fixings |  |  |  |  | Not Started | 0% |  | Low
A-007 | Finishes | Screed preparation | Level 1 apartments | Finishes | 2026-08-21 | 2026-08-25 |  | 4 operatives | Mixer | Primer | Client decision | Floor finish approval | Client PM | 2026-08-14 | Not Started | 0% |  | Medium |  | Approval needed before material order
A-008 | External works | Drainage connection | West boundary | External works | 2026-08-28 | 2026-09-01 |  | 5 operatives | Mini excavator | Pipe fittings | Permit | Road opening permit | Planner | 2026-08-19 | Not Started | 0% |  | High |  | Permit lead time risk
A-009 | Fit-out | Bathroom pod installation | Level 2 | Fit-out | 2026-09-02 | 2026-09-06 |  | 6 operatives | Telehandler | Bathroom pods | Material | Pod delivery slot | Package mgr | 2026-08-26 | Deferred | 0% |  | Medium |  | Supplier proposed later slot