## How to use
Subcontractor Performance Scorecard |  | Free template by Gather
Score subcontractors consistently across programme, quality, safety, commercial performance, collaboration and evidence quality. |  | Book a demo
1. Set weights | Use the Assessment Criteria tab to adjust weighting for each category.
2. Score each package | Enter 1-5 scores in the Scorecard tab. Weighted score and RAG status calculate automatically.
3. Capture evidence | Use diary refs, NCRs, snags, RFIs and commercial notes to make the assessment defensible.
4. Review dashboard | Identify best performers, red-risk subcontractors and repeat pain points.
5. Gather CTA | Gather helps connect real site records to performance reviews, instead of relying on memory and mildly haunted spreadsheets.
Free template by Gather — gatherinsights.com ¦ Want this filled automatically from site diaries, allocation sheets and cost data? Book a demo.

## Assessment Criteria
Assessment Criteria |  |  |  | Free template by Gather
Set scoring weights and keep the scoring definition consistent across teams. |  |  |  | Book a demo
Score weights
Category | Weight | What good looks like | Score 1 warning sign
Programme | 25% | Hits planned dates, recovers slippage early | Repeated slippage without recovery plan
Quality | 20% | Low defects, clean handover, fast close-out | Recurring NCRs, rework or unresolved snags
Safety | 20% | Strong RAMS compliance and no unsafe acts | Incidents, near misses or poor housekeeping
Commercial | 15% | Clear records, fair valuations, few disputes | Late notices, disputed accounts, poor records
Collaboration | 10% | Communicates early and works well with others | Late escalation, poor coordination, blame tennis
Evidence quality | 10% | Good diary, photo and document references | Weak or missing supporting evidence
Total weight

## Scorecard Dashboard
Scorecard Dashboard | [5 empty] | Free template by Gather
Portfolio view of subcontractor performance and risk. | [5 empty] | Book a demo
Key metrics
Average weighted score
Green subcontractors
Amber subcontractors
Red subcontractors
Total contract value
Open snags
Overdue RFIs/TQs
RAG status
Status | Count
Green
Amber
Red
Top packages by value
Package type | Contract value | Avg score | Red count | Amber count | Green count
Groundworks
Frame
Envelope
MEP
Fit-out
External works
Prelims
Other
Free template by Gather — gatherinsights.com ¦ Want this filled automatically from site diaries, allocation sheets and cost data? Book a demo.

## Subcontractor Scorecard
Subcontractor Scorecard | [8 empty] | Free template by Gather
Score each subcontractor/package. Formula cells are protected; yellow cells are inputs. | [8 empty] | Book a demo
Assessment register
Subcontractor | Package | Assessment period | Contract value £ | Actual progress % | Planned progress % | Programme score 1-5 | Quality score 1-5 | Safety score 1-5 | Commercial score 1-5 | Collaboration score 1-5 | Evidence score 1-5 | Progress variance % | Weighted score | RAG status | NCRs / incidents | Open snags | Overdue RFIs/TQs | Variations / CEs open | Payment dispute? | Recommendation | Evidence / notes

## Worked Example
Worked Example | [8 empty] | Free template by Gather
Example subcontractor scores showing green, amber and red outcomes. | [8 empty] | Book a demo
Example assessments
Subcontractor | Package | Assessment period | Contract value £ | Actual progress % | Planned progress % | Programme score 1-5 | Quality score 1-5 | Safety score 1-5 | Commercial score 1-5 | Collaboration score 1-5 | Evidence score 1-5 | Progress variance % | Weighted score | RAG status | NCRs / incidents | Open snags | Overdue RFIs/TQs | Variations / CEs open | Payment dispute? | Recommendation | Evidence / notes
Delta Groundworks | Groundworks | Jul 2026 | 420000 | 74% | 78% | 3 | 3 | 4 | 3 | 3 | 4 |  |  |  | 1 | 8 | 2 | 1 | Watch | Use with controls | Behind programme; evidence acceptable
Northline Frame | Frame | Jul 2026 | 680000 | 92% | 90% | 5 | 4 | 4 | 4 | 4 | 4 |  |  |  | 0 | 3 | 0 | 0 | No | Use again | Strong recovery and clean handover
Bright MEP | MEP | Jul 2026 | 510000 | 58% | 70% | 2 | 3 | 3 | 2 | 2 | 2 |  |  |  | 2 | 19 | 5 | 3 | Yes | Review required | Late responses and weak records
Oak Fit-out | Fit-out | Jul 2026 | 360000 | 42% | 45% | 3 | 4 | 5 | 4 | 4 | 3 |  |  |  | 0 | 6 | 1 | 1 | No | Use again | Good safety and collaboration
Shield Envelope | Envelope | Jul 2026 | 590000 | 63% | 62% | 4 | 3 | 3 | 3 | 3 | 3 |  |  |  | 1 | 12 | 2 | 2 | Watch | Use with controls | Quality close-out needs tighter control
Civic External Works | External works | Jul 2026 | 220000 | 18% | 25% | 2 | 3 | 4 | 3 | 3 | 2 |  |  |  | 0 | 4 | 1 | 0 | No | Use with controls | Early slippage; monitor resources
Free template by Gather — gatherinsights.com ¦ Want this filled automatically from site diaries, allocation sheets and cost data? Book a demo.