## How to use
Construction Variation / Change Order Tracker
Gather construction template - practical spreadsheet for live project controls
What this template does
Tracks variations/change orders from early notice through quotation, approval, valuation and implementation, with value and time-impact reporting.
How to use it
| 1 | Fill the yellow input cells only. Formula cells are protected so the workbook is harder to break.
| 2 | Use the worked example first to see the intended level of detail.
| 3 | Update the log weekly or daily, then review the dashboard and red/amber flags.
| 4 | Use links/references back to site diary entries, photos, drawings, instructions, emails and cost records.
| 5 | Export or copy the report/dashboard into your client or internal progress pack.
Workbook tabs
| Dashboard | Portfolio summary of variation value, status and risk.
| Variation Tracker | Main log for all variations/change orders.
| Worked Example | Pre-filled commercial example.
| Guidance | How to keep variation records claim-ready.
Gather note
Use the spreadsheet if you are doing this manually. Use Gather when you are ready to stop copying records between diaries, trackers, reports and forecasts.
Free template by Gather - gatherinsights.com ¦ Want this built automatically from site records? Book a demo: https://www.gatherinsights.com/en/book-a-demo

## Dashboard
Variation Dashboard
Commercial snapshot of submitted, approved and outstanding change
Summary
Total variations
Submitted value
Approved value
Value variance
Open / pending
Overdue actions
Status counts
Draft
Submitted
Under review
Approved
Rejected
Disputed
Implemented

## Variation Tracker
Variation / Change Order Tracker
Track change from instruction to commercial agreement. Yellow cells are inputs; grey cells calculate.
Variation ref | Date raised | Source / instruction ref | Package | Description | Cause / reason | Submitted date | Required response date | Days open | Submitted value £ | Approved value £ | Value variance £ | Time impact days | Status | Evidence ref | Owner | Action flag | Notes
Formulas:
Days open = IF([Date raised]="","",TODAY()-[Date raised])
Action flag = IF([Status]="Approved","Closed",IF([Status]="Rejected","Closed",IF(AND([Required response date]<>"",TODAY()>[Required response date],[Status]<>"Implemented"),"Overdue",IF([Status]="Disputed","Disputed","Open"))))

## Worked Example
Worked Example
Example variation log for a mid-sized construction project
Variation ref | Date raised | Source / instruction ref | Package | Description | Cause / reason | Submitted date | Required response date | Days open | Submitted value £ | Approved value £ | Value variance £ | Time impact days | Status | Evidence ref | Owner | Action flag | Notes
V-001 | 2026-06-03 | AI-014 | Groundworks | Additional drainage run to south boundary | Client change | 2026-06-06 | 2026-06-20 |  | 18500 | 17250 |  | 2 | Approved | Diary D-011 / PH-033 | QS |  | Agreed with minor rate adjustment
V-002 | 2026-06-12 | RFI-022 | Steel | Additional cleats following revised engineer detail | Design change | 2026-06-17 | 2026-07-01 |  | 9200 | 0 |  | 1 | Under review | Drawing S-214 rev C | PM |  | Awaiting engineer confirmation
V-003 | 2026-06-20 | SI-019 | M&E | Relocation of plant room containment | Coordination clash | 2026-06-27 | 2026-07-04 |  | 14600 | 0 |  | 3 | Disputed | Coordination minutes | Commercial Manager |  | Causation challenged
V-004 | 2026-07-02 | Email client | Finishes | Upgrade to reception floor finish | Client change | 2026-07-04 | 2026-07-18 |  | 7800 | 7800 |  | 0 | Implemented | Quote Q-044 | Site Manager |  | Implemented after approval
Free template by Gather - gatherinsights.com ¦ Want this built automatically from site records? Book a demo: https://www.gatherinsights.com/en/book-a-demo
Formulas:
Days open = TODAY()-[Date raised]
Action flag = IF([Status]="Approved","Closed",IF([Status]="Rejected","Closed",IF(AND([Required response date]<>"",TODAY()>[Required response date],[Status]<>"Implemented"),"Overdue",IF([Status]="Disputed","Disputed","Open"))))

## Guidance
Guidance
What good variation records normally include
Record checklist
| Instruction/source | Reference the instruction, drawing revision, email, site instruction or RFI that triggered the change.
| Cause | Separate client change, design change, unforeseen condition, acceleration, resequencing or contractor proposal.
| Evidence | Link to diary entries, photos, labour/plant allocation, supplier quotes and correspondence.
| Time impact | Record days claimed and keep it separate from value so programme impact is visible.
| Status | Use the same status labels every week so the dashboard is meaningful.
Free template by Gather - gatherinsights.com ¦ Want this built automatically from site records? Book a demo: https://www.gatherinsights.com/en/book-a-demo