## How to use
Construction Project Dashboard Template
Free template by Gather — gatherinsights.com
What this template is for
A practical, formula-only Excel template for construction teams. Fill the yellow cells; the calculated cells and dashboards update automatically.
How to use it
• Fill the Project Data tab with weekly metrics.
• Dashboard KPIs and charts update from the input table.
• Use the Issues & Actions tab to track blockers and owners.
• Use as a monthly client or internal project-control snapshot.
Brand note
Free template by Gather — gatherinsights.com
Want this reporting built automatically from site diaries, cost data and project records? Book a demo → gatherinsights.com/en/book-a-demo

## Project Data
Project Data
Free template by Gather — gatherinsights.com
Weekly project metrics
Week ending | Planned % | Actual % | BAC £ | Actual cost £ | Earned value £ | Open RFIs | Open variations | Delay days | Safety observations | Overdue actions | Notes
2026-02-28 | 12% | 12% | 3500000 | 432600 | 420000 | 8 | 0 | 1 | 0 | 4 | Example weekly update
2026-03-28 | 24% | 24% | 3500000 | 865200 | 840000 | 7 | 1 | 2 | 0 | 3 | Example weekly update
2026-04-28 | 36% | 36% | 3500000 | 1297800 | 1260000 | 6 | 1 | 0 | 1 | 2 | Example weekly update
2026-05-28 | 48% | 46% | 3500000 | 1730400 | 1610000 | 5 | 2 | 1 | 1 | 1 | Example weekly update
2026-06-28 | 60% | 58% | 3500000 | 2163000 | 2030000 | 4 | 2 | 2 | 1 | 0 | Example weekly update
2026-07-28 | 72% | 70% | 3500000 | 2595600 | 2450000 | 3 | 3 | 0 | 2 | 0 | Example weekly update
2026-08-28 | 84% | 82% | 3500000 | 3028200 | 2870000 | 2 | 3 | 1 | 2 | 0 | Example weekly update
2026-09-28 | 96% | 94% | 3500000 | 3460800 | 3290000 | 1 | 4 | 2 | 2 | 0 | Example weekly update

## Dashboard
Construction Project Dashboard
Free template by Gather — gatherinsights.com
Key metrics
Latest planned | Latest actual | Progress variance | Open RFIs | Overdue actions
Want this reporting built automatically from site diaries, cost data and project records? Book a demo → gatherinsights.com/en/book-a-demo

## Issues & Actions
Issues & Actions
Free template by Gather — gatherinsights.com
Open issues and project actions
Ref | Date raised | Type | Description | Owner | Due date | Status | Impact | Days open | Overdue? | Evidence / link | Next step
ACT-001 | 2026-07-01 | RFI | Door schedule clarification | Design Manager | 2026-07-10 | Open | Programme |  |  | RFI-041 | Chase consultant
ACT-002 | 2026-07-03 | Variation | Additional drainage run | QS | 2026-07-15 | In progress | Cost |  |  | VAR-012 | Submit valuation
Formulas:
Days open = IF([Date raised]="","",TODAY()-[Date raised])
Overdue? = IF(AND([Due date]<TODAY(),[Status]<>"Closed"),"Overdue","")