## How to use
Construction Pay Application / Valuation Template
Free template by Gather — gatherinsights.com
What this template is for
A practical, formula-only Excel template for construction teams. Fill the yellow cells; the calculated cells and dashboards update automatically.
How to use it
• Enter contract sum, variations, previous certificates and current valuation.
• Line items calculate gross, retention, VAT and amount due.
• Use the evidence checklist to reduce certification friction.
• Worked example shows a partial monthly application.
Brand note
Free template by Gather — gatherinsights.com
Want this reporting built automatically from site diaries, cost data and project records? Book a demo → gatherinsights.com/en/book-a-demo

## Pay Application
Pay Application / Valuation
Free template by Gather — gatherinsights.com
Application summary
Contract sum £ | 2400000 | Approved variations £ | 85000 | Previous certified £ | 650000 | Retention % | 3% | VAT % | 20% | Application no. | 4
Valuation line items
Item | Description | Contract value £ | % complete | Value to date £ | Previously certified £ | Current application £ | Evidence ref | Certification status | Notes
1 | Preliminaries | 200000 | 60% |  | 90000 |  | DIARY-WK12 | Submitted
2 | Groundworks | 650000 | 95% |  | 550000 |  | PHOTOS-104 | Agreed
3 | Envelope | 800000 | 25% |  | 10000 |  | PROG-005 | Submitted
Totals
Gross current application
Retention deduction
Net before VAT
VAT
Amount due

## Dashboard
Pay Application Dashboard
Free template by Gather — gatherinsights.com
Key metrics
Current application | Retention | Amount due | Value to date
Want this reporting built automatically from site diaries, cost data and project records? Book a demo → gatherinsights.com/en/book-a-demo