## How to use
Construction Meeting Minutes + Action Tracker
Free template by Gather — gatherinsights.com
What this template is for
A practical, formula-only Excel template for construction teams. Fill the yellow cells; the calculated cells and dashboards update automatically.
How to use it
• Use Meeting Minutes for agenda items, decisions and discussion notes.
• Use the Action Tracker to assign owners and due dates.
• Open and overdue actions flow into the dashboard.
• Record RFIs, variations or CEs triggered by decisions.
Brand note
Free template by Gather — gatherinsights.com
Want this reporting built automatically from site diaries, cost data and project records? Book a demo → gatherinsights.com/en/book-a-demo

## Meeting Minutes
Construction Meeting Minutes
Free template by Gather — gatherinsights.com
Meeting details
Project |  | Meeting type |  | Date |  | Chair |  | Attendees | Next meeting
Minutes
Agenda item | Discussion summary | Decision made | Action ref | Linked RFI / CE / variation | Owner | Due date | Status
Programme | Block A is two days behind due to access constraints | Resequence façade works | ACT-001 | RFI-041 | Planner | 2026-07-10 | Open
Commercial | Drainage change instructed by client | QS to submit variation | ACT-002 | VAR-014 | QS | 2026-07-12 | Open

## Action Tracker
Action Tracker
Free template by Gather — gatherinsights.com
Actions
Action ref | Date raised | Source meeting | Action | Owner | Due date | Status | Priority | Days open | Overdue? | Linked record | Notes
ACT-001 | 2026-07-04 | Progress meeting | Confirm resequencing logic | Planner | 2026-07-10 | Open | High |  |  | RFI-041
ACT-002 | 2026-07-04 | Commercial meeting | Submit drainage variation | QS | 2026-07-12 | Open | Medium |  |  | VAR-014
Formulas:
Days open = IF([Date raised]="","",TODAY()-[Date raised])
Overdue? = IF(AND([Due date]<TODAY(),[Status]<>"Closed"),"Overdue","")

## Dashboard
Meeting Actions Dashboard
Free template by Gather — gatherinsights.com
Key metrics
Open actions | Overdue | High priority | Total actions
Want this reporting built automatically from site diaries, cost data and project records? Book a demo → gatherinsights.com/en/book-a-demo