## How to use
Construction Punch List / Defects Tracker
Free template by Gather — gatherinsights.com
What this template is for
A practical, formula-only Excel template for construction teams. Fill the yellow cells; the calculated cells and dashboards update automatically.
How to use it
• Record each defect by location, package and responsible party.
• Use due dates and status to track closeout risk.
• Use evidence references for photos, inspection records and sign-off.
• Dashboard surfaces overdue and high-priority items.
Brand note
Free template by Gather — gatherinsights.com
Want this reporting built automatically from site diaries, cost data and project records? Book a demo → gatherinsights.com/en/book-a-demo

## Punch List
Punch List / Defects Tracker
Free template by Gather — gatherinsights.com
Defect and closeout register
Item ID | Date raised | Location | Package / trade | Defect description | Responsible party | Priority | Due date | Status | Date closed | Days open | Overdue? | Photo ref | Reinspection date | Client sign-off | Cost / retention risk £ | Notes
DEF-001 | 2026-07-01 | Level 3 Apt 12 | Joinery | Door latch not aligned | Joinery Sub | High | 2026-07-07 | Open |  |  |  | IMG-201 | 2026-07-08 | No | 1500 | Blocking handover
DEF-002 | 2026-07-03 | Lobby | Decoration | Paint touch-ups | Painter | Medium | 2026-07-10 | Closed | 2026-07-09 |  |  | IMG-225 | 2026-07-09 | Yes | 250
Formulas:
Days open = IF([Date raised]="","",IF([Date closed]="",TODAY()-[Date raised],[Date closed]-[Date raised]))
Overdue? = IF(AND([Due date]<TODAY(),[Status]<>"Closed"),"Overdue","")

## Dashboard
Punch List Dashboard
Free template by Gather — gatherinsights.com
Key metrics
Total items | Open items | Overdue | Retention risk
Want this reporting built automatically from site diaries, cost data and project records? Book a demo → gatherinsights.com/en/book-a-demo