## How to use
Materials Delivery Log Template
Free template by Gather — gatherinsights.com
What this template is for
A practical, formula-only Excel template for construction teams. Fill the yellow cells; the calculated cells and dashboards update automatically.
How to use it
• Record every delivery with order, supplier, quantity and condition.
• Track planned vs actual delivery dates and whether the delivery affects programme.
• Use the dashboard to see late, damaged and missing deliveries.
• Reference photos, delivery notes and inspections for evidence.
Brand note
Free template by Gather — gatherinsights.com
Want this reporting built automatically from site diaries, cost data and project records? Book a demo → gatherinsights.com/en/book-a-demo

## Delivery Log
Materials Delivery Log
Free template by Gather — gatherinsights.com
Deliveries
Delivery ID | Planned date | Actual date | Supplier | Material | Order / PO ref | Quantity ordered | Quantity received | Unit | Condition | Location stored | Required for activity | Programme critical? | Days late | Variance qty | Issue / action | Evidence ref | Status
DEL-001 | 2026-07-01 | 2026-07-02 | BuildSupplies | Rebar | PO-445 | 12 | 12 | t | Good | Laydown A | Ground beams | Yes |  |  | None | DN-001 | Closed
DEL-002 | 2026-07-04 |  | RoofCo | Insulation | PO-482 | 500 | 0 | m2 |  | Awaiting | Roof works | Yes |  |  | Chase supplier |  | Open
Formulas:
Days late = IF([Actual date]="",IF([Planned date]<TODAY(),TODAY()-[Planned date],0),MAX(0,[Actual date]-[Planned date]))

## Dashboard
Materials Delivery Dashboard
Free template by Gather — gatherinsights.com
Key metrics
Total deliveries | Open deliveries | Late days | Damaged | Critical
Want this reporting built automatically from site diaries, cost data and project records? Book a demo → gatherinsights.com/en/book-a-demo