## How to use
Final Account Tracker Template
Free template by Gather — gatherinsights.com
What this template is for
A practical, formula-only Excel template for construction teams. Fill the yellow cells; the calculated cells and dashboards update automatically.
How to use it
• Track contract sum, variations, provisional sums, claims, contra charges and payments.
• Use status and evidence fields to control closeout.
• Dashboard highlights agreed value, disputed value and outstanding items.
• Use before final account meetings to avoid spreadsheet archaeology.
Brand note
Free template by Gather — gatherinsights.com
Want this reporting built automatically from site diaries, cost data and project records? Book a demo → gatherinsights.com/en/book-a-demo

## Final Account Tracker
Final Account Tracker
Free template by Gather — gatherinsights.com
Final account items
Item ID | Category | Description | Submitted value £ | Agreed value £ | Variance £ | Status | Evidence ref | Owner | Date submitted | Target agreement date | Days outstanding | Dispute risk | Notes
FA-001 | Variation | Additional drainage | 45000 | 38000 |  | Agreed | VAR-014 | QS | 2026-07-01 | 2026-07-20 |  | Low
FA-002 | Claim | Weather delay prelims | 18000 | 0 |  | Disputed | W-002 | Commercial Manager | 2026-07-04 | 2026-07-25 |  | High | Need met evidence
FA-003 | Provisional Sum | Landscaping allowance | 60000 | 55000 |  | Submitted | PS-003 | QS | 2026-07-07 | 2026-07-28 |  | Medium
Formulas:
Days outstanding = IF(AND([Date submitted]<>"",[Status]<>"Agreed"),TODAY()-[Date submitted],0)

## Dashboard
Final Account Dashboard
Free template by Gather — gatherinsights.com
Key metrics
Submitted value | Agreed value | Variance | Disputed items | Outstanding items
Want this reporting built automatically from site diaries, cost data and project records? Book a demo → gatherinsights.com/en/book-a-demo