## How to use
Weather Delay Log Template
Free template by Gather — gatherinsights.com
What this template is for
A practical, formula-only Excel template for construction teams. Fill the yellow cells; the calculated cells and dashboards update automatically.
How to use it
• Capture weather conditions, affected activities and lost time.
• Track whether an event is programme-critical or claim-relevant.
• Use evidence references for forecasts, photos and diary records.
• Dashboard shows total lost hours and open claim events.
Brand note
Free template by Gather — gatherinsights.com
Want this reporting built automatically from site diaries, cost data and project records? Book a demo → gatherinsights.com/en/book-a-demo

## Weather Delay Log
Weather Delay Log
Free template by Gather — gatherinsights.com
Weather events
Event ID | Date | Weather type | Condition details | Affected activity | Location | Planned labour | Actual labour | Planned hours | Lost hours | Programme critical? | Notice required? | Notice submitted? | Evidence refs | Claim status | Cost impact £ | Days since event | Notes
W-001 | 2026-07-05 | Heavy rain | Persistent rain AM, standing water | Excavation | Zone 2 | 8 | 2 | 64 | 40 | Yes | Yes | Yes | DIARY-0705; PHOTO-33 | Notified | 1800 |  | Pumps required
W-002 | 2026-07-12 | High wind | Crane lift suspended | Steel lift | Block B | 6 | 1 | 48 | 36 | Yes | Yes | No | MET-0712 | Draft | 2400
Formulas:
Days since event = IF([Date]="","",TODAY()-[Date])

## Dashboard
Weather Delay Dashboard
Free template by Gather — gatherinsights.com
Key metrics
Events | Lost hours | Cost impact | Notices due | Critical events
Want this reporting built automatically from site diaries, cost data and project records? Book a demo → gatherinsights.com/en/book-a-demo