## How to use
Procurement Tracker / Long-Lead Items Register
Free template by Gather — gatherinsights.com
What this template is for
A practical, formula-only Excel template for construction teams. Fill the yellow cells; the calculated cells and dashboards update automatically.
How to use it
• Track procurement packages and long-lead items from enquiry to delivery.
• Use required-on-site and forecast-delivery dates to expose programme risk.
• Record design approval, order status and supplier ownership.
• Dashboard flags late and critical items.
Brand note
Free template by Gather — gatherinsights.com
Want this reporting built automatically from site diaries, cost data and project records? Book a demo → gatherinsights.com/en/book-a-demo

## Procurement Register
Procurement / Long-Lead Items Register
Free template by Gather — gatherinsights.com
Procurement items
Item ID | Package | Item description | Supplier | Design approval required? | Approval status | Enquiry date | Order date | Required on site | Forecast delivery | Actual delivery | Lead time days | Days to required | Late risk | Order value £ | Programme critical? | Owner | Status | Notes
PR-001 | Envelope | Curtain wall brackets | FacadeCo | Yes | Approved | 2026-06-01 | 2026-06-20 | 2026-08-15 | 2026-08-12 |  |  |  |  | 95000 | Yes | Package Manager | Ordered
PR-002 | MEP | Switchgear | PowerSys | Yes | Pending | 2026-06-05 |  | 2026-09-01 | 2026-09-20 |  |  |  |  | 180000 | Yes | MEP Manager | Enquiry | Factory slot risk
Formulas:
Days to required = IF([Required on site]="","",[Required on site]-TODAY())

## Dashboard
Procurement Dashboard
Free template by Gather — gatherinsights.com
Key metrics
Items | Late risks | Critical | Order value | Pending approvals
Want this reporting built automatically from site diaries, cost data and project records? Book a demo → gatherinsights.com/en/book-a-demo