## Slide 1
The Office Timeline add-in for PowerPoint will help you edit it with just a few clicks.
Get your free 14-day trial of Office Timeline here: https://www.officetimeline.com/14-days-trial Re-open this template, and create your impressive PowerPoint visual in 3 easy steps:
How to update this template in seconds
1
2
3
Click the Edit Data button on the Office Timeline tab.
Use the Data and Timeline views to edit swimlanes, milestones and tasks.
Click Save to instantly update the template.

## Slide 2
Planning
Logistics
Rentals &
services
Jun
Event kickoff meeting
100%
Event details
90%
Guest list
0%
Transportation
0%
Accomodation
0%
Shipping
0%
Venue
0%
Furniture/decor
0%
On-site services
Day 1
4
7
10
13
16
19
22
25
28
Team building event
Example of plan
Progress | 11%
Planning | 95%
Logistics | 0%
Rental & services | 0%
Status
On Track
Has Issues
Blocked
Made with
Chart: 
 | 0.11 | 1

## Slide 3
Jun 1
9 am
10 am
11 am
12 pm
1 pm
2 pm
3 pm
4 pm
5 pm
Arrival
09:00 - 09:30
Briefing
09:30 - 09:45
Bridge Build Challenge
10:00 - 10:50
Target Archery
10:55 - 11:45
Segway Experience
11:50 - 12:40
Lunch
12:45 - 13:30
Powerturn Slalom
13:40 - 14:30
Mobile Escape Room
14:35 - 15:25
Target Golf
15:30 - 16:20
Results & scores
16:45 - 17:00
Departure
17:00 - 17:30
Team building day
Sample itinerary for outdoor activities
Made with
Legend
Collective
Individual

## Slide 4
Build effective
team structure
Establish facilitative leadership
Build team bonding
Team orientation
Team selection and organization charting
Building and understanding team charter
Setting common purpose and expectation
Team communication and meeting plan
Leadership training workshop
Team building exercises
Workplace wellness activities
Provide mentorship guidance
Day 1
3
5
7
3 days
Team orientation
2 days
Team selection and organization charting
2 days
Building and understanding team charter
3 days
Setting common purpose and expectation
4 days
Team communication and meeting plan
2 days
Leadership training workshop
6 days
Team building exercises
6 days
Workplace wellness activities
4 days
Provide mentorship guidance
9
11
13
15
17
19
21
23
Team building strategy
Sample timeline of team building activities
Made with