## Slide 1
Development
Testing
Release
Scoping
Development
Stream
Integration
Training
Pilot
Deployment
2023
2024
Q4
Q1
Q2
Oct
Nov
Dec
Jan
Feb
Mar
Apr
1 wk
Scope
100%
1 wk
Conduct Needs Analysis
100%
Nov 11, 2023
Analysis Complete
3 wks
Design
Development
Automated Testing
10 wks
Manual
Unit Testing
Unit Testing
9 wks
Training
7 wks
Documentation
8 wks
Pilot
Pilot Plan Review
1 wk
Deploy
11 wks
Jan 27, 2024
Code freeze
Stabilize
Scope Complete
Oct 22, 2023
Design Complete
Dec 1, 2023
Development Complete
Dec 31, 2023
Pilot
Feb 17, 2024
Deployment Complete
Feb 24, 2024
Training review
Feb 28, 2024
Training final
Mar 29, 2024
Training outline
Jan 30, 2024
Product Development Plan Workstreams and key milestones
Dev architecture: Dan
Test process: Andreea
Release train: Carmen

## Slide 2
2022
2024
Delivery
Assurance
Workplan Releases
Stage I
Phase 1
Phase 2
Outline
Change Management
2022
2023
Q3
Q4
Q1
Q2
Q3
Q4
Today
Oct 22
Delivery assurance overview
Nov 18
Plan complete & validated
Feb 14
First cut
Second cut
Apr 24
Test
Jun 30
Aug 19
Deploy
2023 Release window 1
2023 Release window 2
Mar 10, 2023
2023-R1
Sep 8, 2023
2023-R2
Nov 2, 2022
Project kick-off
Workplan G0
Plan
Architect
Test
Deploy
Sep 22, 2023
Move to production
2024
Q1
Q2
Q3
Change strategy & analysis
Nov 10 - Mar 3
Change impact analysis
Training Plan
Training development
Training delivery
Aug 9 - Sep 26
Training material sign off
Sep 1, 2024
Project Initiation
2022/Nov
Prototype
2023/Apr
Final Product
2023/Sep
Training Prototype
2024/Apr
Training Final
2024/Sep
Digital Transformation Roadmap Top-level integrated schedule with project highlights

## Slide 3
2023
2025
Q2
Q3
Q4
Q1 2024
Q2
Q3
Q4
Q1 2025
Q2
Q3
16.9 mons
75%
System 1
Lead Time
Install 1A and 1B
Test & stabilize
14 mons
25%
System 2
Lead Time
Install 2A and 2B
Test & Stabilize
*Project Approval
May 1, 2023
Data Backup
2023/Nov
Training Day
2024/Apr
Manufacturer Certification
May 11, 2024
Sign Off
2025/Jul
Checkpoint A
November 25, 2023
Checkpoint B
October 28, 2024
Data Backup
2024/Oct
Project complete
July 7, 2025
Sign Off
2024/Aug
IT Project Management
Infrastructure Upgrade Timeline
Support Ops
Legend
Retail Ops
Ops Milestones
Key Milestones
* Tech sponsor approval required
Switch manufacturers selected
Budget approved & PO issued
IT staff training in progress

## Slide 4
Integrations
Business Apps
BPI
Today
2022
2023
2024
2025
2026
2027
5 yrs
89%
New CI Portal - Integrate with Mobile Apps
1.5 yrs
100%
Help Desk Integration Project
4.5 yrs
45%
New CI Portal - Global Rollout
4.5 yrs
59%
New CRM Solution - Retire Legacy CRM Systems
4.9 yrs
26%
New CI Portal - Consolidate Customer Data Project
4.5 yrs
60%
New CI Portal - Enable Big Data Analysis
4.4 yrs
ERP Solution
1.5 yrs
100%
Legacy Accounting
1.8 yrs
100%
Sales Collaboration Tool
4.5 yrs
60%
MS Power BI Reporting Platform
4.5 yrs
99%
Fitness Connect Mobile App Dev Project
4.5 yrs
97%
Integrate Fitness Connect To CRM Project
4.5 yrs
68%
Box Rollout
4.7 yrs
70%
CPQ Quoting Systems
2.4 yrs
Intranet Integration Engagement Project (FP)
4 yrs
Business Process Improvement Project
4 yrs
ABC GL Integration Engagement Project
Cross Systems Planning Portfolio
Development & Rollout Roadmap
Product / Carmen
Architect / Alex
Marketing / Diana
Biz Dev / Jodi
 | Budget | Actual
 | $1.3M | $1M
 | $500K | $650K
 | $330K | $89K
 | $745K | 475K
 | $398K | $103K
 | $225K | $270K
 | $3.3M | $4.55M
 | $110K | $1.75M
 | $230K | $1.5M
 | $100K | $80K
 | $248K | $250K
 | $145K | $140K
 | $739K | $680K
 | $115K | $98K
 | $150K | $10K
 | $280K | $265K
 | $330K | $322K

## Slide 5
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
9 wks
Assemble Resources
10.2 wks
Subcontractor Selection
Content Plan
9.8 wks
5 wks
Rollout
Prototype
34 wks
Development
Integration R1
9 wks
Integration R2
Jan 2 - Feb 25
Feb 26 - Oct 21
Project Kickoff
January 25
Executive Review
March 10
Executive Decision
March 21
Final Release
October 25
Press Release
August 2
Product Development & Launch
Planning & Execution Overview for MPIQ
Goal | Owner | Target | %
Foundation API coverage | Eddy | 50% | 5%
Infrastructure architecture | Carmen | 18% | 13%
Test coverage | Anna | 15% | 14%
Executive Summary
Development is progressing without issues
Potential issues anticipated with integrations
Content work ahead of schedule

## Slide 6
2024
Test Management
Change Management
Q4
Q1
Q2
Q3
Q4
Jan 9 - Feb 3
Test preparation
Feb 3 - Mar 1
Test Scenario development
Mar 1 - Apr 12
Configuration unit testing
Mar 21 - Apr 25
Finalize scenarios
May 2 - Jun 26
Test execution
Jul 3 - Aug 27
Parallel testing
E2E: Sign Off
2024 Jun 29
Draft test strategy
2024 Dec 5
CUT: Sign Off
2024 Apr 13
Nov 28 - Mar 3
Strategy and analysis
Mar 3 - Mar 26
Stakeholder engagement / Change impact analysis
Mar 26 - Apr 30
Communication and training plan
Apr 30 - Aug 6
Training development
Aug 6 - Sep 23
Training delivery
Jul 10 - Sep 29
Communications delivery
Sep 15 - Dec 3
Stabilization
2024 Aug 30
Training material sign Off
2023
2024
Project Initiation
2023 Nov 11
Product: Prototype
2024 Apr 20
Product: Final
2024 Sep 8
Test & Change Management Plan Overview of dependencies

## Slide 7
 Systems
Controls
Documentation
Personnel
Policies
Risk
Partners
Systems
Onboarding
Auditor
Process
Q2
Q3
Azure Connect
365 Connect
Partner 1
Partner 2
 Risk Assessment Survey
 DevOps access
100%
Devices compliant
Policies drafted
95%
Biz Continuity Plan developed
5%
Partner docs
80%
20%
Risk Mitigation plans
Risk Questionnaires
 Azure configurations
100%
 365 access
100%
Policies approved
89%
Asset inventory
80%
Policies & training
Assign control owners
Vet auditor
Prep with auditor
Processes built & documented
System diagram
50%
Apr
May
Jun
Jul
Aug
Sep
Next quarter planned | Top 3 deliverables in Q2 2022 | Challenges anticipated | Help needed
Complete foundation Roll out training / policies Engage auditor | Implement tooling Azure, 365, and VSO connectivity Policy drafts Visible path | Limited technical capacity Learning curve Unknowns | Technical team engagement Leadership support
Security Certification Roadmap
Passing Control Tests
75%

## Slide 8
Marketing
Product
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Develop
Excite
Ignite
Partners
Press Kit
Media Campaign
45.6 weeks
Web app
34.2 weeks
Mobile app
27 weeks
Windows app
Web Beta
Mobile Beta
Win Beta
Partner NDAs
Sales Agreements
Distributor Agreements
Web App Release
Nov 22
Mobile App Release
Dec 1
PC App Release
Marketing: Diana
Technical: Dan
Release: Carmen
Summary
Marketing planning sessions progressing.
Product feasibility studies are complete.
Proof of concept started early.
 | Marketing | Product | Legal
Web | $3.3M | $4.55M | $650K
Mobile | $500K | $1.75M | -
Win | $330K | $1.5M | -
Marketing and Development
Product Launch Plan

## Slide 9
2021
2023
Other
Europe
NA
Germany
France
UK
USA
Canada
Q1
Q2
Q3
Apr 2021 - Jun 2022
Germany Pilot
Jul 2021 - Jul 2022
France Pilot
Jan 2021 - Dec 2022
Execution
Jan 2021 - Dec 2023
Production
Jan 2021 - Dec 2023
Global Execution
Jul 2021 - Dec 2023
Production
Class II
Class III
Class I
Publish data
Jun 4, 2022
China
NZ
South Korea
Brazil
Data refresh
Jan 31, 2022
*Data refresh
Publish data
Apr 30, 2022
Class I
Sep 5, 2022
Class III
Jul 1, 2022
Q4
Q1 2022
Q2
Q3
Q4
Q1 2023
Q2
Q3
Q4
Push to Class IV
Global Initiatives Timeline
WW Pilot Programs & Execution
Global Programs End Date | Dec 2023
WW IT Lead | Tim Stumbles
Project Sponsor(s) | Sebastian Stingu
PROJECT STATUS
Budget | Forecast
$705,000 | $695,000
$635,000 | $735,000
$905,000 | $1.1M
$2.2M | 2.0M
$2.9M | $2.5M
$1.1M | $2.7M

## Slide 10: Product Release Schedule
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
2018
67 days
Jan 8 - Apr 10
Release 1
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
QA + Refinement
68 days
Apr 11 - Jul 13
Release 2
Sprint 6
Sprint 7
Sprint 8
Sprint 9
Sprint 10
QA + Refinement
68 days
Jul 14 - Oct 17
Release 3
Sprint 11
Sprint 12
Sprint 13
Sprint 14
Sprint 15
QA + Refinement
Release 1
Apr 10
Release 2
Jul 13
Release 3
Oct 17
R3 Sprint Planning
Project | Budget | 
Rainer | $255.3K | 
Olympus | $370.0K | 
Baker | $193.2K | 
St. Helens | $745.3K | 
Core projects slightly off-track due to unexpected framework blockers.