## Slide 1
The Office Timeline add-in for PowerPoint will help you edit it with just a few clicks.
Get your free 14-day trial of Office Timeline here: https://www.officetimeline.com/office-timeline/14-days-trial Re-open this template, and create your impressive PowerPoint visual in 3 easy steps:
How to update this template in seconds
1
2
3
Click the Edit Data button on the Office Timeline tab.
Use the Data and Timeline views to edit swimlanes, milestones and tasks.
Click Save to instantly update the template.

## Slide 2
2025
2025
Today
Feb
Mar
Apr
May
Jun
19 days
Feb 12 - Mar 10
Scope
100%
25 days
Feb 15 - Mar 23
Project Resources
76%
15 days
Mar 1 - Mar 23
Analysis
100%
35 days
Mar 23 - May 10
Design
70%
5 days
May 10 - May 16
Draft Specs
37%
17 days
Apr 27 - May 20
Development
40%
23 days
May 9 - Jun 10
Coding
20%
17 days
May 17 - Jun 10
UI
75%
20 days
May 24 - Jun 22
Testing
15%
12 days
Jun 1 - Jun 17
Training
0%
12 days
May 29 - Jun 14
Documentation
10%
Project Sponsor
Feb 15
Analysis Complete
Mar 23
Functional Design Complete
May 10
Project Status Report
Jun 14
Project Status Report