## Slide 1
The Office Timeline add-in for PowerPoint will help you edit it with just a few clicks.
Get your free 14-day trial of Office Timeline here: https://www.officetimeline.com/office-timeline/14-days-trial Re-open this template, and create your impressive PowerPoint visual in 3 easy steps:
How to update this template in seconds
1
2
3
Click the Edit Data button on the Office Timeline tab.
Use the Data and Timeline views to edit swimlanes, milestones and tasks.
Click Save to instantly update the template.

## Slide 2
2025
2029
Phase I
Phase II
Phase III
2025
2026
18 mons
Jan 2025 - Jun 2026
Trial
Jul 2026 - Jan 2028
19 mons
Trial
14 mons
Sep 2027 - Nov 2028
Trial
Jan
Mar
May
Jul
Sep
Nov
Jan
2027
2028
Today
2029
Mar
May
Jul
Sep
Nov
Jan
Mar
May
Jul
Sep
Nov
Jan
Mar
May
Jul
Sep
Nov
Jan
+30.7 days
+32 days
0 days
Report
Oct 15 '25
Apply for Drug Approval
Aug 10 '27
Report
May 18 '28
Estimated Drug Approval Date
Nov 11 '28
Patients Recruited
Feb 4 '25
Patients
Enrolled
Jun 3 '25
Study Kick-off
Sep 9 '25
Patients
Recruited
Aug 7 '26
Patients
Enrolled
Dec 11 '26
Study
Kick-off
May 8 '27
Study
Modified
Sep 17 '27
Patients
Recruited
Oct 11 '27
Patients
Enrolled
Feb 10 '28
Study
Kick-off
May 15 '28
0 days
0 days
0 days
0 days
0 days
0 days
0 days
0 days
0 days
0 days
0 days
0 days
0 days
0 days
Made with
Stages
Recruitment
Enrollment
Kick-off
Modifications
Clinical Trial Gantt chart