## Slide 1
The Office Timeline add-in for PowerPoint will help you edit it with just a few clicks.
Get your free 14-day trial of Office Timeline here: https://www.officetimeline.com/office-timeline/14-days-trial Re-open this template, and create your impressive PowerPoint visual in 3 easy steps:
How to update this template in seconds
1
2
3
Click the Edit Data button on the Office Timeline tab.
Use the Data and Timeline views to edit swimlanes, milestones and tasks.
Click Save to instantly update the template.

## Slide 2
2027
2026
Site preparation
Demolition
Framing & structural work
Electrical & plumbing
Interior finishing
Today
2026
2027
Aug 3 - Aug 4
Site survey and inspection
Aug 5 - Aug 13
Site clearance
100%
Sep 4 - Sep 15
Frame building structure
0%
Sep 23 - Oct 12
Install structural components
0%
Oct 20 - Oct 31
Rough-in electrical wiring
0%
Oct 22 - Nov 10
Rough-in plumbing
0%
Nov 15 - Nov 25
Install fixtures & connections
0%
Dec 1 - Dec 15
Install drywall & insulation
0%
Dec 16 - Dec 22
Paint interior walls & ceilings
0%
Jan 7 - Jan 12
Flooring installation
0%
Aug 14 - Aug 26
Demolition
60%
Aug
Sep
Oct
Nov
Dec
Jan
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
Week 1
2 days
100%
7 days
9 days
8 days
14 days
9 days
14 days
8 days
11 days
5 days
4 days
First inspection
Dec 22
Final walkthrough and approval
Jan 16
Demolition completed
Aug 26
+261 days
+261 days
+260 days
Renovation timeline