## Slide 1
The Office Timeline add-in for PowerPoint will help you edit it with just a few clicks.
Get your free 14-day trial of Office Timeline here: https://www.officetimeline.com/office-timeline/14-days-trial Re-open this template, and create your impressive PowerPoint visual in 3 easy steps:
How to update this template in seconds
1
2
3
Click the Edit Data button on the Office Timeline tab.
Use the Data and Timeline views to edit swimlanes, milestones and tasks.
Click Save to instantly update the template.

## Slide 2
2026
2026
Site clearing & excavation
Foundation pour
Steel framing
Mechanical & electrical systems
Roofing & glazing
Interior construction
Exterior finishing
Final inspection
Surveying & site prep
Concrete foundation
Structural framing
Electrical systems
HVAC systems
Roofing
Glazing
Drywall & insulation
Flooring
Exterior painting
Approval
Mar
Apr
May
Jun
Jul
Aug
Mar 1 - Mar 3
Site survey and land inspection
Mar 4 - Mar 14
Site clearing and excavation
Mar 11 - Mar 14
Pour foundation concrete
Mar 11 - Mar 26
Install steel framing
Mar 26 - Apr 10
Frame building structure
Apr 1 - Apr 15
Install electrical wiring
Apr 5 - Apr 15
Install plumbing systems
Apr 10 - Apr 20
Install HVAC systems
May 1 - May 15
Install roof structure
May 15 - Jun 1
Install windows and glazing
Jun 1 - Jun 15
Install drywall and insulation
Jun 10 - Jun 20
Paint interior walls and ceilings
Jun 18 - Jun 27
Install flooring
Jul 1 - Jul 15
Exterior painting and finishing
First inspection
Sign-off
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
Week 1
Today
2 days
0%
0 days
8 days
0%
+2 days
3 days
0%
0 days
12 days
0%
0 days
12 days
0%
0 days
11 days
0%
0 days
8 days
0%
+3 days
7 days
0%
0 days
11 days
0%
-2 days
12 days
0%
0 days
11 days
0%
0 days
8 days
0%
0 days
7 days
0%
-1 day
11 days
0%
0 days
Aug 18
0 days
Aug 24
0 days
Foundation curing
Final inspection of roofing & glazing
Final exterior inspection
Mar 14
0 days
Jun 1
0 days
Jul 15
0 days
Construction building