## Slide 1
The Office Timeline add-in for PowerPoint will help you edit it with just a few clicks.
Get your free 14-day trial of Office Timeline here: https://www.officetimeline.com/office-timeline/14-days-trial Re-open this template, and create your impressive PowerPoint visual in 3 easy steps:
How to update this template in seconds
1
2
3
Click the Edit Data button on the Office Timeline tab.
Use the Data and Timeline views to edit swimlanes, milestones and tasks.
Click Save to instantly update the template.

## Slide 2
2026
2026
Land surveying
Excavation & groundworks
Piling & foundations
Concrete works
Road work & paving
Utilities installation
Inspection & handover
Surveying
Excavation
Groundworks
Foundation piling
Preparation
Pouring
Curing & inspection
Excavation
Road paving
Excavation
Installation
Final inspections
Mar
Apr
May
Jun
Jul
Mar 1 - Mar 3
Survey land and site inspection
Finalize land survey
Mar 4
Mar 6 - Mar 16
Begin excavation and site preparation
Mar 17 - Mar 23
Complete groundwork and trenching
Mar 21 - Apr 5
Install piling and foundations
Foundation curing and inspections
Apr 6
Apr 10 - Apr 15
Pour concrete foundation
Apr 16 - Apr 27
Pour slabs and supports
Apr 25 - May 5
Concrete curing and structural inspection
May 6 - May 18
Begin excavation for road base
May 15 - Jun 4
Lay asphalt and road surfacing
Jun 4 - Jun 10
Dig trenches for utility lines
Jun 10 - Jun 23
Install water, gas, and electric lines
Jun 29 - Jul 5
Final site inspections
Inspect utility installations
Jun 24
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
Week 1
Today
2 days
0%
0 days
7 days
0%
5 days
0%
10 days
0%
0 days
4 days
0%
8 days
0%
7 days
0%
9 days
0%
15 days
0%
5 days
0%
10 days
0%
+3 days
5 days
0%
Final handover to client
Jul 9
Site handover to contractor
Mar 1
0 days
0 days
Infrastructure roadmap