## Slide 1
The Office Timeline add-in for PowerPoint will help you edit it with just a few clicks.
Get your free 14-day trial of Office Timeline here: https://www.officetimeline.com/office-timeline/14-days-trial Re-open this template, and create your impressive PowerPoint visual in 3 easy steps:
How to update this template in seconds
1
2
3
Click the Edit Data button on the Office Timeline tab.
Use the Data and Timeline views to edit swimlanes, milestones and tasks.
Click Save to instantly update the template.

## Slide 2
2026
2027
PHASE 1 - Project initiation and planning
PHASE 2 - System design and development
PHASE 3 -
Testing and deployment
PHASE 4 - Maintenance
PMO, Senior management, BA, all relevant
IT, External security consultants
IT, QA, Marketing
IT support
2026
2027
4/26 - 6/26
Project initiation and planning
Project scope
Feasibility study
Requirements gathering
Project plan development
6/26 - 10/26
System design and development
System architecture design
Development (dev & testing)
Security and penetration testing
Security audit
10/26 - 1/27
Testing and deployment
User acceptance testing (UAT)
Performance testing
Deployment and go-live
User training
Post-implementation review
12/26 - 3/27
Maintenance and support
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
3
5
7
9
11
13
15
17
19
21
23
25
27
29
31
33
35
37
39
41
43
45
47
49
51
Go-live
12/26
Apr
Week 1
Today
50 days
10 days
4/26 - 4/26
20 days
5/26 - 6/26
6 days
5/26 - 5/26
14 days
4/26 - 5/26
85 days
19 days
6/26 - 7/26
49 days
7/26 - 9/26
14 days
9/26 - 10/26
15 days
9/26 - 10/26
+261 days
64 days
15 days
10/26 - 11/26
10 days
11/26 - 11/26
19 days
11/26 - 12/26
5 days
12/26 - 12/26
19 days
12/26 - 1/27
75 days
Initial budget
Apr 8
+261 days
Communication plan
Jun 12
+261 days
Risk assessment
Apr 30
+261 days
Estimate ROI
May 7
+261 days
Integration testing
Sep 15
+261 days
System optimization
Feb 15
+261 days
Knowledge transfer
Mar 15
+261 days
Online Banking Platform Implementation