## Slide 1
The Office Timeline add-in for PowerPoint will help you edit it with just a few clicks.
Get your free 14-day trial of Office Timeline here: https://www.officetimeline.com/office-timeline/14-days-trial Re-open this template, and create your impressive PowerPoint visual in 3 easy steps:
How to update this template in seconds
1
2
3
Click the Edit Data button on the Office Timeline tab.
Use the Data and Timeline views to edit swimlanes, milestones and tasks.
Click Save to instantly update the template.

## Slide 2
2025
2025
Planning
Community
Vendors
Start
Skills
Implementation
Q2
May 1 - May 29
Program Planning
Define objectives
May 18 - Jun 22
Identify Community
Training analysis
Prioritize needs
Jun 8 - Jul 7
Vendor Input
Deliverables
Commitment
Jun 12 - Aug 10
Skill Assessment
Identify recipients
Program award matrix
Finalize program budget
Jun 21 - Jul 28
Program Commencement
Determine locations
Jun 28 - Aug 30
Program Implementation
Execute program
Collect feedback
Follow-up training
Report results
May
Jun
Day 1
15
29
43
Q3
Jul
Aug
57
71
85
99
113
Sep
Today
21 days
12 days
May 1 - May 17
25 days
15 days
May 18 - Jun 7
10 days
Jun 7 - Jun 22
10 days
Jun 8 - Jun 20
21 days
9 days
Jun 12 - Jun 24
26 days
20 days
Jun 22 - Jul 20
41.6 days
11.2 days
Jun 12 - Jun 29
15 days
Jun 29 - Jul 20
15 days
Jul 19 - Aug 10
45 days
10.8 days
Jun 28 - Jul 14
11.9 days
Jul 14 - Jul 29
12.7 days
Jul 28 - Aug 14
12.1 days
Aug 13 - Aug 30
Secure team support
May 1
Create target list
May 18
Present findings to PM
Jun 6
Post program online
Jul 4
E-mail invitations
Jul 22
Issue purchase orders
Jun 20
Issue certificates
Aug 16
Program
Plan Template