Monte Carlo Exercise

Scenario: Estimating Well Duration

You are planning to drill a well and need to build a time estimate for the well duration based on uncertain drilling operations, weather, and unexpected nonproductive time. Since all these factors vary, we will use a Monte Carlo simulation to model different outcomes. We will be using 100% probability for all events for simplicity.

Step 1: Define the Variables

We assume:

- Meeting time (M): The time of the planning meeting in hours (deterministic).

- M/U BHA (B) The BHA operations in hours (random).

- Drilling (D): The drilling time in hours (random).

- Work String Free (S): The time working the string free in hours (random).

- Cut Pipe (C): The time cutting pipe and fishing in hours (random).

- POOH (P): The time pulling out of hole in hours (random).

- Waiting on Weather (W): The time spent waiting on weather to clear (deterministic).

- Nonproductive Time (N): Nonproductive time (random).

Step 2: Assign Probability

We assume:

- Meeting time (M)  2 hours

- M/U BHA (B)  6,8,16 hours

- Drilling (D)  30,40,60 hours

- Work String Free (S)  0,1,2 hours

- Cut Pipe (C)  3,6 hours

- POOH (P)  2,4,9 hours

- Waiting on Weather (W)  10 hours

- Nonproductive Time (N)  6,12 hours

Step 3: Generate Random Samples (Simulating 10 Trials)

To generate randomness, we use dice:

- Roll a 6-sided die for M/U BHA (B)

  - 1-2 → 6 hours

  - 3-4 → 8 hours

  - 5-6 → 16 hours

- Roll a 6-sided die for Drilling (D)

  - 1-2 → 30 hours

  - 3-4 → 40 hours

  - 5-6 → 60 hours

- Roll a 6-sided die for Work String Free (S)

  - 1-3 → 0 hours

  - 4-5 → 1 hour

  - 6 → 2 hours

- Roll a 6-sided die for Cut Pipe (C)

  - 1-3 → 3 hours

  - 4-6 → 6 hours

- Roll a 6-sided die for POOH (P)

  - 1-2 → 2 hours

  - 3-4 → 4 hours

  - 5-6 → 9 hours

- Roll a 6-sided die for Nonproductive Time (N)

  - 1-3 → 6 hours

  - 4-6 → 12 hours

Step 4: Perform Multiple Trials

We manually simulate 11 trials using dice rolls.

Step 5: Analyze Results

- Best Case (Lowest):

  - Trial 4 → 69 hours

- Worst Case (Highest):

  - Trial 7→ 117 hours

- Risk Assessment:

  - 10 out of 11 trials had durations under 100 hours

  - Only one trial resulted in a duration of over 100 hours.

Step 6: Decision Making

Based on this simulation:

- The expected duration is under 100 hours.