# Pre-Production Meeting Agenda

Video Production — Meeting Template

| Project |  |
| --- | --- |
| Date |  |
| Shoot Date(s) |  |
| Meeting Location |  |
| Attendees |  |

Meeting Agenda

| Time | Agenda Item | Led By | What to Cover |
| --- | --- | --- | --- |
| 0:00–0:05 | Project overview and objectives | Producer | One-minute recap of the project scope, deliverables, and shoot dates. Confirm everyone has the latest script and creative brief. State the goal of the meeting: lock the plan and assign open items. |
| 0:05–0:15 | Creative review and alignment | Director | Walk through the creative approach: tone, visual references, key moments, any changes since the last creative review. Confirm the shot list is locked or flag remaining open questions. |
| 0:15–0:30 | Schedule walkthrough | Producer / 1st AD | Walk through the shooting schedule scene by scene. Confirm scene order, time allocations, meal breaks, company moves, and wrap time. Flag any timing conflicts or tight windows. |
| 0:30–0:40 | Logistics review | Producer | Confirm location access, load-in windows, parking, power, catering, and any permits. Confirm talent call times, wardrobe status, HMU requirements. Confirm equipment package and any specialty gear. |
| 0:40–0:50 | Department-specific needs | Each dept. head | Quick round-robin: each department head raises anything not already covered. Keep each response to one or two items max. |
| 0:50–0:55 | Open questions | Producer | Any unanswered questions from the group. Anything the client needs to decide before the shoot. Flag items that can’t be resolved in the room and assign owners. |
| 0:55–1:00 | Action items and next steps | Producer | Read back every open action item with an owner and a deadline. Confirm the date for distributing the final schedule and call sheet. |

Notes

- The schedule walkthrough gets the biggest time block because it surfaces the most issues. Protect this section when time gets tight.

- Scale the template to the shoot. A simple one-day interview shoot may only need 30 minutes. Multi-day shoots with large crews may need 90.

- Send the agenda, latest script, shot list, and schedule draft to all attendees at least 48 hours before the meeting.

- Keep the invite list to decision makers only. Brief the rest of the crew with a written recap afterward.

Post-Meeting Action Items

Capture every unresolved item with an owner and a deadline. Distribute within 24 hours of the meeting.

| Action Item | Owner | Deadline |
| --- | --- | --- |

Decisions Locked in This Meeting

Record any creative, logistics, or scheduling decisions confirmed during the meeting.

Next Touchpoint Before Shoot

| Date / Time |  |
| --- | --- |
| Format | (call / in-person / email check-in) |
| Purpose |  |