## Sheet1
Phase / Stage | Specific Task (Activity Level) | Duration (Working Days) | Preceding Task/Dependency | Responsible Party | Required Client Input/Action (Critical Path) | Gate / Milestone (Required Sign-Off) | Completion Status (TRUE/FALSE) | Risk Factor
**I. Pre-Design** | **A. Program Verification & Needs Assessment** | 5 | Contract Signed | Architect (PM) | Finalized Program Document, Stakeholder Interview Schedule. | Program Approval Milestone | TRUE | Low
**I. Pre-Design** | **B. Site Analysis & Feasibility Study (Zoning)** | 10 | A | Architect | Existing Survey/Geotech Data. | Feasibility Report Approved | TRUE | Medium
**I. Pre-Design** | **C. Budget & Schedule Confirmation** | 3 | B (High-level data only) | Client/Cost Mgr | Final Project Budget Ceiling, Financing Secured. | Project Parameters Locked | FALSE | High
**II. Schematic Design (SD)** | **D. Massing Studies & Conceptual Layouts (3 Options)** | 15 | C (Approved Parameters) | Architect (Lead) | Feedback on Massing Option 1, 2, 3. | Conceptual Design Review (Client Mtg) | FALSE | Medium
**II. Schematic Design (SD)** | **E. Structural & MEP System Feasibility Input** | 7 | D (Selected Concept) | Consultants | N/A | System Selection Confirmed | FALSE | Low
**II. Schematic Design (SD)** | **F. SD Deliverable Package Preparation** | 5 | E | Architect | N/A | **SD Phase Sign-Off** | FALSE | Low
**III. Design Development (DD)** | **G. Major Material and System Selection (FF\&E)** | 12 | F (SD Sign-Off) | Architect/Client | Finalized Material Palettes and Key Equipment Specs. | DD Material Approval | FALSE | Medium
**III. Design Development (DD)** | **H. Consultant Coordination & Clash Resolution (First BIM Audit)** | 15 | G | BIM Manager | Consultant Models Uploaded to CDE. | BIM Clash Report Issued | FALSE | High
**III. Design Development (DD)** | **I. Preliminary Cost Estimate Review** | 5 | H | Cost Consultant | N/A | DD Estimate Approved (Must be within 5% of target) | FALSE | High
**IV. Construction Documents (CD)** | **J. Detailed Specification Writing & Review** | 20 | I (DD Approval) | Architect/Specs | N/A | Specs Package Completed | FALSE | Medium
**IV. Construction Documents (CD)** | **K. Final Code Review and Agency Submission Drafting** | 10 | J | Architect | Signed Authorization to Proceed with Permitting. | Code Review Completed | FALSE | High
**IV. Construction Documents (CD)** | **L. CD QA/QC Internal Peer Review** | 7 | K (Draft CD Set) | QC Lead | N/A | CD Set 90% Complete Check | FALSE | Low
**IV. Construction Documents (CD)** | **M. Final Consultant Deliverables Integration & Final Clash** | 5 | L (QC Check Complete) | BIM Manager | Final Consultant Drawings/Models. | **CD Phase Sign-Off (100% Set Issued)** | FALSE | Medium
**V. Tender/Bidding** | **N. Tender Package Preparation & Distribution** | 5 | M | Architect (PM) | Approved Bidder List. | Bidding Period Commenced | FALSE | Low
**V. Tender/Bidding** | **O. Bid Review, Qualification, and Recommendation** | 10 | Bids Received | Architect/Client | N/A | Contractor Recommendation Approved | FALSE | Medium