## Sheet1
Winning Architecture Proposal
Client / Project | Specific Focus | Key Data Required (Internal Input) | Deliverable Output (Client View) | Rationale / Strategic Purpose | Target Stakeholder | Checklist (TRUE/FALSE) | Required Level of Detail | Final Proposal
**I. Client & Project Insight** | **Client Pain Point Validation** | Pre-briefing notes, RFI responses, Meeting transcripts. | Bulleted list (3-5 points max) | Demonstrates active listening and proves the proposal is custom-built, not boilerplate. | Decision Maker | TRUE | High | Link Here
**I. Client & Project Insight** | **Defined Success Metrics** | Client's stated budget, functionality needs, aspirational goals (e.g., certification level). | Numbered List/Table | Aligns your service outcomes directly with the client's quantifiable goals. | Decision Maker | TRUE | High | Link Here
**I. Client & Project Insight** | **Project Assumptions Register** | Zoning codes, Geotech report status, Client's existing vendor list. | Itemized List | Mitigates future scope creep and clearly defines boundaries upfront. | Legal/Finance | TRUE | Medium | Link Here
**II. Design & Technical Approach** | **Phased Design Milestones** | Internal design process standards (AIA Phases), estimated hours per phase, client response windows. | Detailed Timeline/Flowchart | Manages client expectations regarding feedback loops and decision paralysis. | Project Manager | TRUE | High | Link Here
**II. Design & Technical Approach** | **Sustainability Strategy** | Material performance data, local climate analysis, energy modeling estimates. | Descriptive Paragraphs & Technical Specifications (Specs Table) | Positions the firm as forward-thinking and committed to long-term asset value. | Decision Maker | FALSE |  | Link Here
**II. Design & Technical Approach** | **Technology Integration Plan** | Specific software list (e.g., Revit, Rhino, Bluebeam), internal clash detection protocols. | Process Diagram & Explanatory Text | Showcases modern project management capabilities and quality control measures. | Project Manager | TRUE | Medium | Link Here
**III. Execution & Risk** | **Risk Identification & Mitigation Matrix** | Historical project risk logs, Supply chain status, Site assessment notes. | 3-Column Table (Risk, Impact, Mitigation Strategy) | Builds confidence by demonstrating proactive planning rather than reactive problem-solving. | Legal/Finance | TRUE | High | Link Here
**III. Execution & Risk** | **Communication Protocol** | Internal meeting standards, designated team roles (SPOC, backup), client's preferred medium. | Defined Policy Document/Table | Establishes clear, consistent working relationships and accountability. | Project Manager | TRUE | Medium | Link Here
**IV. Financial & Legal** | **Detailed Fee Breakdown by Phase** | Labor rates, consultant quotes, overhead calculations, reimbursable expense projections. | Itemized Budget Table (with percentages/fixed costs) | Provides complete financial transparency, justifying the total investment. | Finance Director | TRUE | High | Link Here
**IV. Financial & Legal** | **Scope Change Procedure** | Firm's standard change order form and approval workflow. | Workflow Diagram & Policy Statement | Protects both the client and the firm from ambiguity when project requirements inevitably shift. | Legal/Project Manager | TRUE | High | Link Here
**IV. Financial & Legal** | **Insurance & Liability Coverage Summary** | Current liability policy names, expiration dates, coverage limits. | List of Coverage Types | Addresses legal compliance and provides assurance regarding professional protection. | Legal/Finance | TRUE | Medium | Link Here

## Copy of Sheet1
Client / Project | Specific Focus | Key Data Required (Internal Input) | Deliverable Output (Client View) | Rationale / Strategic Purpose | Target Stakeholder | Checklist (TRUE/FALSE) | Required Level of Detail | Final Proposal
**I. Client & Project Insight** | **Client Pain Point Validation** | Pre-briefing notes, RFI responses, Meeting transcripts. | Bulleted list (3-5 points max) | Demonstrates active listening and proves the proposal is custom-built, not boilerplate. | Decision Maker | TRUE | High | Link Here
**I. Client & Project Insight** | **Defined Success Metrics** | Client's stated budget, functionality needs, aspirational goals (e.g., certification level). | Numbered List/Table | Aligns your service outcomes directly with the client's quantifiable goals. | Decision Maker | TRUE | High | Link Here
**I. Client & Project Insight** | **Project Assumptions Register** | Zoning codes, Geotech report status, Client's existing vendor list. | Itemized List | Mitigates future scope creep and clearly defines boundaries upfront. | Legal/Finance | TRUE | Medium | Link Here
**II. Design & Technical Approach** | **Phased Design Milestones** | Internal design process standards (AIA Phases), estimated hours per phase, client response windows. | Detailed Timeline/Flowchart | Manages client expectations regarding feedback loops and decision paralysis. | Project Manager | TRUE | High | Link Here
**II. Design & Technical Approach** | **Sustainability Strategy** | Material performance data, local climate analysis, energy modeling estimates. | Descriptive Paragraphs & Technical Specifications (Specs Table) | Positions the firm as forward-thinking and committed to long-term asset value. | Decision Maker | High |  | Link Here
**II. Design & Technical Approach** | **Technology Integration Plan** | Specific software list (e.g., Revit, Rhino, Bluebeam), internal clash detection protocols. | Process Diagram & Explanatory Text | Showcases modern project management capabilities and quality control measures. | Project Manager | TRUE | Medium | Link Here
**III. Execution & Risk** | **Risk Identification & Mitigation Matrix** | Historical project risk logs, Supply chain status, Site assessment notes. | 3-Column Table (Risk, Impact, Mitigation Strategy) | Builds confidence by demonstrating proactive planning rather than reactive problem-solving. | Legal/Finance | TRUE | High | Link Here
**III. Execution & Risk** | **Communication Protocol** | Internal meeting standards, designated team roles (SPOC, backup), client's preferred medium. | Defined Policy Document/Table | Establishes clear, consistent working relationships and accountability. | Project Manager | TRUE | Medium | Link Here
**IV. Financial & Legal** | **Detailed Fee Breakdown by Phase** | Labor rates, consultant quotes, overhead calculations, reimbursable expense projections. | Itemized Budget Table (with percentages/fixed costs) | Provides complete financial transparency, justifying the total investment. | Finance Director | TRUE | High | Link Here
**IV. Financial & Legal** | **Scope Change Procedure** | Firm's standard change order form and approval workflow. | Workflow Diagram & Policy Statement | Protects both the client and the firm from ambiguity when project requirements inevitably shift. | Legal/Project Manager | TRUE | High | Link Here
**IV. Financial & Legal** | **Insurance & Liability Coverage Summary** | Current liability policy names, expiration dates, coverage limits. | List of Coverage Types | Addresses legal compliance and provides assurance regarding professional protection. | Legal/Finance | TRUE | Medium | Link Here