## V5 Baseline Task List
BASELINE TASK LIST
Transition
Milestone Task | Task Name | Additional Info | Baseline Job Title | Department | Phase | Community | Target Days Out | Static Target Date | Start Days Out | Start Static Date | Contact Info | Contact Email | Link 1 Name | Link 1 URL | Link 2 Name | Link 2 URL | Link 3 Name | Link 3 URL | Link 4 Name | Link 4 URL
No | Identify third-party consultants | The incoming management company needs to know which outside experts — legal, FF&E, IT, F&B consulting — are already under contract so specialized services aren't inadvertently dropped at handover. Many consultants hold institutional knowledge about this property that would take months to rebuild. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Obtain employee roster | Before any workforce decisions or communications go out, the new management team needs a complete picture of who they're inheriting — names, roles, pay grades, tenure, and employment status. This is the foundation for every HR action that follows. | Human Resources Leader | Human Resources |  | Team-Level Tasks | 30
No | Review current pay schedules | The incoming management company operates its own payroll system, which may run on a different pay period, pay cadence, or pay date than the outgoing operator. Mapping current pay schedules to the new system before transition ensures employees are paid correctly and on time — a missed or wrong paycheck in week one destroys trust that takes months to rebuild. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Set up new payroll provider | Even though the brand isn't changing, the legal employer of record is. The new management entity must onboard all employees into its own payroll platform before the transition date so the first payroll run processes without interruption. Employees don't care who manages the hotel — they care whether their direct deposit hits on Friday. | Human Resources Leader | Human Resources |  | Team-Level Tasks | 30
No | Schedule staff orientation sessions | The brand standards stay the same, but the management company's policies, reporting structures, HR practices, and operating systems may differ from the outgoing operator's. Orientation sessions give associates the information they need about who to call, how to report issues, and what changes under the new team. | Human Resources Leader | Human Resources |  | Team-Level Tasks | 30
No | Review PTO and vacation balances | Accrued PTO is a legal liability that transfers with the employees. Balances must be fully documented and honored per state law and any applicable employment agreements before the transition closes — discovering undisclosed balances post-handover creates costly disputes between the outgoing and incoming operators. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Define benefits eligibility rules | The incoming management company may offer a different benefits package than the outgoing operator — different carriers, different waiting periods, different covered dependents. Eligibility rules must be locked before enrollment opens so HR communicates accurately and no associate ends up uninsured during the gap. | Human Resources Leader | Human Resources |  | Team-Level Tasks | 30
No | Schedule benefits enrollment meetings | Associates have a limited enrollment window when their employer of record changes. Structured meetings give them the information they need to make informed elections and significantly reduce the flood of individual HR inquiries that otherwise derail the transition team in the first weeks. | Human Resources Leader | Human Resources |  | Team-Level Tasks | 30
No | Collect employee onboarding documents | Because the new management company is a new employer of record, new I-9s, direct deposit authorizations, and tax withholding elections are required for all staff — even those who have worked at this property for years under the prior operator. Missing documents block payroll processing. | Human Resources Leader | Human Resources |  | Team-Level Tasks | 30
No | Verify work authorization compliance | The new management entity assumes full I-9 compliance liability as the new employer of record. All work authorizations must be re-verified at onboarding. A federal audit finding I-9 deficiencies carries significant fines regardless of how long ago the employee was originally hired. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Review and update employee handbook | The outgoing management company's HR policies, code of conduct, and workplace rules no longer govern this property. The incoming company's handbook must be distributed and acknowledged before day one — a verbal transition is not legally defensible in an employment dispute. | Human Resources Leader | Human Resources |  | Team-Level Tasks | 30
No | Distribute onboarding SOPs | The brand's service standards don't change, but the management company's operational procedures — how issues are escalated, how maintenance is logged, how scheduling works — likely do. Written SOPs eliminate ambiguity about how things are done under the new team. | Human Resources Leader | Human Resources |  | Team-Level Tasks | 30
No | Obtain required business licenses | Business licenses are tied to the legal entity operating the property. The new management company must secure its own city, county, and state operating licenses before the handover date — operating under the prior entity's licenses creates regulatory exposure. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Transfer or apply for liquor license | A liquor license is issued to a specific legal entity. The outgoing operator's license does not automatically carry over to the new management company. Serving alcohol under the prior entity's license — even for a single day — creates significant legal and liability exposure. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Update legal business registrations | The property must operate under the new management entity's legal name and tax ID from the moment of handover. Stale registrations in the prior entity's name create complications in opening bank accounts, filing taxes, and obtaining any new permits going forward. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Confirm insurance coverage | The outgoing management company's general liability, property, and workers' comp policies lapse at transition. Even a one-day coverage gap exposes the new operator to uninsured liability for any incident at the property. Guests and associates don't stop having accidents because management is changing. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Review employment agreements | Some key managers may have contracts with the outgoing operator that include non-competes, retention bonuses, or severance triggers tied to a change in management. These must be reviewed before any offer letters go out so the incoming team doesn't inadvertently trigger obligations they didn't know existed. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Identify union agreements if applicable | Collective bargaining agreements bind the incoming management company as a successor employer under the NLRA. Ignoring an existing CBA — even unintentionally — is an unfair labor practice that can result in costly arbitration, back pay awards, and strained labor relations at a property you're trying to stabilize. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Create asset and inventory register | The incoming management company must document exactly what they are receiving custody of — FF&E, operating supplies, vehicles, technology — to establish depreciation records and protect against post-close disputes with the outgoing operator over missing or damaged property. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Update vendor contracts as needed | Existing vendor agreements may reference the outgoing management entity as the contracting party. Updated contracts establish clear payment obligations and liability under the new management company — and protect the incoming operator from being held to terms they never negotiated. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Validate vendor payment details | Stale banking information in the AP system leads to misdirected payments — a particularly common fraud vector during transitions when systems are in flux and multiple teams have temporary access. Validating remittance details directly with each vendor before the first payment run prevents both error and loss. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Schedule inventory transfer | Physical goods — linens, chemicals, F&B stock, operating supplies — must be formally counted and transferred at a defined point in time. This establishes clear ownership between the outgoing and incoming operators and prevents disputes about what was and wasn't included in the handover. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Update online listings | Even with no brand change, GDS channels, OTAs, and direct booking platforms need updated management contacts, billing entities, and commission routing. Stale entity information causes payment delays and booking complications that guests never see but the finance team feels immediately. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Reissue access keys and credentials | All outgoing management personnel, their vendors, and any third parties granted access must be deprogrammed from electronic locks, IT systems, and secure areas at the point of handover. Active credentials from the prior management team represent a direct security risk to guests and the property. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Schedule health inspections | Health department permits for food service, the pool, and the spa may require re-issuance under the new management entity. Getting on the inspector's calendar early avoids a forced closure of an outlet on or shortly after the transition date. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Notify distribution partners | OTAs, GDS platforms, consortia, and corporate travel agencies need updated billing and contact information for the new management entity. Even without a brand change, stale contact records cause commission payment delays and rate loading problems. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Develop staff training schedule | Brand standards remain the same, but the management company's systems, escalation paths, scheduling tools, and operational procedures may differ significantly from the outgoing operator's. A structured training calendar ensures all associates are fluent in how the new team operates before the first shift. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Conduct department onboarding sessions | Each department has specific questions about how things will work under the new management team — who approves overtime, how maintenance gets logged, where to escalate a guest complaint. Department-level sessions let leaders address these directly and build early trust with their inherited teams. | Human Resources Leader | Human Resources |  | Team-Level Tasks | 30
No | Distribute department checklists | With dozens of workstreams running simultaneously, checklists formalize accountability at the department level and ensure critical tasks aren't assumed to be someone else's responsibility. In a management transition, ambiguity is the enemy — what gets written down gets done. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Notify local partners | Shuttle companies, tour operators, local restaurants, and concierge referral networks need to know who the new management contacts are and how to reach them. The brand relationship stays intact, but the operational point of contact has changed — letting partners figure that out on their own damages relationships that drive real revenue. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Review sponsorships and partnerships | The outgoing management team may have entered into local sponsorships, revenue-sharing arrangements, or in-kind partnerships that the incoming team either isn't aware of or wouldn't have agreed to. These need to be reviewed before the handover so the incoming team knows what obligations they're assuming. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Conduct day-one asset count | A physical count at the exact moment of handover, agreed to by both parties, establishes a clean baseline. It protects the incoming management company from post-close claims of missing or damaged property and creates a defensible starting point for the new team's asset records. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Finalize closeout documentation | The management agreement requires formal documentation confirming that the transition is complete and all obligations have been satisfied. Clean closeout records protect the incoming management company in future audits or disputes about what was transferred and in what condition. | General Manager | Admin / GM |  | Team-Level Tasks | 30
No | Set up transition project plan and team | A management transition touches every department simultaneously — HR, finance, IT, operations, legal. Without a formal project plan and a dedicated transition team with clear ownership, critical tasks fall through the cracks and the handover date becomes a crisis instead of a clean handoff. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Establish transition timeline and milestones | Hard deadlines tied to the management handover date create urgency and accountability across all departments. A milestone-based timeline surfaces delays early — when there's still time to recover — rather than discovering gaps the week before the transition. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Assign project roles and responsibilities | Ambiguity about who owns each workstream is the most common cause of transition failures. A clear RACI structure — even a simple one — ensures every task has a name next to it, eliminating duplication and preventing tasks from being assumed covered by someone else. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Set up secure transition data room | Sensitive documents — management agreements, employee records, financial statements, vendor contracts — must be shared between the outgoing and incoming operators in a controlled environment. An unsecured exchange creates legal, privacy, and confidentiality exposure for both parties. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Schedule regular transition status meetings | Cadenced check-ins across all departments surface blockers while there is still time to resolve them. Without a regular forum, problems simmer in silos until they become emergencies that hit the entire transition team at once. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Document transition communication protocols | Clear protocols define who speaks to the staff, who speaks to key vendors, and who speaks to guests — and when. Undisciplined communication in a management transition leads to rumors, conflicting messages, and anxiety that drives turnover at the worst possible time. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Confirm transition contact list | A master contact directory with phone numbers and emails for every key counterpart — outgoing department heads, incoming team leads, ownership representatives, legal counsel — eliminates information delays during a period when speed of communication is everything. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Configure timekeeping system | The new management company's payroll provider requires time and attendance data from its own timekeeping platform. All associates must be loaded, schedules configured, and supervisors trained on the approval workflow before the first pay period closes under new management or payroll will be manual — and full of errors. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Communicate benefit changes to staff | Associates are anxious about their benefits any time management changes hands. Proactive, clear, and early communication about what changes and what stays the same is the single most effective retention tool available to the incoming management team during the transition period. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Apply for tax and permit registrations | The incoming management entity needs its own federal EIN, state tax ID, and local business permits. These registrations are prerequisites for payroll, banking, and legal operations — they cannot be obtained retroactively and their absence cascades into delays across every other workstream. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Schedule compliance audits | The incoming management company assumes regulatory compliance responsibility across OSHA, health codes, and fire safety from the moment of handover. Scheduling audits proactively demonstrates good faith to regulators and surfaces any inherited violations before they become the new team's liability. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Verify accessibility compliance | ADA deficiencies that existed under the prior management team become the incoming management company's liability to remediate from the day of handover. A pre-transition walkthrough protects against expensive retrofits and potential litigation that can follow years after a violation was first created. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Set up operating bank accounts | All revenue and expenses must flow through the new management entity's accounts from the moment of handover. Operating even temporarily under the prior entity's accounts creates co-mingling of funds, tax complications, and potential fraud exposure. | Finance Leader | Finance |  | Team-Level Tasks | 21
No | Establish cash handling procedures | The new management company may have different cash handling policies than the outgoing operator — different count procedures, different deposit schedules, different oversight requirements. These must be trained and enforced from the very first shift, not discovered informally over the first few weeks. | Finance Leader | Finance |  | Team-Level Tasks | 21
No | Reconcile cash and house banks | The outgoing operator's house banks and petty cash floats must be formally counted and reconciled at the transition point with both parties present. Any discrepancy must be resolved before the new management team takes physical custody — otherwise that shortage becomes their problem. | Finance Leader | Finance |  | Team-Level Tasks | 21
No | Configure accounting system | The incoming management company's chart of accounts, cost centers, revenue categories, and reporting structure may differ from the outgoing operator's. A properly configured accounting system is the foundation of clean financial reporting from day one and avoids months of retroactive reclassification. | Finance Leader | Finance |  | Team-Level Tasks | 21
No | Train staff on financial systems | If the incoming management company uses a different accounting, purchasing, or expense management platform, staff need hands-on training before go-live. Posting errors and revenue leakage discovered after close are far harder to unwind than those prevented by training beforehand. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Review transition budget forecasts | The transition period carries one-time costs — overtime, consultant fees, supply gaps, system setup — that fall outside the normal operating budget. A reviewed forecast ensures these are funded and tracked rather than surfacing as unexplained variances in the first monthly P&L under new management. | Finance Leader | Finance |  | Team-Level Tasks | 21
No | Audit outgoing payables and receivables | The incoming management team must understand exactly what invoices are outstanding and what revenue is owed before assuming operational control. Inheriting unresolved payables and receivables without documentation creates cash flow surprises and, sometimes, legal claims in the first critical weeks of operation. | Finance Leader | Finance |  | Team-Level Tasks | 21
No | Audit vendor list | The outgoing management team may have approved vendors, expired contracts, or supplier relationships that the incoming company's procurement standards don't permit. A clean, current vendor list ensures all purchases flow through properly contracted and approved suppliers from day one. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Audit IT hardware assets | Computers, printers, POS terminals, phone systems, and AV equipment must be inventoried and ownership clearly assigned at the time of handover. Unclaimed or disputed hardware delays system setup and creates security gaps when devices fall outside the new management team's control. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Set up user accounts and system access | Every associate needs role-appropriate access to the PMS, email, scheduling software, and financial systems before their first shift under new management. Delayed provisioning forces workarounds — shared logins, paper logs — that create audit exposure and security vulnerabilities. | Finance Leader | Finance |  | Team-Level Tasks | 21
No | Schedule network transition date | If the incoming management company operates its own network infrastructure or IT services, the cutover must be precisely planned and communicated to every department. An uncoordinated cutover during live hotel operations means front desk systems go down, key cards stop working, and guests lose connectivity. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Confirm system migrations | Guest reservation data, historical folios, and AR balances must migrate cleanly to the incoming management company's systems. Corrupted or incomplete data leads to billing disputes, missing reservations, and check-in failures that guests experience personally and remember. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Update email and domain access | If the incoming management company uses its own email domain or communication platform, all internal and guest-facing addresses must transition at handover. The outgoing management team's email access must also be terminated cleanly to protect proprietary guest and operational data. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Test system integrations | The PMS must communicate correctly with the POS, accounting system, GDS, and door lock platform. A broken integration discovered during live operations is far more costly — in time, guest experience, and revenue — than one caught during pre-transition testing. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Confirm data backup protocols | All operational and guest data must be backed up under the incoming management company's IT policy from the first day of operation. A system failure in the first weeks without confirmed backups can result in catastrophic and unrecoverable loss of reservations, folios, and financial records. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Activate property management system | Whether the incoming management company brings its own PMS or continues the existing one, the system must be fully configured, tested, and live before the first check-in under new management. Reservations, rates, room assignments, and billing all flow through it — it is not optional. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Reconfigure keycard systems | All key management credentials from the outgoing management team — master keys, vendor access cards, contractor fobs — must be invalidated at the point of handover. Active credentials in the hands of individuals no longer affiliated with the property represent a direct guest security threat. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Confirm guest safety systems | Smoke detectors, emergency phones, AED devices, and emergency egress routes must be verified operational under the new management team's emergency response protocols before guests occupy the property. The incoming management company assumes full safety liability from the moment of handover. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Audit reservation transfers | Every reservation in the pipeline must be verified in the active PMS with rate, room type, special requests, and deposit records confirmed. A guest who arrives with a confirmed reservation and finds no record of it is a guest service failure at the most fundamental level — and a likely chargeback. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Audit room readiness | Even in a same-brand transition, rooms may have deferred maintenance, housekeeping deficiencies, or inventory gaps that the outgoing team let slide as the handover approached. An independent inspection before the first guest check-in under new management establishes a clean baseline and sets the tone for the incoming team's standards. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Inspect facilities and back-of-house | Kitchen equipment, laundry, loading docks, and storage areas directly impact the team's ability to deliver service. Deficiencies found during a pre-transition inspection cost a fraction of what they cost to correct after the property is live and the outgoing operator is no longer accountable. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Verify fire and life safety systems | Fire alarm, suppression, and emergency egress systems must be confirmed operational and compliant before the handover. The incoming management company assumes full personal and corporate liability for life safety from the moment they sign the management agreement. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Inspect elevators and critical equipment | Elevators require current state inspection certificates to legally operate. An incoming management team inheriting an elevator with an expired certificate can be ordered to shut it down immediately by a regulator — a significant operational disruption in any multi-story property. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Review HVAC and mechanical systems | Deferred maintenance on HVAC and mechanical systems doesn't disappear at handover — it becomes the incoming management team's problem, often at the worst possible moment. A pre-transition review surfaces known issues and creates a documented record so responsibility is clearly assigned. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Audit security systems | CCTV coverage, access control panels, perimeter security, and incident response protocols must be verified and formally transferred to the incoming management team's security program. Any gap in coverage during or after the handover creates liability exposure that is very difficult to defend. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Review utility accounts | Electric, gas, water, and waste management accounts must be transferred to the new management entity. Utilities left in the prior operator's name create billing disputes, payment delays, and — in the worst case — service interruptions the new management team can't resolve because they're not the account holder. | Finance Leader | Finance |  | Team-Level Tasks | 21
No | Confirm kitchen and equipment inspections | Health department inspections of food preparation equipment are required under the new operating entity. Deficiencies discovered during a surprise health inspection after opening are far more damaging — and public — than those found and corrected before the first cover is served. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Audit food and beverage inventory | All perishable and non-perishable F&B inventory must be physically counted at the transition point. The incoming management company should not accept spoiled goods, items past their use-by date, or inventory at inflated transfer values — and should not pay for what isn't actually there. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Configure POS system | The incoming management company may use a different POS platform or require reconfiguration of the existing one to align with its reporting structure, tip policies, and financial integrations. A misconfigured POS causes transaction errors and revenue posting problems from the first meal period. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Update website and digital profiles | Management contact information, billing entities, and booking inquiry routing on the hotel's direct website and online profiles must reflect the new management team from the day of handover. Guests and partners who call the wrong entity create confusion and lost revenue. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Launch transition marketing campaign | A same-brand management transition is an opportunity to communicate continuity and confidence to past guests and the local market — not a rebrand, but a reintroduction of the team. Proactive outreach reassures loyal guests that their experience won't change and signals to the market that leadership is engaged. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Migrate sales systems | CRM data, corporate account histories, negotiated rate files, and group prospect pipelines must transfer cleanly to the incoming management team's sales platform. A sales team starting from a blank CRM effectively starts from zero on accounts the prior team spent years developing — a significant and avoidable competitive disadvantage. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Train sales team | The incoming management company may have a different RFP process, sales tools, revenue management approach, and reporting cadence than the outgoing operator. An untrained sales team either undersells the property or makes commitments that fall outside the new management company's revenue strategy. | Sales Leader | Sales |  | Team-Level Tasks | 21
No | Audit future event bookings | All group, wedding, and catering contracts in the pipeline must be reviewed for terms, deposit amounts, attrition clauses, and service commitments. The incoming management team's first test with the event community is whether they honor what was promised — and they can't honor what they don't know about. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Notify group and event clients | Clients with future bookings need personal outreach from the incoming management team. A proactive letter or phone call from the new Director of Sales or GM builds confidence and significantly reduces cancellation risk — clients cancel when they feel uncertain, not when they feel informed. | Sales Leader | Sales |  | Team-Level Tasks | 21
No | Update catering contracts | Catering agreements must be reviewed and re-executed under the new management entity's name. Contracts still referencing the outgoing operator are legally ambiguous and create complications in revenue recognition, liability, and dispute resolution if something goes wrong with an event. | Sales Leader | Sales |  | Team-Level Tasks | 21
No | Confirm AV and event services | Event clients made booking decisions based on AV capabilities, room configurations, and service commitments. Verifying these are fully staffed and operational under the new management team prevents day-of-event failures that end up on social media and permanently damage the property's reputation with the event community. | Sales Leader | Sales |  | Team-Level Tasks | 21
No | Launch transition FAQ | Associates, vendors, and local partners will all have questions about what's changing under the new management team and what stays the same. A proactive FAQ distributed before the handover reduces inbound noise to the transition team and ensures consistent, accurate messaging rather than corridor rumors. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Monitor guest feedback | The first weeks under new management are when small service gaps are most likely — systems are new, staff are adjusting, and processes are still settling. Real-time monitoring of reviews and comment cards allows the incoming GM to identify and correct failures before they become a pattern that follows the property for months. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Monitor operational KPIs | Occupancy, ADR, RevPAR, labor cost percentage, and guest satisfaction scores must be tracked from the first day of operation under new management. These early metrics establish the baseline against which the incoming team's performance will be measured — and demonstrate to ownership that the transition did not disrupt the business. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Hold post-transition review meeting | A structured debrief within 30 days of the handover surfaces what worked, what didn't, and what is still open. Without this meeting, transition issues quietly become operating problems that never get formally closed, and lessons learned get lost before the next transition. | IT Systems Leader | IT |  | Team-Level Tasks | 21
No | Organize project kickoff meeting | A formal kickoff aligns all department heads on the shared transition timeline, their individual workstreams, and the specific milestones they are accountable for. Without it, each department plans in isolation, critical interdependencies are missed, and the transition team discovers conflicts at the worst possible moment. | Marketing Leader | Field Marketing |  | Team-Level Tasks | 14
No | Distribute project directory | A single reference document listing every key contact — outgoing department heads, incoming team leads, ownership representatives, brand contacts, and legal counsel — eliminates the time wasted searching for the right person during a period when speed of communication is everything. | Marketing Leader | Field Marketing |  | Team-Level Tasks | 14
No | Prepare management offer letters | Incoming management leaders need formal written offers before they can give notice to their current employer. Delays in getting these out create leadership gaps during the most critical window of the transition — a hotel without a confirmed Director of Finance or Director of Operations is operating at significant risk. | Marketing Leader | Field Marketing |  | Team-Level Tasks | 14
No | Activate employment verification process | The new management company is a new employer of record. All hired staff must complete I-9 re-verification as new hires — including associates who have worked at this property for years under the prior operator. This is a federal requirement that applies regardless of continuity of employment at the site. | Marketing Leader | Field Marketing |  | Team-Level Tasks | 14
No | Set up approved vendor list | The incoming management company likely has its own approved supplier programs for operating supplies, amenities, and services that provide negotiated pricing and quality standards. Operating outside the approved vendor list creates compliance issues and forfeits cost savings from day one. | Marketing Leader | Field Marketing |  | Team-Level Tasks | 14
No | Confirm service provider agreements | Pest control, elevator maintenance, landscaping, waste management, and security must all have active contracts in the new management entity's name before operations begin. A lapsed contract discovered during a health inspection or a security incident is not a problem you want to explain to ownership. | Marketing Leader | Field Marketing |  | Team-Level Tasks | 14
No | Update front desk SOPs | Brand standards stay the same, but the new management company's front desk procedures — how complaints are escalated, what comp authority front desk has, how VIPs are handled — may differ from the outgoing operator's. Documented SOPs eliminate ambiguity and protect against inconsistent guest experiences during the adjustment period. | Front Office Leader | Front Office |  | Team-Level Tasks | 14
No | Prepare model guest rooms | A model room set to the brand standard gives the incoming housekeeping leadership a physical reference for training their inherited team. It also gives the incoming GM and ownership a clear inspection benchmark before evaluating the broader room inventory. | Front Office Leader | Front Office |  | Team-Level Tasks | 14
No | Review lost and found procedures | The incoming management company inherits responsibility for items left by guests under the prior management team. Documented procedures establish a chain of custody, protect the property legally, and ensure guest property is handled consistently from the first day of new management. | Marketing Leader | Field Marketing |  | Team-Level Tasks | 14
No | Launch guest service scripts | Brand service standards don't change, but the incoming management team needs to confirm that all associates are actively using the correct greeting, check-in dialogue, and service recovery language. Auditing and relaunching these scripts signals that service standards remain the priority under new management. | Front Office Leader | Front Office |  | Team-Level Tasks | 14
No | Inventory maintenance tools | The incoming engineering team cannot respond to work orders without an accurate picture of what tools and spare parts are on property. An inventory before the handover identifies gaps that must be purchased immediately and prevents the engineering team from starting at a deficit. | Engineering Leader | Engineering |  | Team-Level Tasks | 14
No | Update menus and pricing | Even in a same-brand transition, the incoming F&B leadership may adjust menu composition, pricing strategy, or supplier relationships to reflect their culinary direction and the management company's cost structure. Menus must be updated and approved before the first service period under new management. | Food & Beverage Leader | F&B |  | Team-Level Tasks | 14
No | Train food and beverage staff | The incoming management team may have different service protocols, tip-out policies, and upsell priorities than the outgoing operator. F&B associates need to understand how things work under the new team before the first cover — not during it. | Food & Beverage Leader | F&B |  | Team-Level Tasks | 14
No | Remove outgoing branding | Any collateral, signage, or materials branded to the outgoing management company — not the hotel brand — must be removed at the handover. This includes management company logos on uniforms, correspondence, and back-of-house materials that reference the prior operating entity. | Marketing Leader | Field Marketing |  | Team-Level Tasks | 14
No | Install new branding and signage | Materials referencing the incoming management company — employee-facing signage, HR collateral, correspondence headers, management bios — should be installed at the time of handover to signal a clean transition to staff and ownership. The hotel brand itself remains unchanged. | Marketing Leader | Field Marketing |  | Team-Level Tasks | 14
No | Update guest communication templates | Confirmation emails, pre-arrival messages, and post-stay surveys must reflect the correct management entity contact information, reply-to addresses, and signature blocks from the first reservation under new management. Guest-facing communications tied to the prior operator's contact details create confusion and misdirected replies. | Front Office Leader | Front Office |  | Team-Level Tasks | 14
No | Prepare press and PR messaging | A management transition — without a brand change — should be framed as a story of continuity and operational strength. A clear press statement and aligned talking points for the GM ensure the property controls the narrative rather than allowing speculation to fill the void. | Marketing Leader | Field Marketing |  | Team-Level Tasks | 14
No | Finalize loyalty program participation | The brand's loyalty program doesn't change, but the incoming management company must confirm that the property's enrollment, point-earning structure, and redemption capabilities are correctly configured under the new operating entity. Any technical gaps at the management layer can disrupt guest-facing loyalty functionality. | Marketing Leader | Field Marketing |  | Team-Level Tasks | 14
No | Review room type configuration | Room type names, descriptions, and rate categories in the PMS must remain consistent through the transition. A management handover is a common point where configuration errors are introduced — confirming that room types are correctly mapped in all channels protects rate integrity and guest expectations. | Housekeeping Leader | Housekeeping |  | Team-Level Tasks | 10
No | Update housekeeping SOPs | The brand's cleanliness and presentation standards don't change, but the incoming management company may have its own inspection checklists, productivity targets, and quality assurance processes. Distributing updated SOPs ensures the housekeeping team knows exactly what is expected under the new management. | Housekeeping Leader | Housekeeping |  | Team-Level Tasks | 10
No | Order cleaning and operating supplies | Par levels of approved cleaning chemicals, amenities, and linen must be confirmed and orders placed before the handover. An inherited supply shortfall on day one — even a minor one — creates operational disruption at exactly the moment the new management team is trying to make a strong first impression. | Housekeeping Leader | Housekeeping |  | Team-Level Tasks | 10
No | Complete deep cleaning prior to opening | A documented deep clean completed under the incoming management team's supervision establishes a verified baseline of cleanliness — and accountability. It also surfaces any deferred maintenance or housekeeping deficiencies while the outgoing operator is still available to address any disputed items. | Housekeeping Leader | Housekeeping |  | Team-Level Tasks | 10