## Introduction
Digital Transformation Planning Toolkit
Purpose
The purpose of this toolkit is to guide CHPs on how to prioritise their digital objectives when defining their digital strategy and then to map out planned digital projects.
This tool accompanies the document 07 Digital Transformation Implementation Guide.pdf
Sheets 1 -7 guide you through the process of defining your digital objectives.
Having prioritised your digital objectives, sheets 8 - 10 guide you through the process of defining your digital projects.
Instructions In sheet 1, Digital Readiness Questions, in a workshop setting with a group of staff from across your organisation, consider each question and enter your answer using the dop-down list In sheet 2, Readiness State & Targets, consider the current state assessment calculated based on your answers entered in sheet 1. After entering your answers in worksheet 1, right click and press refresh to update the information in the pivot table. After considering your current state which is automatically calculated, select your desired target state for each readiness category from the list of values incolumn J. In sheet 3, Digital Weaknesses, review the readiness topics to which you entered Strongly Disagree, Disagree and Neither Agree nor Disagree, as these indicate potential weaknesses in relation to your current state of digital readiness In sheet 4 Channel Shift Analysis, set out the trends affecting your organisation which you need to consider. In sheet 5, Digital Objectives, first consider the target state suggestions in sheet 2. Readiness State & Targets and assess whether those are relevant to your organisation. Then consider the weaknesses identified in worksheet 3. Digital Weaknesses in relation to the questions where you answered 'Strongly Disagree', Disagree', and 'Neither Agree nor Disagree.' Consider the short description and summarise the action you need to take. The objective summary is automatically collated. Also consider the recommendations based on your trend analysis in sheet 4. Channel Shift Analysis. Based on your consideration of these factors, select the category, topic and then concisely summarise the action you need to take. In sheet 6, Journey Mapping Outputs, record the touch and pain points from each persona journey mapping exercise you have undertaken to date, record the areas where digital improvements have been identified and then summarise the digital objective In sheet 7, Challenges & Constraints, record the extent of challenges and constraints which may prevent you from achieving the objectives which you have identified as being needed. Record a severity rating for the challenge / constraint and the actions needed to address it.
In sheet 8, Prioritising Objectives, enter weighting criteria for each objective generated from digital readiness target state; digital weaknesses and journey mapping objectives. Objectives will be automatically prioritised and ranked based on the weightings entered. You will then be able to use the ranked objectives to formulate your digital transformation action plan. In sheet 9, Project Planning, the digital objectives which were ranked in sheet 7, Prioritising Objectives are displayed in order, ready for you to map out projects in relation to people, process and / or technology. Up to 3 projects may be recorded for each objective. If more are needed, insert rows and copy the lists of values from preceding cells. Enter the target year and month for the project to commence and summarise the expected benefits, dependencies, additional considerations and budget costs. In sheet 10, Change Management, record the extent of change management which will result as a result of the objective being implemented. Select the complexity change and areas of your CHP which will be affected by it. A score is automatically calculated enabling you to prioritise the change related actions that will be needed. In sheet 11, Digital Risks, identify any risks in relation to each digital objective. The risk level and rating is automatically calculated based on the likelihood of the risk occurring combined with the consequences. Summarise the mitigation action that is needed. In sheet 12, Roadmap, the objectives to which you assigned projects in sheet 8 Project Planning are automatically populated. Having considered the risks, dependencies, additional considerations and budget, input the start and end date for each project. A Gantt chart overview of planned digital projects is now displayed.
Cell Colour Shading
These cells contain either formulas or fixed statements. Do not delete them
These cells contain drop-down list of available values to select from.
These cells are open text and can be used for comments
Distribution This document is intended for the sole use of the Community Housing Industry Association NSW, the Community Housing Industry Association Victoria and their respective member organisations. It is not be provided to any unrelated third parties without the written permission of Housing Information Solutions. Copyright © 2023 Housing Information Solutions. All rights reserved.

## Contents
Digital Transformation Planning Toolkit Contents
1. Digital Readiness Questions
2. Readiness State & Targets
3. Digital Weaknesses
4. Channel Shift Analysis
5. Digital Objectives
6. Journey Mapping Outputs
7. Challenges & Constraints
8. Prioritising Objectives
9. Project Planning
10. Change Management
11. Digital Risks
12. Roadmap

## 1. Digital Readiness Questions
1. Digital Readiness Questions
Completing this survey is the first step on your digital transformation journey. Assessing your level of digital readiness is important as it will enable you to: 1. Assess where you are in terms of your readiness to implement digital transformation initiatives 2. Objectively assess tenant needs 3. Create goals and plans as part of a digital transformation strategy 4. Prioritise your capabilities 5. Evaluate process and service improvements as well as assessing how to improve the customer experience 6. Determine where to make impactful investments 7. Enable you to identify your target state in worksheet 2. Readiness State & Targets For the majority of questions, a list of available answers is provided using the Likert scale (strongly agree; agree; neither agree nor disagree; disagree or strongly disagree) For others, a text or numerical entry is required. Use your judgement in selecting the appropriate answer for your organisation.
Analysis
Ref | Function | Topic | Short Description | Question | Answer | Value | Max Score | Scoring | Strongly Agree | Agree | Neither Agree nor Disagree | Disagree | Strongly Disagree | Needs Review | Totals
1 | Customer Experience | Contact Management | Preferred Contact Method | Does your main tenancy / customer relationship management system allow you to record information on preferred contact method? | Disagree | 2 | 5 | 5 to 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1
2 | Customer Experience | Consultation | Tenant Engagement Method | We know our tenants well, including their engagement preferences and have recorded contact details for all tenants and household members in our tenancy / customer relationship management system | Neither Agree nor Disagree | 3 | 5 | 5 to 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1
3 | Customer Experience | Contact Management | Tenants Confirm Details | We regularly ask our tenants to confirm contact details for themselves and their household members | Strongly Disagree | 1 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1
4 | Customer Experience | Consultation | Consulted Tenants on Digital Channels | We have consulted with our tenants to find out how many would use digital channels to communicate with us and the facilities they currently have access to |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
5 | Customer Experience | Customer Needs & Service | Seamless Integrated Customer Experience | The experience we provide to our tenants is seamlessly integrated across multiple digital (social media, websites, portals etc) and non-digital channels |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
6 | Customer Experience | Digital Channels | Digital Marketing Channels Utilised | We make full use of digital marketing channels (social media, search engine, email and others) to promote our services; housing initiatives; opportunities; schemes and community engagement activities |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
7 | Customer Experience | Consultation | Collect Act on Tenant Feedback | We collect and act on feedback and / or insight about our tenants’ experience on the quality of our services across all of our physical channels |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
8 | Customer Experience | Customer Needs & Service | Focused Tenants; Needs & Technology | We are focused on our tenants, suppliers and customers; their needs and how technology can support us in delivering a quality experience |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
9 | Customer Experience | Reporting & Analysis | Real-Time Data Analysis | We use real-time data analytics / reporting tools to measure how our tenants and customers interact with us |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10 | Customer Experience | Structure | Customer Focused Team Structure | Our teams are structured based around the customer rather than the service functions we perform |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
11 | Customer Experience | Consultation | Tenant Views on Service Quality | Our tenants currently think highly of the quality of our services |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
12 | Customer Experience | Digital Channels | Covid Digital Interaction Increased | Covid-19 resulted in more tenants wanting to interact with us digitally |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
13 | Customer Experience | Digital Channels | Covid Lack of Digital Channels | Covid-19 highlighted our lack of digital channels and we faced challenges as to how we responded |  | 0 | 5 | 1 to 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1
14 | Customer Experience | Digital Channels | Digital Channels Already Established | We already have a digital portal / channel in place through our web site where tenants can submit service requests or make enquiries |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
15 | Operations | Customer Needs & Service | Focus Digital Meeting Customer Needs | Our focus is on how digital can meet the needs of our customers |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
16 | Operations | Current Systems | Current Systems Support Service Delivery | Our current information systems support us in administering and responding to all forms of service enquiries / requests and they are fully capable of supporting us in how we deliver all aspects of our customer services |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
17 | Operations | Processes | Business Process Service Enquiries Requests | We have established business processes in place to professionally administer and respond to all forms of service enquiries and requests |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
18 | Operations | Customer Needs & Service | Tenant Pain Points Known | We know what our tenants’ pain points are in terms of how they contact us and how we respond |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
19 | Operations | Processes | Processes Reviewed for Digital Initiatives | We have reviewed our business processes in preparation for implementing digital service initiatives |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
20 | Operations | Current Systems | Communication Channels Integrated Current Systems | We provide multiple communication channels all of which intelligently integrate with our information systems |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
21 | Operations | Business Functions | Core Functions Digitised | Our core business functions are digitised, driving efficiency and effectiveness and saving us time on administrative tasks (e.g. document management functions and storage are in place with all document templates and forms digitised; task driven / workflow software capable of supporting a wide array of business functions and processes is in place; photographs are captured remotely and stored against the tenant or property record |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
22 | Operations | Business Functions | All Functions Fully Automated | All key business functions are fully automated supported by reliable or established technology and systems |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
23 | Operations | Processes | Process Improvements Identified Digital Initiatives | We have identified where we can streamline our business processes in order that we can best maximise digital initiatives |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
24 | Operations | Resource Capability | Strong Staff Digital Skillsets | We have staff with strong internal digital skillsets or acumen |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
25 | Operations | Resource Technical | Reliance on Trusted Providers | Due to our current level of staff resources, we need to rely on trusted providers to either manage or assist our technology needs |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
26 | Operations | Structure | Silo Departmental Structure | Our operational structure is based on departmental silos |  | 0 | 5 | 1 to 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1
27 | Operations | Structure | Digital Drive Organisational Structure & Reporting | Digital services and channels drive the organisational structure and reporting |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
28 | Operations | Structure | Collaborative Approach Service Delivery | We are implementing or have implemented collaborative practices across the organisation in relation to customer service delivery |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
29 | Operations | Data Management | Regular Data Reviews | We regularly review and maintain the quality and accuracy of our data |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
30 | Organisation, Culture, Governance, Risk & Security | Digital Awareness | Digital Value Fully Understood | Based on what we know, we fully understand the value that digital initiatives can offer to us |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
31 | Organisation, Culture, Governance, Risk & Security | Digital Awareness | Digital Opportunities Not Understood | Digital opportunities and usage are not understood or defined in our organisation |  | 0 | 5 | 1 to 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1
32 | Organisation, Culture, Governance, Risk & Security | Digital Awareness | Low Appetite Digital Service Delivery | Our organisation has little or no appetite for digital service delivery |  | 0 | 5 | 1 to 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1
33 | Organisation, Culture, Governance, Risk & Security | Resource Capability | Exploring Impact Innovation Technology Utilisation | We are starting to or already have explored the impact of innovation and how technology can be effectively utilised |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
34 | Organisation, Culture, Governance, Risk & Security | Change Management | Change Management Practices Established | We have practices in place to effectively manage change and consult with staff |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
35 | Organisation, Culture, Governance, Risk & Security | Change Management | Agile Techniques to Manage Change | We deploy agile techniques / approaches to managing and implementing change |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
36 | Organisation, Culture, Governance, Risk & Security | Resource Technical | Technical Resource Constraints Adverse Impact | We are constrained by our lack of technical resources which has an adverse impact on what we are able to do |  | 0 | 5 | 1 to 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1
37 | Organisation, Culture, Governance, Risk & Security | Digital Awareness | Observe Initiatives Other Orgs | We prefer to see how other organisations implement initiatives first so we can judge whether they will be successful or not |  | 0 | 5 | 1 to 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1
38 | Organisation, Culture, Governance, Risk & Security | Resource Capability | Staff Embrace Digital Initiatives | All staff fully embrace the implementation of digital initiatives |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
39 | Organisation, Culture, Governance, Risk & Security | Data Management | Data Privacy Policies Established | We have data privacy policies in place |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
40 | Organisation, Culture, Governance, Risk & Security | Cybersecurity | Cybersecurity Proactive Network Monitoring | We proactively monitor our network for cybersecurity threats |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
41 | Organisation, Culture, Governance, Risk & Security | Cybersecurity | Cybersecurity Processes Established | We have established processes in place for managing cybersecurity incidents |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
42 | Organisation, Culture, Governance, Risk & Security | Cybersecurity | Cybersecurity Staff Training Established | We provide regular training or guidance to staff on cybersecurity threats, phishing scams, email security, viruses and malware |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
43 | Organisation, Culture, Governance, Risk & Security | System Management | Systems Administration Processes Operational | Our network and systems infrastructure are backed up daily, either by ourselves or by our systems supplier |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
44 | Organisation, Culture, Governance, Risk & Security | System Management | Antivirus Software Implemented | We use up-to-date antivirus / malware / firewall software to protect against unauthorised access to our network and systems |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
45 | Technology | Vision | Clear Vision Technology Roadmap | We have a clear vision and roadmap to implement technology that is linked to our mission, goals and strategies. |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
46 | Technology | Vision | Departmental IT Not Digital Channels | Our focus is on departmental IT solutions to support our current operations, not digital channels nor tenant / supplier needs |  | 0 | 5 | 1 to 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1
47 | Technology | Current Systems | Integrated Systems 360 Degree View | We have implemented integrated systems to manage our tenancy management and maintenance functions (and where appropriate, finance) such that they provide a single 360-degree view of the tenant or person and they support joined-up operations across our organisation |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
48 | Technology | Resource Capability | Ensure Awareness Latest Technologies | We keep up-to-date with the latest technologies and products related to the housing sector |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
49 | Technology | Current Systems | Cloud-based Transactional Systems SaaS | Our core transactional systems are cloud-based (i.e., we use software applications and / or data storage facilities from one or more software suppliers which are accessed over the Internet and on a pay-as-you-go software-as-a-service basis). |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
50 | Technology | Technology Investment | Technology Investment Major Budget Component | Investment in technology forms a major part of our annual budget and will continue to do so. |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
51 | Technology | Technology Deployment | Track Record New Technology Deployment | We have a proven track record in planning for and then effectively and efficiently deploying new technologies, ensuring they are fully integrated with our systems infrastructure |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
52 | Technology | Technology Deployment | Always Assessing Technology Capability | In maximising our use of technology, our approach is to always assess what it is really capable of, how we can adapt our business and processes to make the most of our technology investments and where relevant, implement new processes to maximise usage and deliver service improvements. |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
53 | Technology | Current Systems | Current Systems Enable Digital Connectivity | Our current systems have enabled us to be digitally connected with our suppliers, contractors and service partners allowing us to initiate, monitor and complete the progress of each type of supply (e.g. electronically issuing purchase orders, receiving and processing invoices; suppliers have access to a portal to lodge invoices and request changes, variations or amendments) |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
54 | Technology | Current Systems | Current Systems Enable Digital Capability | Our current systems have either enabled us or are capable of enabling us to be digitally connected with our tenants and customers |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
55 | Technology | Digital Channels | Viewing Status Key Digital Requirement | In using digital channels, it is important to us that all tenants and suppliers can easily view the latest status of their service enquiry or request and what is happening to it |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
56 | Technology | Resource Technical | Open to Specialist Digital Providers | We are open to considering how specialist digital software providers can assist us in implementing specific digital apps rather than rely on the main software supplier of our core transactional system(s) |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
57 | Technology | Technology Deployment | Entrenched Use of Systems | In implementing any new technology and system(s), we typically take the view that it must support what we do now on the basis this is how we’ve always done it |  | 0 | 5 | 1 to 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1
58 | Technology | Reporting & Analysis | Real-time Analytics Customer Demand | We have reporting tools which are either provided in our current systems or interact with them such they provide real-time data analytics allowing us to see, understand and respond to customer demand and workforce needs |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
59 | Technology | Mobile | Well-established Mobile Apps Used | We use well-established mobile technology apps to support our staff when visiting clients |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
60 | Technology | Mobile | Intention Implement Mobile Apps | We intend to implement mobile technology apps to support our staff when working on-site |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
61 | Strategy | Innovation | Structured Approach Implementing New Ideas | We have a structured and managed approach to implementing new ideas and innovative practices |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
62 | Strategy | Innovation | Technology Digital, Innovation Top Priorities | Technology, digital and innovation are among our top business priorities |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
63 | Strategy | Vision | IT Strategy Aligned Organisational Vision | IT strategy and performance are entirely aligned to our organisational vision and strategy |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
64 | Strategy | Resource Capability | Digital Strategy Implementation Roles Understood | The required roles and responsibilities for delivering a digital strategy are clear and understood |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
65 | Strategy | Customer Needs & Service | Integrated Digital Experience NOT Priority | Establishing a seamless integrated digital experience across multiple digital channels is not a priority for us |  | 0 | 5 | 1 to 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1
66 | Strategy | Reporting & Analysis | Strategic Decisions Based on Data | Our strategic decision making is guided by the data we collect |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
67 | Strategy | Reporting & Analysis | Data Analytics Generate Business Insights | Our data analytics generate business data that provide great insights |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
68 | Strategy | Data Management | Data Treated Asset Regularly Reviewed | We treat data as an asset and seek to maximise its value by regularly reviewing and maintaining it |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
69 | Strategy | Data Management | Data Management Strategy Established | We have a data management strategy in place |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
70 | Strategy | Digital Channels | Digital Strategy Established | We have defined a digital strategy |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
71 | Strategy | Processes | Online Processes Defined | Business processes that are easy and cost-effective to deliver online have been identified and are either in place or will be implemented |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
72 | Strategy | Digital Channels | Exploring Digital Channels | The potential for digital channels to create new ways of engaging with tenants and customers and delivering services is being or has been explored |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
73 | Strategy | Customer Needs & Service | Tenant Expectations Needs Driving Innovation | The needs and expectations of our tenants and suppliers is driving innovation in how we deliver services |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
74 | Strategy | Consultation | Consult Listen Act Formulating Strategy | We listen to all our tenants, suppliers, stakeholders and partners, and act on suggestions in formulating our strategies |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
75 | Strategy | Consultation | Tenants Consulted Internet Access Usage | We have consulted with our tenants on what they use in accessing the Internet and we know the level of Internet usage across our portfolio |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
76 | Strategy | Third-party Partnerships | Third Party Initiatives Assist Tenants | We have explored or are currently exploring initiatives and / or partnerships with third party organisations as to how we can best assist our tenants in accessing the Internet |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
77 | Strategy | Resource Capability | Resource Capacity Deliver Digital Initiatives | We have the resource capacity and capabilities to deliver digital initiatives taking into account all other objectives, projects, funding and development opportunities |  | 0 | 5 | 5 to 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1

## 2. Readiness State & Targets
2. Digital Readiness: Current & Target State
After entering the answers in worksheet 1. Digital Readiness Questions, right click and press refresh | [7 empty] | After considering your current state as generated in response to your answers to the questions in worksheet 1 Digital Readiness Questions as well as your identified weaknesses in worksheet 3. Digital Weaknesses, select the desired target state in column J below from the list of values. Aspects to consider will be automatically populated which will assist you in defining your future digital objectives and determining actions, to be recorded in worksheet 5. Digital Objectives.
Section | No. of Topics | Score | Max Score | % Score | Current State |  | Factors Influencing Current State Assessment | Target State |  | Target State: Aspects to Consider
Customer Experience | 14 | 6 | 70 | 8.571% | Basic | Customer Experience Basic | • No digital interaction with customers exists or at the very least thinking is at the minimal stage as to how digital technology can be utilised. • A website may exist but this does not support any effective interaction with customers. • Customers largely rely in traditional or accustomed means in contacting CHP staff, e.g., by phone, office visit, at home or by email. |  | Customer Experience | #N/A
Operations | 15 | 0 | 75 | 0% |  | Operations | #N/A |  | Operations | #N/A
Organisation, Culture, Governance, Risk & Security | 15 | 0 | 75 | 0% |  | Organisation, Culture, Governance, Risk & Security | #N/A |  | Organisation, Culture, Governance, Risk & Security | #N/A
Strategy | 17 | 0 | 85 | 0% |  | Strategy | #N/A |  | Strategy | #N/A
Technology | 16 | 0 | 80 | 0% |  | Technology | #N/A |  | Technology | #N/A
Grand Total | 77 | 6 | 385 | 1.558%

## 3. Digital Weaknesses
3. Digital Weaknesses
The pivot table below shows all answers where 'neither agree nor disagree'; 'disagree' and 'strongly agree' have been entered in worksheet 1. Digital Readiness Questions
Readiness Section
Weaknesses | Topic | Short Description | Neither Agree nor Disagree | Disagree | Strongly Disagree | Readiness Section | Topic | Sum of Neither Agree nor Disagree | Sum of Disagree | Sum of Strongly Disagree | Sum of Topics Needing Review | Total Survey Topics | %
Customer Experience | Consultation | Tenant Engagement Method | 1 |  |  | Customer Experience | Consultation | 1 | 0 | 0 | 1 | 4 | 25%
| Contact Management | Preferred Contact Method |  | 1 |  |  | Contact Management | 0 | 1 | 1 | 2 | 2 | 100%
|  | Tenants Confirm Details |  |  | 1 |  | Customer Needs & Service | 0 | 0 | 0 | 0 | 2 | 0%
[7 empty] | Digital Channels | 0 | 0 | 0 | 0 | 4 | 0%
[7 empty] | Reporting & Analysis | 0 | 0 | 0 | 0 | 1 | 0%
[7 empty] | Structure | 0 | 0 | 0 | 0 | 1 | 0%
[6 empty] | Customer Experience Total |  | 1 | 1 | 1 | 3 | 14 | 21.43%
[6 empty] | Operations | Business Functions | 0 | 0 | 0 | 0 | 2 | 0%
[7 empty] | Current Systems | 0 | 0 | 0 | 0 | 2 | 0%
[7 empty] | Customer Needs & Service | 0 | 0 | 0 | 0 | 2 | 0%
[7 empty] | Data Management | 0 | 0 | 0 | 0 | 1 | 0%
[7 empty] | Processes | 0 | 0 | 0 | 0 | 3 | 0%
[7 empty] | Resource Capability | 0 | 0 | 0 | 0 | 1 | 0%
[7 empty] | Resource Technical | 0 | 0 | 0 | 0 | 1 | 0%
[7 empty] | Structure | 0 | 0 | 0 | 0 | 3 | 0%
[6 empty] | Operations Total |  | 0 | 0 | 0 | 0 | 15 | 0%
[6 empty] | Organisation, Culture, Governance, Risk & Security | Change Management | 0 | 0 | 0 | 0 | 2 | 0%
[7 empty] | Cybersecurity | 0 | 0 | 0 | 0 | 3 | 0%
[7 empty] | Data Management | 0 | 0 | 0 | 0 | 1 | 0%
[7 empty] | Digital Awareness | 0 | 0 | 0 | 0 | 4 | 0%
[7 empty] | Resource Capability | 0 | 0 | 0 | 0 | 2 | 0%
[7 empty] | Resource Technical | 0 | 0 | 0 | 0 | 1 | 0%
[7 empty] | System Management | 0 | 0 | 0 | 0 | 2 | 0%
[6 empty] | Organisation, Culture, Governance, Risk & Security Total |  | 0 | 0 | 0 | 0 | 15 | 0%
[6 empty] | Strategy | Consultation | 0 | 0 | 0 | 0 | 2 | 0%
[7 empty] | Customer Needs & Service | 0 | 0 | 0 | 0 | 2 | 0%
[7 empty] | Data Management | 0 | 0 | 0 | 0 | 2 | 0%
[7 empty] | Digital Channels | 0 | 0 | 0 | 0 | 2 | 0%
[7 empty] | Innovation | 0 | 0 | 0 | 0 | 2 | 0%
[7 empty] | Processes | 0 | 0 | 0 | 0 | 1 | 0%
[7 empty] | Reporting & Analysis | 0 | 0 | 0 | 0 | 2 | 0%
[7 empty] | Resource Capability | 0 | 0 | 0 | 0 | 2 | 0%
[7 empty] | Third-party Partnerships | 0 | 0 | 0 | 0 | 1 | 0%
[7 empty] | Vision | 0 | 0 | 0 | 0 | 1 | 0%
[6 empty] | Strategy Total |  | 0 | 0 | 0 | 0 | 17 | 0%
[6 empty] | Technology | Current Systems | 0 | 0 | 0 | 0 | 4 | 0%
[7 empty] | Digital Channels | 0 | 0 | 0 | 0 | 1 | 0%
[7 empty] | Mobile | 0 | 0 | 0 | 0 | 2 | 0%
[7 empty] | Reporting & Analysis | 0 | 0 | 0 | 0 | 1 | 0%
[7 empty] | Resource Capability | 0 | 0 | 0 | 0 | 1 | 0%
[7 empty] | Resource Technical | 0 | 0 | 0 | 0 | 1 | 0%
[7 empty] | Technology Deployment | 0 | 0 | 0 | 0 | 3 | 0%
[7 empty] | Technology Investment | 0 | 0 | 0 | 0 | 1 | 0%
[7 empty] | Vision | 0 | 0 | 0 | 0 | 2 | 0%
[6 empty] | Technology Total |  | 0 | 0 | 0 | 0 | 16 | 0%

## 4. Channel Shift Analysis
4. Channel Shift Analysis
The purpose of the channel shift analysis is for you to record the trends that you are aware of which may affect how you manage your operations and deliver services. Refer to 02 IS / IT Strategy Toolkit.xlsx wjhich sets out templates to first undertake a SWOT and a PESTLE analysis. In preparing your digital objectives, it is recommended that after first conducting a PESTLE analysis, you then identify the possible shifts that may or are likely to affect the community housing sector and how these could impact your organisation 1. Start by selecting macro trends that you are aware of in relation to the digital readiness categories below. These are the large-scale transformative trends that could impact your organisation. The table below provides you with suggestions of macro trends, however, not all need to be considered. Delete as necessary. If inserting new rows, ensure the list options are displayed and the recommendation formula in the preceding row is copied 2. For each trend, summarise the main driver behind these trends. Why are these trends occurring? What are the causal forces behind them? If you think there are more drivers, summarise these for each trend identified. 3. Deprioritise trends that are expected to happen beyond 24 months. 4. Prioritise the trends that have a high impact and relevance to your CHP by selecting the drop-down options. 5. In a workshop setting with selected staff, discuss which trend you would like to pursue and limit it to one opportunity. The macro trends below are provided for illustrative purposes. Amend these as required. Add or delete rows as needed. If adding new rows, ensure the list options are displayed and the recommendation formula in the preceding row is copied After adding the trends, right click in the Ranked Objectives pivot table and press refresh
[16 empty] | Pivot | Y
|  | Describe macro trend | Succinctly summarise the driver(s) behind the trend | [12 empty] | Ranked Objectives
Ref | Category | Macro Trend | Driver | Time to Impact | Potential Impact on CHP | Relevance to CHP | Recommendation | Objective | Impact Score | Relevance Score | Calculated Score | Ranking | Count Total Scores | Middle (for Recommendation | Pivot | Ranking | Objective | Count of Category
1 | Customer Experience | Chatbots | Providing chatbots in mutiple lanaguages | 1 - 2 years | High | High | Adopt | Adopt Customer Experience : Chatbots - Providing chatbots in mutiple lanaguages | 4 | 4 | 4 | 1 | 1 | 0.5 | Y | 1 | Adopt Customer Experience : Chatbots - Providing chatbots in mutiple lanaguages | 1
2 | [11 empty] | 0 |  |  | N
3 | [11 empty] | 0 |  |  | N
4 | [11 empty] | 0 |  |  | N
5 | [11 empty] | 0 |  |  | N
6 | [11 empty] | 0 |  |  | N
7 | [11 empty] | 0 |  |  | N
8 | [11 empty] | 0 |  |  | N
9 | [11 empty] | 0 |  |  | N
10 | [11 empty] | 0 |  |  | N
11 | [11 empty] | 0 |  |  | N
12 | [11 empty] | 0 |  |  | N
13 | [11 empty] | 0 |  |  | N
14 | [11 empty] | 0 |  |  | N
15 | [11 empty] | 0 |  |  | N
16 | [14 empty] | N
17 | [11 empty] | 0 |  |  | N
18 | [14 empty] | N
19 | [11 empty] | 0 |  |  | N
20 | [14 empty] | N
21 | [11 empty] | 0 |  |  | N
22 | [14 empty] | N
23 | [11 empty] | 0 |  |  | N
24 | [14 empty] | N
25 | [11 empty] | 0 |  |  | N

## 5. Digital Objectives
5. Digital Objectives
1. Consider the target state suggestions in worksheet 2. Readiness State & Targets and assess whether those are relevant to your organisation
2. Then consider the weaknesses identified in worksheet 3. Digital Weaknesses in relation to the questions where you answered 'Strongly Disagree', Disagree', and 'Neither Agree nor Disagree.' Consider the short description.
3. Consider the macro tends you have prioritised in worksheet 4. Channel Shift Analysis
4. Based on the above, identify your digital objectives derived from your readiness current state and future state; your digital weaknesses and the trends in channel shift.
5. In the table below, select the Readiness Category and Topic from the dropdown list. Now summarise the action that is needed for each in column F. The Digital Objective is automatically displayed and carried forward to worksheet 7. Prioritising Objectives
| Category | Target State | Topic | Action | Digital Objective
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## 6. Journey Mapping Outputs
6. Journey Mapping Outputs
From the persona journey mapping exercises and journey mapping grid used to document each journey, list the following for each journey:
1. Touch points
2. Pain points
3. Digital improvements identified
4. Objectives - from the digital improvement(s) identified from the journey mapping exercise, you should be able to define a related objective. This may include e.g. an investment in people, process or technology for the purpose of building or improving a business capability and a brief description of what needs to be done. Limit one objective for each journey activity phase. If more than one objective is identified for each journey, use adjacent columns as needed
Journey | 1 | 2 | 3 | 4 | 5 | 6` | 7 | 8
Enter the name of the persona journey examined
Touch Points
Summarise the touchpoints between the customer / person and your CHP
Key Pain Points
The emotional status of the person at each stage of the journey
Digital Improvements
Summarise the extent of any digital improvements identified from the persona journey mapping exercise
Objective
From the improvements identified, summarise the objective and the action needed to implement it | Journey Example: Operations: establish collaborative working across teams to improve customer enquiry process | Journey Example: Technology - implement self-service app
Journey | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Enter the name of the persona journey examined
Touch Points
Summarise the touchpoints between the customer / person and your CHP
Key Pain Points
The emotional status of the person at each stage of the journey
Digital Improvements
Summarise the extent of any digital improvements identified from the persona journey mapping exercise
Actions
From the improvements identified, summarise what is needed to implement the improvement

## 7. Challenges & Constraints
7. Challenges & Constraints
Consider the extent of challenges and constraints (internal or external) which may prevent the objective from being realised
The objective is automatically populated from worksheet 5. Digital Objectives and worksheet 6. Journey Mapping Outputs
Select a severity rating for the challenge / constraint
Describe the possible actions you can take to address the constraint. Some actions may be beyond your control.
| Describe the strategic business goal to which the digital objective can be aligned | Describe the challenge or constraint which may prevent the objective from being realised | Select a rating level | Describe the actions that could possibly be taken to address the challenge or constraint
Digital Objective | Strategic Business Goal | Challenge / Constraint | Rating | Possible Actions
Journey Example: Operations: establish collaborative working across teams to improve customer enquiry process
Journey Example: Technology - implement self-service app
Digital Objective

## 8. Prioritising Objectives
8. Prioritising Digital Objectives
1. Prioritise the required improvements by selecting a priority for each digital objective using the weighting categories for desirability, feasibility and viability. |  |  |  | Impact / Effort |  |  |  | Digital Objective Weighting Criteria
2. Amend the weighting criteria in cells C9:E9 as needed, ensuring the total = 100% |  |  |  | Business Impact | Effort | Score | Initial Recommendation | Desirability | Feasibility | Viability
3. Based on the weightings selected, the objectives will be prioritised and displayed in order of priority in the adjacent table Prioritised Objectives 4. When new values are entered for each digital objective, always refresh the Prioritised Objectives table (right click in the table and select Refresh). |  |  |  | How beneficial will this be if it is implemented? | How hard will this be in terms of time, budget and resources? |  | Initial prioritisation is calculated below | Is this a solution that would benefit / improve the customer experience? Has demand / need been identified / verified? | How important is it for this improvement enhance your operations? Will this improvement enhance your capabilities and performance? | Will this improvement contribute to your organisation's strategic objectives?
[17 empty] | Pivot | Y
|  | Describe the strategic business goal to which the digital objective can be aligned | Describe the desired outcome to be achieved | Impact / Effort |  |  | Recommendation | 40% | 30% | 30% | Ranking | [5 empty] | Prioritised Objectives
| Digital Objective | Strategic Business Goal | Desired Outcome | Impact | Effort | Score | Action | Desirability | Feasibility | Viability | Ranking | Desirability | Feasibility | Viability | Total | Pivot | Ranking | Digital Objective
Journey Mapping Outcomes | Journey Example: Operations: establish collaborative working across teams to improve customer enquiry process |  |  | High | Low | 1 | Prioritise | Critical | High | High | 1 | 7 | 5.6 | 5.6 | 18.2 | Y | 1 | Journey Example: Operations: establish collaborative working across teams to improve customer enquiry process
| Journey Example: Technology - implement self-service app |  |  | High | Low | 1 | Prioritise | High | High | High | 2 | 5.6 | 5.6 | 5.6 | 16.8 | Y | 2 | Journey Example: Technology - implement self-service app
[11 empty] | 0 | 0 | 0 | 0 | 0 | N | Grand Total
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
Digital Objectives | [10 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[11 empty] | 0 | 0 | 0 | 0 | 0 | N
[12 empty] | 0 | 0 | 0 | 0 | N

## 9. Project Planning
9. Project Planning
The digital objective descriptions and rankings are generated below based on the prioritised objectives in worksheet 7. Prioritising Objectives. When these are refreshed, the list of objectives below is automatically updated
Up to 3 projects can be defined for each objective. If fewer projects need to be defined, delete the row as required. If more projects are relevant to the objective, insert a row and copy the formula from the preceding row
For each objective, complete the project information using the yellow drop-down cells or by entering details in the white cells | [13 empty] | Budget
Ensure projects have unique names
Enter the overall start date for your digital transformation programme
Transformation Roadmap Start Date |  | Enter date
|  | Enter a unique name for the project |  | Enter the name of the project sponsor | Enter the name of the manager |  |  |  | Summarise the benefits for each project in this column | Summarise any additional consideration for each project in this column | Summarise any dependencies for each project in this column | Do have the resources and capabilities to deliver this project in-house or will you need to outsource it? | Describe the metrics to be used to measure success of the project | Budget
Rank | Digital Objective | Project Name | Project Type | Sponsor | Project Manager | Year | Month | Duration (Weeks) | Benefits | Additional Considerations | Dependencies | Resourcing | Success Factors | Staff Costs | Technology Costs | Contract Costs | Total
1 | Journey Example: Operations: establish collaborative working across teams to improve customer enquiry process | 001 Train staff on new ways of working | People | [Enter name] | [Enter name] |  |  | 4 | [8 empty] | 0
2 | Journey Example: Technology - implement self-service app | 002 Revise customer facing business processes | Processes |  |  |  |  | 10 | [8 empty] | 0
0 |  | 003 Implement workflows to support collaborative working | Technology |  |  |  |  | 12 | [8 empty] | 0
0 |  | 004 Project JKL | [5 empty] | 4 | [8 empty] | 0
0 |  | 005 Project MNO | [5 empty] | 4 | [8 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0
0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0
0 | [16 empty] | 0

## 10. Change Management
10. Change Management | Change Management
| Select the prioritised Digital Objective from the drop down list where a risk can be identified | Enter the name of the planned project where change will result | Summarise the nature of the change | Select the size of the change. Amend reference values or add new values as needed in column K | Select complexity level of the change | Score is calculated based on complexity level | Reference Values |  | Change Assessment
# | Digital Objective | Project | Change | Scope of Change | Change Complexity | Change Score | Complexity | Size of Change | Project | Sum of Change Score
1 | [6 empty] | Extreme | 1 team | (blank) | 0
2 | [6 empty] | High | 1 business unit
3 | [6 empty] | Medium | 1 department
4 | [6 empty] | Low | Multiple teams
5 | [6 empty] | Very Low | Entire CHP
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## 11. Digital Risks
11. Digital Risks
Select the prioritised Digital Objective from the drop down list where a risk can be identified |  | Enter the name of the planned project where a risk can be identified | Select Risk Category from drop down list - add to list in Config worksheet if additional values needed | Select Risk Factor from drop down list - add to list in Config worksheet if additional values needed | Enter description of the risk | Enter description of the risk impact on CHP's operations | Select from drop down list | Select from drop down list | Calculated Field | Calculated Field | Enter description of actions needed to mitigate the risk
# | Digital Objective | Project | Risk Category | Risk Factor | Risk Description | Impact Assessment | Likelihood | Consequences | Risk Level | Rating | Mitigation Action | Rating | Key | Description
1 | [11 empty] | 1 | Very Low | Minimal Impact
2 | [11 empty] | 2 | Low | limited Impact but issues to address contributing to wider risk
3 | [11 empty] | 3 | Moderate | Some risk of delays; issues likely to arise
4 | [11 empty] | 4 | Major | Significant risk of delays; issues probable; adverse impact on operation
5 | [11 empty] | 5 | Critical | Project in potential jeopardy and failure; delays inevitable
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## 12. Roadmap
12. Digital Project Roadmap
Use this Gantt chart to create a roadmap for your IT strategy by assigning start dates, and end dates for each of the initiatives below.
Change conditional formatting rule if your Initiative Types differ from the examples below
# | Digital Transformation Objective | Project | Project Type | Planned Start Date (mm-yy) | Planned End Date (mm-yy) | Expected Duration (Days) | time axis 2023-01-01 to 2026-12-01
1 | Journey Example: Operations: establish collaborative working across teams to improve customer enquiry process | 001 Train staff on new ways of working | People | 2023-06-01 | 2023-12-01 | 183 | 2023-06-01: People; 2023-07-01: People; 2023-08-01: People; 2023-09-01: People; 2023-10-01: People; 2023-11-01: People; 2023-12-01: People
2 | Journey Example: Technology - implement self-service app | 002 Revise customer facing business processes | Processes | 2023-05-01 | 2023-07-01 | 61 | 2023-05-01: Processes; 2023-06-01: Processes; 2023-07-01: Processes
3 |  | 003 Implement workflows to support collaborative working | Technology
4 |  | 004 Project JKL
5 |  | 005 Project MNO
6
7
8
9
11
12
13
15
16
17
19
20
21
23
24
25
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55

## Topic Summary (hidden)
Row Labels | Count of Topic | Row Labels | Count of Topic
Business Functions | 2 | Business Functions | 2
Change Management | 2 | Operations | 2
Consultation | 6 | Change Management | 2
Contact Management | 2 | Organisation, Culture, Governance, Risk & Security | 2
Current Systems | 6 | Consultation | 6
Customer Needs & Service | 6 | Customer Experience | 4
Cybersecurity | 3 | Strategy | 2
Data Management | 4 | Contact Management | 2
Digital Awareness | 4 | Customer Experience | 2
Digital Channels | 7 | Current Systems | 6
Innovation | 2 | Operations | 2
Mobile | 2 | Technology | 4
Processes | 4 | Customer Needs & Service | 6
Reporting & Analysis | 4 | Customer Experience | 2
Resource Capability | 6 | Operations | 2
Resource Technical | 3 | Strategy | 2
Structure | 4 | Cybersecurity | 3
System Management | 2 | Organisation, Culture, Governance, Risk & Security | 3
Technology Deployment | 3 | Data Management | 4
Technology Investment | 1 | Operations | 1
Third-party Partnerships | 1 | Organisation, Culture, Governance, Risk & Security | 1
Vision | 3 | Strategy | 2
Grand Total | 77 | Digital Awareness | 4
|  | Organisation, Culture, Governance, Risk & Security | 4
|  | Digital Channels | 7
|  | Customer Experience | 4
|  | Strategy | 2
|  | Technology | 1
|  | Innovation | 2
|  | Strategy | 2
|  | Mobile | 2
|  | Technology | 2
|  | Processes | 4
|  | Operations | 3
|  | Strategy | 1
|  | Reporting & Analysis | 4
|  | Customer Experience | 1
|  | Strategy | 2
|  | Technology | 1
|  | Resource Capability | 6
|  | Operations | 1
|  | Organisation, Culture, Governance, Risk & Security | 2
|  | Strategy | 2
|  | Technology | 1
|  | Resource Technical | 3
|  | Operations | 1
|  | Organisation, Culture, Governance, Risk & Security | 1
|  | Technology | 1
|  | Structure | 4
|  | Customer Experience | 1
|  | Operations | 3
|  | System Management | 2
|  | Organisation, Culture, Governance, Risk & Security | 2
|  | Technology Deployment | 3
|  | Technology | 3
|  | Technology Investment | 1
|  | Technology | 1
|  | Third-party Partnerships | 1
|  | Strategy | 1
|  | Vision | 3
|  | Strategy | 1
|  | Technology | 2
|  | Grand Total | 77

## Config
1. Digital Readiness Questions | 2. Readiness State & Targets | [7 empty] | 4. Channel Shift Analysis | [5 empty] | 7. Challenges & Constraints | 8. Prioritising Objectives |  |  | 8. Project Planning |  |  |  | 9. Digital Risks
Answers | Readiness Bandings
Strongly Agree | Less than % | Description | Aspects to Consider |  |  |  | Readiness Sections | Readiness Topics | Time to impact | ImpactRelevance | ImpactRelevance Score | Relevance | Relevance Score | Recommendation | Challenge Constraint Rating | Improvement Criteria | HighLowScale | Score | Project Type | Year | Month | Project Resourcing | Likelihood | Consequences | Risk Level | Rating | Risk Category | Risk Factor | Risk calculation |  | Consequences
Agree | 56 | Basic | Customer Experience | Basic | Customer Experience Basic | • No digital interaction with customers exists or at the very least thinking is at the minimal stage as to how digital technology can be utilised. • A website may exist but this does not support any effective interaction with customers. • Customers largely rely in traditional or accustomed means in contacting CHP staff, e.g., by phone, office visit, at home or by email. | Customer Experience | Business Functions | Less than 1 year | Very High | 5 | Very High | 5 | Adopt | Critical | Critical | High | 3 | People | Year 1 | January | In-house | Almost Certain | Minimal | Very Low | 1 | Compliance & Legal | Change |  |  | Minimal | Minor | Moderate | Significant | Severe
Neither Agree nor Disagree | 66 | Developing | Customer Experience | Developing | Customer Experience Developing | • Increasing awareness of digital channel benefits to customers. • Consideration being given as to how digital channels can be used and how they would benefit or improve the current customer experience. | Operations | Change Management | 1 - 2 years | High | 4 | High | 4 | Aware | High | High | Medium | 2 | Processes | Year2 | February | Outsource | Likely | Minor | Low | 2 | Cybersecurity / IT | Cost | Likelihood | Almost Certain | Moderate | Major | Major | Critical | Critical
Disagree | 76 | Established | Customer Experience | Established | Customer Experience Established | • Customers have use of a portal or able to submit service requests and enquiries through the CHP’s web site. • Pro-active engagement with customers, suppliers and stakeholders is in place across a variety of platforms. • Solid use is made of social media channels to promote services. | Organisation, Culture, Governance, Risk & Security | Consultation | 2- 3 years | Moderate | 3 | Moderate | 3 |  | Medium | Medium | Low | 1 | Technology | Year 3 | March |  | Possible | Moderate | Moderate | 3 | Operational | Culture |  | Likely | Moderate | Moderate | Major | Major | Critical
Strongly Disagree | 86 | Advanced | Customer Experience | Advanced | Customer Experience Advanced | • Customers and suppliers are accustomed to using digital channels to interact with the CHP. • Staff are organised in teams around the customer rather than the organisation. • The CHP regularly and pro-actively engages with customers, suppliers and stakeholders to assess the merits and benefits of using digital channels as well as reviewing its overall track record on customer service. • The customer experience across all channels (digital and non-digital) is seamless. | Technology | Contact Management | 3 - 5 years | Low | 2 | Low | 2 |  | Low | Low | N/A | 0 |  | Year 4 | April |  | Unlikely | Significant | Major | 4 | Organisational | Data Privacy |  | Possible | Low | Moderate | Moderate | Major | Major
| 200 | Leading | Customer Experience | Leading | Customer Experience Leading | • Feedback from pro-active engagement with customers, suppliers and stakeholders is actively encouraged, with action taken, made public with lessons learnt being continually applied. • Seamless two-way integration is established through digital channels such that customers, suppliers and stakeholders can immediately know the status of a service request, transaction or enquiry. | Strategy | Current Systems |  | Very Low | 1 | Very Low | 1 |  | Least Important | Least Important |  |  |  |  | May |  | Rare | Severe | Critical | 5 | Strategic / Innovation | Functionality |  | Unlikely | Very Low | Low | Moderate | Moderate | Major
|  |  | Operations | Basic | Operations Basic | • Largely traditional methods in service delivery • Business functions and units typically operate in silos rather than collaboratively • No or limited experimentation or questioning of current methods of service delivery and better ways of engaging with customers • Staff may use smartphones and tablets but do not have any real or value-added access to digital tools or software to operate effectively in the field when dealing with customers |  | Customer Needs & Service | [6 empty] | N/A | N/A |  |  |  |  | June | [6 empty] | Health & Safety |  | Rare | Very Low | Very Low | Low | Moderate | Moderate
|  |  | Operations | Developing | Operations Developing | • Increasing awareness of digital channel benefits to customers • Moving towards defining digital capabilities and identifying scope • Consideration being given or explored to leveraging digital channels which are or will be impacting on service delivery channels are managed • Collaborative practices emerging with breakdown of internal silos |  | Cybersecurity | [12 empty] | July | [6 empty] | Processes / Automation
|  |  | Operations | Established | Operations Established | • An organisational-wide collaborative approach to service delivery is in place • Business processes have been reviewed and amended to support collaborative ways of working • Fully integrated systems are in place which minimise the extent of manual intervention needed to communicate internally and undertake specific operational tasks • Staff are recognising the value of working collaboratively |  | Data Management | [12 empty] | August | [6 empty] | Productivity
|  |  | Operations | Advanced | Operations Advanced | • Service delivery collaboration across the CHP is well-established and supported by integrated systems and digital tools • A strong customer focussed culture has been adopted and is continually reviewed • All digital policies and procedures have been identified and developed • All digital resources and staff training are focussed on meeting the needs of customers and continually improving the customer experience |  | Digital Awareness | [7 empty] | Impact / Effort |  |  |  |  | September | [6 empty] | Project Mgmt.
|  |  | Operations | Leading | Operations Leading | • All digital policies, procedures and digital activities are core to service delivery and business operations • Non-digital services and processes are or have been re-engineered, joined up and re-born as digital • New management practices and organisational structures have emerged or are emerging to align with digital approaches to service delivery across the CHP |  | Digital Channels | [7 empty] | High |  |  |  |  | October | [6 empty] | Quality
|  |  | Organisation, Culture, Governance, Risk & Security | Basic | Organisation, Culture, Governance, Risk & Security Basic | • Limited appetite in the organisation for implementing digital service initiatives • Resistance to change apparent • Limited skill sets in the organisation to effectively embrace digital technology • Limited buy-in from senior management for digital solutions • Digital proposition not fully understood • Limited understanding or application of information management and data security |  | Innovation | [7 empty] | Low |  |  |  |  | November | [6 empty] | Regulations
|  |  | Organisation, Culture, Governance, Risk & Security | Developing | Organisation, Culture, Governance, Risk & Security Developing | • Value proposition of digital beginning to be recognised by management • Some cross-organisational awareness of digital opportunities • Commitment to risk aversion which may be affecting or inhibiting change • Understanding of data security • Growing awareness amongst some staff of how digital applications and tools could be of benefit • Social media channels being monitored / assessed but still viewed as a risk rather than an opportunity |  | Mobile | [12 empty] | December | [6 empty] | Remote Working
|  |  | Organisation, Culture, Governance, Risk & Security | Established | Organisation, Culture, Governance, Risk & Security Established | • Roles and responsibilities for delivering the digital strategy are clear and understood • Benefits of digital channels are well-defined and understood • Staff understand the benefits and opportunities through use of digital applications and channels • Data security and review mechanisms are in place with cyber-security policies established | [21 empty] | Reporting
|  |  | Organisation, Culture, Governance, Risk & Security | Advanced | Organisation, Culture, Governance, Risk & Security Advanced | • Experimentation is encouraged across all channels • Many staff are digitally aware, embrace the digital strategy and support cultural change • Staff have the necessary resources available to them and have had training to fulfil their respective roles for delivering the digital strategy • Staff seek to re-define their roles and KPIs in line with the digital strategy and organisational KPIs • Cybersecurity policies are aligned to the Essential 8 guidelines and are regularly reviewed • A business continuity is in place and is regularly reviewed • Regular training is provided to staff on cyber security | [21 empty] | Resources
|  |  | Organisation, Culture, Governance, Risk & Security | Leading | Organisation, Culture, Governance, Risk & Security Leading | • CHP management fully understands and embraces digital channels, leading by example • All staff are digital aware • Digital culture is fully embedded within the organisation and is continuously being monitored, improved and refined. • Staff pro-actively explore and implement ways to improve operations and productivity using digital tools | [21 empty] | Supply Chain
|  |  | Technology | Basic | Technology Basic | • Limited or no dedicated IT commitment and / or budget for digital initiatives. • Reliant mainly on legacy technologies which may have been in use for some time. • Minimal or no defined IS / IT strategy in place. • Adopts a largely reactive approach to procuring technology and software. • No integration of digital channels with business processes or systems. | [21 empty] | Support
|  |  | Technology | Developing | Technology Developing | • Some integration of digital applications and channels with business processes, systems and communications. • Main focus remains on departmental ITT solutions and not how digital channels could better support customers. • IS / IT strategy being assessed / formulated. • Consideration being given to budget implications of implementing digital applications and tools. | [21 empty] | Tech. Environment
|  |  | Technology | Established | Technology Established | • An IS / IT strategy has been defined with an annual budget allocated with digital transformation initiatives identified and included. • Systems integration either as a fully integrated suite or across multiple systems is in place, which supports the CHP in ensuring the operation of joined-up services and ensuring a 360-degree view of the customer can be maintained. • CHP has an established IT team / department. • IT systems and solutions comply with best practice in business continuity and security. • IT is focussed on delivering the benefits set out in the digital strategy. | [21 empty] | Third-party
|  |  | Technology | Advanced | Technology Advanced | • The IS / IT strategy is aligned to the CHP's business goals and sets out a clear vision for future initiatives and projects, which have been costed for budgetary purposes • IT enhances the delivery of digital services and ease of implementing, maintaining and / or developing new digital services • IT team input ensures digital services are responsive to customers' chosen devices and comply with accessibility standards • IT team is adept at training and supporting CHP staff in use of digital applications, channels and tools | [21 empty] | Training
|  |  | Technology | Leading | Technology Leading | • The IS / IT strategy is entirely aligned to the CHP's vision and business strategy • IT is constantly optimising the benefits of digital service delivery • Resources and budgets are in place for supporting digital channels and activities • Business processes and IT systems are being driven by a combination of digital channels and customer needs • The CHP has resources in place to anticipate and respond to new technologies and digital innovation • Exploring and experimenting with new technology is common practice to identify how it can be best exploited and implemented |  | Processes | [19 empty] | Transformation
|  |  | Strategy | Basic | Strategy Basic | • The CHP may have a business plan but this does not include any provision or clear plan for digital transformation or initiatives • Thinking is still mainly in its infancy with either no or only limited attempts in considering how digital solutions may benefit the CHP and its customers • A website may exist but there is no digital strategy in place
|  |  | Strategy | Developing | Strategy Developing | • Beginning to explore the impact of digital initiatives and how emerging technologies could better support operations and service delivery • Business plan makes reference to potential use of digital applications • Consideration is being given to defining a digital strategy
|  |  | Strategy | Established | Strategy Established | • A digital strategy is in place • The CHP business plan makes specific reference to digital initiatives and how digital can support the business • CHP is focussed on its customers, suppliers and stakeholders together with how emerging technologies can better support their needs • Benefits of social media are understood and drive activity |  | Reporting & Analysis
|  |  | Strategy | Advanced | Strategy Advanced | • Customer needs and expectations are driving innovation in service delivery, either through new services, products and relationships • New methods of delivering services are being actively or continuously explored • The business plan sets out a range of innovative new services and sets out how digital technology can support operations • Digital is fully integrated into organisational plans and the business review cycle |  | Resource Capability
|  |  | Strategy | Leading | Strategy Leading | • The digital strategy is embedded in, and indistinguishable from, the CHP’s vision and business strategy • The CHP, in its entirety, continually seeks ways to use digital channels and technologies to re-define customer services and generate new benefits • New services are born digital as a matter of course i.e., it is considered as part of strategy formulation and not afterwards • Digital services and channels are driving the CHP’s structure and reporting |  | Resource Technical
Structure
System Management
Technology Deployment
Technology Investment
Third-party Partnerships
Vision