## 1. Basic
Tcharts
WIP Schedule — Basic
Five projects. Type the four inputs; every other column calculates itself.
Legend: blue cells with a tan fill are inputs you type · green cells are formulas — don't overwrite them
Project | Contract value | Costs to date | Est. total cost | % complete | Revenue earned | Billings to date | Over/(under) billing
Project A — Office fit-out | 2000000 | 800000 | 1600000 | 50% | 1000000 | 850000 | 150000
Project B — Retail center | 3500000 | 2900000 | 3100000 | 93.55% | 3274193.5484 | 3300000 | -25806.4516
Project C — Warehouse slab | 750000 | 90000 | 600000 | 15% | 112500 | 120000 | -7500
Project D — Bridge repair | 1200000 | 1050000 | 1150000 | 91.3% | 1095652.1739 | 1180000 | -84347.8261
Project E — Mixed-use tower | 6000000 | 1800000 | 5400000 | 33.33% | 2000000 | 1500000 | 500000
Total | 13450000 | 6640000 | 11850000 | 56.03% | 7482345.7223 | 6950000 | 532345.7223

## 2. Intermediate
Tcharts
WIP Schedule — Intermediate
Adds the multi-year split (prior vs current year), cost-to-complete, and retainage.
Legend: blue cells with a tan fill are inputs you type · green cells are formulas — don't overwrite them
Project | Contract value | Costs to date | Est. total cost | % complete | Revenue earned (PTD) | Prior-year revenue | Current-year revenue | Est. cost to complete | Billings to date | Over/(under) billing | Retainage rec.
Project A — Office fit-out | 2000000 | 800000 | 1600000 | 50% | 1000000 | 400000 | 600000 | 800000 | 850000 | 150000 | 100000
Project B — Retail center | 3500000 | 2900000 | 3100000 | 93.55% | 3274193.5484 | 1500000 | 1774193.5484 | 200000 | 3300000 | -25806.4516 | 165000
Project C — Warehouse slab | 750000 | 90000 | 600000 | 15% | 112500 | 0 | 112500 | 510000 | 120000 | -7500 | 12000
Project D — Bridge repair | 1200000 | 1050000 | 1150000 | 91.3% | 1095652.1739 | 600000 | 495652.1739 | 100000 | 1180000 | -84347.8261 | 60000
Project E — Mixed-use tower | 6000000 | 1800000 | 5400000 | 33.33% | 2000000 | 900000 | 1100000 | 3600000 | 1500000 | 500000 | 250000
Total | 13450000 | 6640000 | 11850000 | 56.03% | 7482345.7223 | 3400000 | 4082345.7223 | 5210000 | 6950000 | 532345.7223 | 587000

## 3. Detailed
Tcharts
WIP Schedule — Detailed
Full executive view: balance-sheet split, AR/AP, retainage, and net working capital.
Legend: blue cells with a tan fill are inputs you type · green cells are formulas — don't overwrite them
Project | Contract value | Costs to date | Est. total cost | % complete | Revenue earned (PTD) | Billings to date | Over/(under) billing | Contract asset (under-bill) | Contract liability (over-bill) | Check | Accounts receivable | Retainage rec. | Accounts payable | Net working capital
Project A — Office fit-out | 2000000 | 800000 | 1600000 | 50% | 1000000 | 850000 | 150000 | 150000 | 0 | OK | 120000 | 100000 | 90000 | 280000
Project B — Retail center | 3500000 | 2900000 | 3100000 | 93.55% | 3274193.5484 | 3300000 | -25806.4516 | 0 | 25806.4516 | OK | 210000 | 165000 | 140000 | 209193.5484
Project C — Warehouse slab | 750000 | 90000 | 600000 | 15% | 112500 | 120000 | -7500 | 0 | 7500 | OK | 30000 | 12000 | 45000 | -10500
Project D — Bridge repair | 1200000 | 1050000 | 1150000 | 91.3% | 1095652.1739 | 1180000 | -84347.8261 | 0 | 84347.8261 | OK | 75000 | 60000 | 130000 | -79347.8261
Project E — Mixed-use tower | 6000000 | 1800000 | 5400000 | 33.33% | 2000000 | 1500000 | 500000 | 500000 | 0 | OK | 340000 | 250000 | 220000 | 870000
Total | 13450000 | 6640000 | 11850000 | 56.03% | 7482345.7223 | 6950000 | 532345.7223 | 650000 | 117654.2777 | OK | 775000 | 587000 | 625000 | 1269345.7223
How the split works: a project is either under-billed (a contract asset) or over-billed (a contract liability) — never both.
The IF formula sends the amount to one column and 0 to the other, so the totals don't double-count. The Check column confirms the split ties to the net over/(under) billing.