## Checklist
Tcharts
Accounting Software Migration Checklist
A controller's stage-by-stage guide to implementing a new accounting system
PROGRESS |  | 0 |  |  |  | 0% | 0
0 of 36 applicable tasks complete | [6 empty] | 36
To complete a task, set its Status to “Done” — the ✓ appears and the progress bar fills automatically. Tasks set to “N/A” are excluded from the total.
To customize: right-click a task row and choose Insert to add a task (the dropdown and ✓ copy down). Use Owner, Date, and Notes to run it like a project plan.
✓ Done | Task | What it involves | Owner | Set Status ▾ | Date | Notes
Stage 1 · Planning
| Map the project & stages | Lay out all five stages with dependencies, critical timelines, and the resources/skills each stage needs. |  | Not started
| Set a realistic timeframe | Plan for 3–6 months. Simpler out-of-the-box moves take less; complex multi-site projects take more. |  | Not started
| Build the project plan | Map every stage to a due date and name an owner for each. Track it in a PM tool, Word, or Excel. |  | Not started
| Decide on talent | Choose between an outside implementation/migration consultant and internal staff, based on budget and workload. |  | Not started
| Select the data range to import | Decide how far back history goes, and prepare the tools needed for the migration. |  | Not started
| Choose import depth | Decide whether data comes in as summarized journal entries or at full transaction-detail level. |  | Not started
| Back up critical data & reports | Use a third-party backup before you start, to guard against data loss. |  | Not started
| Confirm & purchase integrations | Lock in every third-party integration you'll use, and budget for it. |  | Not started
| Announce start & end dates | Share the timeline and any incentives to boost team motivation and buy-in. |  | Not started
| Pick the right time of year | Avoid kicking off near key holidays, seasonal peaks, or year-end close. |  | Not started
Stage 2 · Software Set-Up
| Enter the company profile | Company name, logo, address, colors, and welcome messages. |  | Not started
| Add users, roles & permissions | Assign access by role for segregation of duties. Set strong password policies. Chase invites before they expire. |  | Not started
| Enable two-factor authentication | Turn on 2FA, especially for high-access users. Make sure everyone has a phone or authenticator ready. |  | Not started
| Set up security features | Coordinate with any cyber-security firm and finish integrations before real data is entered. |  | Not started
| Set up the chart of accounts | Build the hierarchical list: assets, liabilities, equity, revenue, expenses. |  | Not started
| Add products / services | List everything offered, with pricing and variations. |  | Not started
| Create classification labels | Add tags for cleaner categorization and reporting (e.g., Operational, Marketing, R&D). |  | Not started
| Customize dashboards & reports | Tailor KPIs and report layouts to each role. |  | Not started
| Automate reporting | Schedule recurring reports to stakeholders; configure notifications. |  | Not started
| Connect bank accounts | Link all bank and credit card accounts. |  | Not started
| Connect & test integrations | Wire up billing, expense, payroll, tax, etc. Run mock transactions to confirm each works. |  | Not started
Stage 3 · Data Migration
| Clean up the data first | Remove test/dummy data, fix formatting, standardize names and capitalization before import. |  | Not started
| Enter opening balances | Post a journal entry from a detailed trial balance to set opening balances. |  | Not started
| Import employees | If the system handles time, expenses, or payroll, bring in employee records. |  | Not started
| Import customers | Contact info, credit terms, and any transaction history. |  | Not started
| Import vendors & contractors | Payment terms, contacts, history. Double-check 1099 settings. |  | Not started
| Review & reconcile data | Pull ledger reports and compare to the old system to catch duplicates and errors. |  | Not started
| Save document attachments | Attachments and images usually don't migrate — download, store, and re-upload as needed. |  | Not started
Stage 4 · Training
| Set up users & assign licenses | Confirm every user has the right license for their role before training starts. |  | Not started
| Schedule & hold sessions | Mandatory, role-based, short, interactive, and recorded where possible. Collect feedback after. |  | Not started
| Let users test the system | Before go-live, have users run their real daily tasks in the new system. |  | Not started
| Create training materials | Turn sessions into manuals, video tutorials, and FAQs for new hires and absentees. |  | Not started
Stage 5 · Trial Run / Go-Live
| Announce the go-live date | Best practice: switch on the 1st of a month. Tell clients and stakeholders so they can prepare. |  | Not started
| Run systems in parallel | Keep the old system running alongside the new one (typically 30 days, up to 90 for complex setups). |  | Not started
| Back up old data & reports | Make sure old-system data stays accessible — especially anything auditors or lenders request. |  | Not started
| Implement a bug process | Log issues, work with support to resolve fast, and keep the process running after go-live. |  | Not started
Built by Tcharts · Accrual-based accounting software for growing businesses · tcharts.com