## Timeline
Office of Research — Timeline for Submitting a Grant Proposal
|  | ENTER PROPOSAL DUE DATE: | 2023-10-25
| Timeline |  |  | Activity | Deadline |  |  | Contact
2022-10-25 | Locate opportunity 9-12 months before due date |  |  | Locate opportunity | 2022-10-25 | – | 2023-01-28 | Grant Writer
Locate funding opportunity; determine eligibility; contact and possibly meet Program Officer
2022-11-24 |  |  |  | Start proposal | 2023-01-28 | – | 2023-04-28 | Grant Writer
Start drafting proposal—contact UNO grant writer for assistance; review sponsor guidelines; contact subcontracting entities; review budget templates
2022-12-24
|  |  |  | Submit award proposal | 2023-07-27 | – | 2023-09-25 | Research Administrator
2023-01-23 | Start proposal 6-9 months before due date |  |  | Finalize budget with Research Administrator; attach draft of narrative to award proposal request (you can continue working on your narrative); obtain cost-share approvals from unit administrators
2023-02-22 |  |  |  | Deadline for external review | 2023-08-02 |  |  | Grant Writer
If you HAVE NOT confirmed with a reviewer, submit service request 12 weeks ahead of proposal deadline.
2023-03-24 |  |  |  | Deadline for external review | 2023-08-16 |  |  | Grant Writer
If you HAVE confirmed with a reviewer, submit service request 10 weeks ahead of proposal deadline.
2023-04-23 |  |  |  | In-Depth proposal editing deadline | 2023-08-30 |  |  | Grant Writer
| Continue working on proposal |  |  | If you desire in-depth editing from a grant writer, submit draft proposal with 8 weeks' notice
2023-05-23 |  |  |  | Basic proposal editing deadline | 2023-09-27 |  |  | Grant Writer
If you desire basic editing from a grant writer, submit draft proposal with 4 weeks' notice
2023-06-22 |  |  |  | Deadline for revisions | 2023-10-04 |  |  | Research Administrator
Final day to revise budget as needed; complete non-narrative documents
2023-07-22 |  | Submit award proposal form 1-3 months before deadline | External review | PI document upload | 2023-10-18 |  |  | Research Administrator
Upload to sponsor website; Office of Research can upload, if sponsor allows
2023-08-21 |  |  |  | Final Approval, Office of Research | 2023-10-22 |  |  | Research Administrator
|  |  | Editing deadline | Proposal due date | 2023-10-25 |  |  | Research Administrator
2023-10-04 |  |  | Final Revisions
Visit the UNO Office of Research website to identify the grant writer and research administrator serving your unit.
2023-10-18 |  |  | Document upload
2023-10-22 |  |  | Final Approval
2023-10-25 |  |  | DUE DATE