## APQP_PPAP Checklist ProcessFlow
CORE TEAM CONTENT RESPONSIBILITY
Program Manager
Plant Quality Engineer
Supplier
Corporate Supplier Quality
Responsiblility | Step |  | Timing | Team
Program Manager | Send APQP / PPAP Checklist |  | Start of Program | Program Manager
to suppliers
Send updated document based on Status
Supplier | of each element |  | Monthly | Supplier
Program Manager | Review document and report out any |  | Monthly | Program Manager
| at risk elements |  |  | Plant Quality Engineer
Program Manager
| Review at risk elements with supplier |  | Monthly - If warranted | Plant Quality Engineer
Program Manager | and respective departments within Teijin |  |  | Supplier
| Automotive Technologies |  |  | Corp Supplier Quality
*
*Note: additional departments may
need to be involved depending
elements that are at risk.
APQP / PPAP Checklist - Suppliers
Continuous loop until completion of APQP / PPAP Approval
Continuous loop until APQP Complete
PPAP Approval

## PPAP Review Sheet
PPAP Review Guide | [10 empty] | PPAP Risk: | Medium
[12 empty] | PPAP Recommendation: | Maybe Approved, noting issues
Note: All documentation must be legible
Comments
|  |  | PPAP Team Lead: |  | Auditor/Team:
Supplier Name:
|  |  | Part No.: |  | Design Level: | MY:
|  |  | PPAP No. | Family (Y/N): |  | Date:
| CHECKLIST | [5 empty] | Yes | No | N/A | Comments
| 2 | Is Part #, Description, and Revision level documented and correct?
| 3 | Are all selected elements appropriate for submission? Appropriate A, B, C analysis
| 4 | Does checklist note regulatory or CoP attribute requirements? If required per design record
1 | WARRANT [PSW] | [5 empty] | Yes | No | N/A | Comments
| 1 | Is the warrant Current AIAG edition compliant?
| 2 | Does warrant include correct Part number and Revision level?
| 3 | Are all required sections filled in by supplier?
| 4 | Is warrant signed by supplier representative?
2 | DESIGN RECORD | [5 empty] | Yes | No | N/A | Comments
| 1 | Are print(s) included to authorized revision level?
| 2 | Are prints of components and details included?
| 3 | Are supplier prints included? Check N/A if no supplier prints are required
| 4 | Are KPC(s), KCC(s), SC's and CoP/Regulatory attributes called out on the drawing?
| 5 | Has GD&T been agreed upon, and specified on the drawing?
| 6 | Are there any Special Characteristics, and if so, detailed on the drawing?
3 | AUTHORIZED ENTERPRISE CHANGE DOCUMENTS | [5 empty] | Yes | No | N/A | Comments
| 1 | Are all Enterprise Change documents closed and approved? Note: PPAP cannot be approved to an ECN
4 | ENGINEERING APPROVAL as required per print | [5 empty] | Yes | No | N/A | Comments
| 1 | Is engineering approval provided where required? Check N/A if approval is not required
5 | DESIGN FAILURE MODE & EFFECTS ANALYSIS [DFMEA] | [5 empty] | Yes | No | N/A | Comments
| 1 | Are part number and revision level noted ?
| 2 | Are potential KPC(s), KCC(s), SC's and CoP/Regulatory attributes assigned correctly?
6 | PROCESS FLOW DIAGRAMS [PFD] | [5 empty] | Yes | No | N/A | Comments
| 1 | Are part number and revision level noted?
| 2 | Are process steps listed, including outside services, or process graphically shown?
| 3 | Is the Supply Chain represented and included?
| 4 | Is rework included on the flow diagram? If rework is part of normal processing
| 5 | Have proprietary Process Flow Diagrams been reviewed and approved?
7 | PROCESS FAILURE MODE & EFFECTS ANALYSIS [PFMEA] | [5 empty] | Yes | No | N/A | Comments
| 1 | Are part number and revision level noted?
| 2 | Is the PFMEA consistent with the process flow diagram?
| 3 | Are KPC(s), KCC(s), SC's and CoP/Regulatory attributes included, if shown on design record?
| 4 | Are Failures consistent and appropriate?
| 5 | Are Effects consistent and appropriate with Failure Modes?
| 6 | Are Causes consistent and appropriate with Failure Modes?
| 7 | Are Controls (Prevention and Detection) consistent and appropriate with Failure Modes and Causes?
| 8 | Are Severity, Occurrence and Detection ratings consistent and appropriate?
| 9 | Are RPNs consistent with ratings and appropriately addressed?
| 10 | Are Recommended Actions documented and appropriate?
| 11 | Have proprietary PFMEAs been reviewed and approved?
8 | CONTROL PLAN | [5 empty] | Yes | No | N/A | Comments
| 1 | Are part number and revision level noted?
| 2 | Is control plan consistent with the process flow diagram and PFMEA?
| 3 | Are gages and checking aids noted?
| 4 | Are KPC(s), KCC(s), SC's and CoP/Regulatory attributes included, if shown on design record?
| 5 | Are controls and gages appropriate for tolerances, process and product characteristics, etc?
| 6 | Are dimensions/tolerances consistent with print and is sampling plan appropriate for dimensions/tolerances?
| 7 | Is Reaction Plan included?
| 8 | Have proprietary Control Plans been reviewed and approved?
9 | MEASUREMENT SYSTEM ANALYSIS STUDIES | [5 empty] | Yes | No | N/A | Comments
| 1 | Was Measurement Systems Analysis (GR&Rs) performed on all checking aids and/or special gages?
| 2 | Are all gage R&R's results <10%?
| 3 | If R&R results >10% to < 30%, Is there evidence of management review for acceptability?
| 4 | Are R&R results > 30%?
| 5 | Are attribute gage studies completed using non-conforming parts?
10 | DIMENSIONAL RESULTS | [5 empty] | Yes | No | N/A | Comments
| 1 | Is a fully bubbled print included? Can be part of Design Record
| 2 | Is part number and revision level documented?
| 3 | Are actual results recorded for five samples (or for # of samples requested)?
| 4 | Are actual results recorded for all mold cavities?
| 5 | Are results recorded for all dimensions, specifications, and notes? (may be noted on print)
| 6 | Are specification and tolerance included to compare to result?
| 7 | Do all results fall within specification limits?
| 8 | Are KPC(s), KCC(s), SC(s,) CoP/Regulatory attributes dimensions identified? Check N/A if not required
11 | MATERIAL / PERFORMANCE TEST RESULTS | [5 empty] | Yes | No | N/A
| 1 | Are there acceptable test results for all tests noted on print & control plan?
| 2 | Are there acceptable test results for all SAE, ASTM and other specifications noted on print & control plan?
| 3 | Do material test results include part number and meet what is specified on design record?
| 4 | Do performance test reports show who performed tests, date of test, number parts tested, change level of parts tested, and specification & change level parts were tested to?
| 5 | Are test results on lab letterhead or laboratory report format?
| 6 | Is documentation supplied for all Regulatory / "Conformance of Production" / Homologation compliance requirements identified on the design record? (documentation, including the Certification Cover Sheet HS2.05.44, to be forwarded to CoP representative and stored in Certification Repository)
12 | INITIAL PROCESS CAPABILITY | [5 empty] | Yes | No | N/A | Comments
| 1 | Was capability study performed per acceptable standards? control charts, 100pcs, etc
| 2 | Are capability results reported for all KPC(s), KCC(s), SC's or other features as required?
| 3 | Are SC attributes equal or greater than 1.33 or inspected at 100%?
| 4 | Are KPC or KCC attributes equal or greater than 1.67 or inspected at 100%?
13 | QUALIFIED LABORATORY DOCUMENTATION | [5 empty] | Yes | No | N/A | Comments
| 1 | Is laboratory accredited for tests conducted? (Third party only)
| 2 | Is A2LA, ISO 17025 or etc. certification and scope provided for tests conducted? (does not include QMS certification)
14. | COSMETIC VALIDATION REPORT (CVR) or Appearance Approval Report (AAR) | [5 empty] | Yes | No | N/A | Comments
| 1 | Is cosmetic validation form submitted, completed, and approved?
17 | CHECKING AIDS | [5 empty] | Yes | No | N/A | Comments
| 1 | Is Checking Aid noted on warrant with correct Change Level and date?
| 2 | Does the checking aid agree with part dimensional requirements? Includes layout, drawings proof of calibration, etc
18 | RECORDS OF COMPLIANCE TO CUSTOMER-SPECIFIC REQUIREMENTS | [8 empty] | Comments
a | Certification of number of pieces run | [5 empty] | Yes | No | N/A | Comments
| 1 | Were 300 consecutive pieces produced or Customer documented approval for lesser quantity?
| 2 | Is the declaration signed by appropriate supplier representative?
b | Tooling Photograph (for customer owned tooling) | [5 empty] | Yes | No | N/A | Comments
| 1 | Are all tool photos included and legible? Photos of ownership, entire tool and tool detail that holds or produces part
| 2 | Are tools properly marked? Tool Number, Property, Part Number
c | Additional Requirements | [5 empty] | Yes | No | N/A | Comments
| 1 | Are additional requirements provided as noted?
| 2 | Are all exceptions documented?
| 3 | Run at Rate
| 4 | IMDS Submission

## APQP Review Sheet
APQP Review Guide | [10 empty] | APQP Risk: | Medium
[12 empty] | APQP Recommendation: | Maybe Approved, noting issues
Note: All documentation must be legible
Comments
|  |  | Team Lead: |  | Auditor/Team:
Supplier Name:
|  |  | Part No.: |  | Design Level: | MY:
|  |  | PPAP No. | Family (Y/N): |  | Date:
| GENERAL |  |  |  |  | Low | Yes | No | N/A | Comments
| 1 | Organize the Team |  |  |  |  | x
| 2 | Define Scope |  |  |  |  | x
| 3 | Timing - Project Tracker |  |  |  |  | x
1 | PLAN AND DEFINE |  |  |  |  | Low | Yes | No | N/A | Comments
| 1 | Program Timing |  |  |  |  | x
| 2 | Engineering BOM |  |  |  |  | x
| 3 | Design Feasibility Study |  |  |  |  | x
| 4 | Preliminary Process Flow Chart |  |  |  |  | x
| 5 | Preliminary List of special product and process characteristics |  |  |  |  | x
| 6 | Capacity Study/Capital Lineup |  |  |  |  | x
| 7 | Tooling Lineup |  |  |  |  | x
| 8 | Lessons Learned |  |  |  |  | x
2 | PRODUCT DESIGN AND DEVELOPMENT |  |  |  |  | Medium | Yes | No | N/A | Comments
| 1 | DFMEA |  |  |  |  | x
| 2 | Design for Manufacturability and Assesmbly |  |  |  |  | x
| 3 | Design Verification |  |  |  |  | x | x
| 4 | Proto-type build Control Plan |  |  |  |  | x
| 5 | Engineering Drawings (including math data / datums / special characteristics) |  |  |  |  | x
| 6 | Engineering Specifications |  |  |  |  | x
| 7 | Material Specifications |  |  |  |  | x
| 8 | New Equipment, tooling, and facilities requirements |  |  |  |  | x
| 9 | Special Product and Process Characterisitcs |  |  |  |  | x
| 10 | Gages (including datums based on sub-assembly functionality / special characteristics) and Testing Requirements |  |  |  |  | x
3 | PROCESS DESIGN AND DEVELOPMENT |  |  |  |  | Medium | Yes | No | N/A | Comments
| 1 | Packaging Standards and specifications |  |  |  |  | x
| 2 | Product / Process Quality System Review | [5 empty] | x
| 3 | Process Flow Chart |  |  |  |  | x
| 4 | Floor Plan Layout |  |  |  |  | x
| 5 | Charactersitic Matrix |  |  |  |  | x
| 6 | PFMEA |  |  |  |  | x
| 7 | Pre-Launch Control Plan (including error-proofing devices) |  |  |  |  | x
| 8 | Process Instructions |  |  |  |  | x
| 9 | Measurement System Analysis Plan |  |  |  |  | x
| 10 | Preliminary Process Capability Study Plan |  |  |  |  | x
4 | PRODUCT AND PROCESS VALIDATION |  |  |  |  | Low | Yes | No | N/A | Comments
| 1 | Significant production run |  |  |  |  | x
| 2 | Measurement System Analysis |  |  |  |  | x
| 3 | Preliminary Process Capability Study |  |  |  |  | x
| 4 | Production Part Approval - Received / Reviewed PPAP Checklist |  |  |  |  | x
| 5 | Packaging Evaluation |  |  |  |  | x
| 6 | Production Control Plan |  |  |  |  | x
| 7 | Quality Planning sign-off and meanagement support |  |  |  |  | x
5 | FEEDBACK, ASSESSMENT, AND CORRECTIVE ACTION |  |  |  |  | Low | Yes | No | N/A | Comments
| 1 | Reduced Variation |  |  |  |  | x
| 2 | Improvement delivery and service |  |  |  |  | x
| 3 | Effective use of Lessons Learned/Best Practices |  |  |  |  | x
Note on L14: Kristen Gilgenbach: >= 5 - High 4 to 1 - Medium <1 - Low

## Flow and Gateway Reviews (hidden)
CORE TEAM CONTENT RESPONSIBILITY
Program Manager
Plant Launch Leader
Product Engineer
Manufacturing Engineer
Tooling Engineer
Commercial Manager
Sign-Off Description | Content |  | Records | Attendees / Signatures
| General Program Information |  |  | Commercial Manager
#1 | Core Team Established |  | Signed Gate #1 Checklist Form | Product Engineer
Program Kick-Off | Initial Launch Tracker |  | Supporting Content Documents | Program Manager
| Financial/PO Terms & Condiitions |  |  | Tooling Engineer
| Target Agreements / Sourcing Letter |  |  | Manufacturing Engineer
| Warranty Responsibility |  |  | Engineering Director
| Design Responsibility |  |  | CSP Plant Quality
| Analysis Responsibility |  |  | VP Engineering
| Testing Responsibility |  |  | CSP Plant Manager (or designee)
| Customer Statement of Work |  |  | Plant Launch Leader/Process Engr
| Payment/Productivity Terms |  |  | Corporate Quality
| CSP Program Authorization (PRF) |  |  | Corporate Purchasing
Freight & Packaging Terms
| Program Timing |  |  | Review: Monthly Engrg Mgmt Meeting
Engineering BOM
Design Feasibility Study
Capacity Study/Capital Lineup
Tooling Lineup
Surrogate Lessons Learned
Signed Gate #1 Checklist
Program Open Issues
Program Timeline Update
#2 | DFMEA (Draft)
Design | CAE Report
DVP&R
Engineering BOM
| Launch Tracker Updated |  | Signed Gate #2 Checklist Form | Commercial Manager
| GD&T / Inspection Plan |  | Supporting Content Documents | Product Engineer
| Math Data Release |  |  | Program Manager
| Material Shrink Factor Worksheet |  |  | Tooling Engineer
| Product Design Team Approval Form |  |  | Manufacturing Engineer
| Manufacturing Team Approval Form |  |  | Product Engineering Director
| Load Pattern Form E-111 |  |  | CSP Plant Quality
| Status of Tooling Sign-Offs |  |  | CSP Launch Leader/Process Engineer
| Status of Capital Equipment Sign-Offs |  |  | Corporate Quality
| Status of WIP & Shipping Rack Sign-Offs |  |  | Corporate Purchasing
Initial Program Lessons Learned
| Design Feasibility Concerns |  |  | Review: Weekly Engrg Dept Meeting
Supplier Selection / Risk Assesment List
Signed Gate #2 Checklist
Commercial Manager
#3 | Program Open Issues |  |  | Product Engineer
Manufacturing Plan | Program Timeline Update |  |  | Program Manager
| Prototype Control Plan |  |  | Tooling Engineer
| Load Pattern Form E-111 (Update) |  |  | Manufacturing Engineer
| Initial Launch Readiness Assessment Form |  | Signed Gate #3 Checklist Form | Product Engineering Director
| Launch Tracker Updated |  | Supporting Content Documents | CSP Plant Manager
| Process Flow Diagrams |  |  | CSP Plant Quality Representative
| PFMEA Update |  |  | CSP Launch Leader/Process Engineer
| Production Control Plans |  |  | Corporate Quality
| Status of Tooling Sign-Offs |  |  | Corporate Purchasing
Status of Capital Equipment Sign-Offs
Status of WIP & Shipping Rack Sign-Offs
Plant Floor Layout Update
Program Lessons Learned Update
Team Feasibility Commitment Form
Manpower, Hiring & Training Plan
Signed Gate #3 Checklist
Program Open Issues
#4 | Program Timeline Update |  | Signed Gate #4 Checklist Form | Product Engineer
Launch Readiness | Plant Enterprise System Manf. BOM |  | Supporting Content Documents | Program Manager
| Control Plan |  |  | Tooling Engineer
| PFMEA Update |  |  | Manufacturing Engineer
| Operator/Work Instructions |  |  | Product Engineering Director
| Sub-Supplier PPAPs |  |  | CSP Plant Manager
| Status of Tooling Sign-Offs |  |  | CSP Plant Quality Representative
| Status of Capital Equipment Sign-Offs |  |  | CSP Launch Leader/Process Engineer
| Status of WIP & Shipping Rack Sign-Offs |  |  | Corporate Quality
| Country of Origin Uploaded to Customer System (if required) |  |  | Corporate Purchasing
DVP&R
Final Launch Readiness Assessment Form
Ramp Up & Rack Delivery Schedule
Program Lessons Learned Update
Launch Tracker Updated
Load Pattern Form E-111 (Update)
| Signed Gate #4 Checklist |  |  | Product Engineer
Program Manager
Tooling Engineer
| Tooling Invoiced |  |  | Manufacturing Engineer
#5 | PPAP Package |  | Signed Gate #5 Checklist Form | Product Engineering Director
Launch Validation | Launch Alerts |  | Supporting Content Documents | CSP Plant Quality Representative
Lessons Learned | Final Program Lessons Learned |  |  | CSP Launch Leader/Process Engineer
| Launch Tracker Review |  |  | Corporate Quality
| Load Pattern Form E-111 (Update) |  |  | Corporate Purchasing
Signed Gate #5 Checklist
Program Team Gateway Sign-Offs

## APQP Elements (hidden)
APQP Element
1 | Design Review
2 | Drawings and Specifications
3 | Preliminary Bill of Materials
4 | Design Failure Mode Analysis (DFMEA)
5 | Design Verification Requirements
6 | Design DVP&R
7 | Design Verification Test Review
8 | Preliminary Process Flow Diagram
9 | Utilities Plan, Layout Plan & Manpower Plan
10 | Tooling and Inspection Equipment
11 | Prototype Process Flow Chart, FMEA, Control Plan
12 | Logistics and Packaging Internal / External
13 | Pre-Production Process Flow Diagram, PFMEA, CP
14 | Production Test and Measuring Equipment
15 | Planned Maintenance and Key Spares Requirement
16 | Process PPAP and Capacity Planning
17 | Sub-Supplier Selection - Direct Materials
18 | Sub-Supplier - Capital Equipment and Tooling
19 | Sub-Supplier Program Staus Matrix
20 | Pre-Production Process Flow Diagram
21 | Tooling
22 | Pre-Production Control Plan
23 | Operator Inspection / Process Instructions
24 | Preliminary Capability Studies
25 | Production Test and Measuring Equipment
26 | Document Review
27 | Process Capacity Sign-off
28 | Product and Process Sign-off (Phase-1 Parts)
29 | Product and Process Sign-off (Phase-2 Parts)
30 | Sub-Supplier - Direct Materials