## Slide 1
Milestone | Participants | Typical Activities
Discovery and Ambition | Top executive team Cross-section of senior leaders (20-30) | Setting scope and design parameters Interviewed during data gathering Feedback re interview findings and fine-tuning themes Finalizing the problem to solve
Architecture | Cross-section of leadership from levels, functions, geos, etc. (30-100 or more) Design teams for specific functions and/or business units | Large-group design workshops to understand case for change, review and refine design ideas Design teams complete assigned design tasks Executive team finalizes architecture choices
Integration | Multiple sets of cross-functional groups Design teams focused on cross-functional ways of working Altogether may include a few hundred leaders from all areas of the business | Large or small-group design workshops to identify key points of interaction Begin process redesign efforts Develop interaction models and provide input on decision tension areas and guardrails Complete detailed design work in specific parts of the business
Leadership | Top executive team and selective managers from one or more layers below | Designing the role of the top team, meeting cadence, agendas, etc. Overseeing the staffing selection process for new roles Defining key management processes, e.g. talent management, etc.
Transition | Implementation teams working across various element of the new operating model | Continued process redesign initiatives Continued layer-by-layer structure design Talent development initiatives
Options for engaging people in the design process: high involvement design by milestone.
M1.19