## Sheet2
#VALUE!
The Ultimate Change Control Workflow Checklist A Guide to Building an Effective Change Control Process
A well-designed change control process is the backbone of GxP compliance. It ensures that every change is managed, documented, verified, and audit-ready. But how do you know if your workflow is truly robust? Use this checklist to help design a new change control process from the ground up or to audit your existing workflow for potential gaps.
PART 1 Foundational Workflow Design This section covers the essential structure and logic of your process.
Checklist Item | Yes/No | Notes
Defined Stages Does your change control workflow include distinct, mandatory stages for:
Change Request/Initiation? Capturing the "what," "why," "where," "when," and "who." | FALSE
Risk Assessment & Planning? Evaluating risk and defining tasks. | FALSE
Pre-Implementation Approval? A formal approval before work begins. | FALSE
Implementation? Executing the planned tasks. | FALSE
Verification/Validation? Proving the change was successful. | FALSE
Final Approval & Closure? Officially approving and closing the record. | FALSE
Process Logic
Do you have a defined process path for Emergency Changes that allows for expedited approval and post-facto documentation? | FALSE
Is there a formal change control cancellation workflow when a change is determined to no longer be necessary? | FALSE
Is there a rework workflow? If verification fails, can the workflow be routed back to the implementation stage with clear instructions? | FALSE
Categorization
Do you have defined Change Categories (e.g., General, Software, Vendor, etc.)? | FALSE
Are the fields and required information tailored for each category? (e.g., asking for "Supplier Criticality" only on a Vendor change). | FALSE
PART 2 Risk Assessment & Implementation Planning This section ensures your workflow requires the input of information critical for success.
Checklist Item | Yes/No | Notes
Risk Assessment Prompts Does your process require the team to formally assess the impact on:
Product Quality, Safety, and Efficacy | FALSE
Validated Systems (Does this change require re-validation?) | FALSE
Regulatory Filings or Submissions | FALSE
Other Departments or Processes | FALSE
Existing SOPs, Work Instructions, and other Documentation | FALSE
Employee Training Requirements | FALSE
Implementation Plan
Does the plan require a list of specific, actionable tasks? | FALSE
Is each task assigned to a named individual? | FALSE
Are due dates required for each task? | FALSE
Does the plan define how the change's effectiveness will be verified? | FALSE
PART 3 Audit Readiness & Compliance This section ensures your process generates a defensible, auditable record.
Checklist Item | Yes/No | Notes
Evidence-Based Closure:
Does your process require objective evidence to be uploaded for each implementation and verification task? (e.g., updated documents, test results, screenshots, photos). | FALSE
Traceability
Are all approvals captured with 21 CFR Part 11-compliant electronic signatures (including name, date, and time)? | FALSE
Can you easily link the change control record to other quality records (e.g., the CAPA that prompted it, the documents it revised)? | FALSE
Reporting & Oversight
Can you easily track the status of all open change controls? | FALSE
Can you measure key metrics like average time to closure or most overdue change control categories to identify process bottlenecks? | FALSE
PART 4 Your plan is complete. Now, let's automate it.
This completed checklist serves as the blueprint for a compliant, robust change control process. While it's possible to manage this process manually, doing so with spreadsheets and email introduces risk, creates administrative burden, and makes auditing difficult. The logical next step is to translate this workflow into a flexible electronic Quality Management System (eQMS). An eQMS allows you to configure these stages, rules, and requirements directly into the system, giving you automated notifications, integrated records, and audit-ready data at your fingertips.
Want to see how it works? We can show you.